## Schedules
Schedule - List - 150 Banksia Street, Ivanhoe - FC (exported on May 13, 2026)
ID # | Title | Complete | Percent Complete | Phase | Duration | Start | End | Assigned To | Accepted | Pending | Declined | Pred 1 Id | Pred 1 Type | Pred 1 Lag | Pred 2 Id | Pred 2 Type | Pred 2 Lag
1 | Client to confirm order&Delivery of all CTS items | FALSE | 0 | Site Preparation | 1 | 2026-06-05 | 2026-06-05 |  | 0 | 0 | 0 | 2 | FS | -1
2 | PRECON CHECKLIST | FALSE | 0 | Site Preparation | 1 | 2026-06-05 | 2026-06-05 |  | 0 | 0 | 0
3 | Asbestos Testing (if req'd) | FALSE | 0 | Demolition | 1 | 2026-06-09 | 2026-06-09 |  | 0 | 0 | 0 | 1 | SS | 1
4 | Electrical Make Safe | FALSE | 0 | Site Preparation | 1 | 2026-06-09 | 2026-06-09 |  | 0 | 0 | 0 | 3 | SS | 0
5 | Neighbour Notification | FALSE | 0 | Site Preparation | 1 | 2026-06-09 | 2026-06-09 |  | 0 | 0 | 0 | 4 | SS | 0
6 | Plumbing Make Safe | FALSE | 0 | Site Preparation | 1 | 2026-06-09 | 2026-06-09 |  | 0 | 0 | 0 | 5 | SS | 0
7 | Pre-Demo Meeting | FALSE | 0 | Demolition | 1 | 2026-06-09 | 2026-06-09 |  | 0 | 0 | 0 | 6 | SS | 0
8 | Site Setup / Protection/ Cameras etc | FALSE | 0 | Site Preparation | 1 | 2026-06-09 | 2026-06-09 | John Bainbridge | 0 | 0 | 0 | 7 | SS | 0
9 | Skip Bin Delivery | FALSE | 0 | Site Preparation | 1 | 2026-06-09 | 2026-06-09 |  | 0 | 0 | 0 | 8 | SS | 0
10 | Sub-Floor Plumbing Camera/Test | FALSE | 0 | Steel Work | 1 | 2026-06-09 | 2026-06-09 |  | 0 | 0 | 0 | 6 | FS | -1
11 | Demolition - Simcat TBC | FALSE | 0 | Demolition | 3 | 2026-06-11 | 2026-06-15 |  | 0 | 0 | 0 | 9 | FS | 1
12 | Frame & Subfloor Assessment | FALSE | 0 |  | 1 | 2026-06-16 | 2026-06-16 | Dale Psaila, Lachlan Findlay | 0 | 0 | 0 | 11 | FS | 0
13 | Framing | FALSE | 0 | Steel Work | 5 | 2026-06-16 | 2026-06-22 | Dale Psaila, Lachlan Findlay | 0 | 0 | 0 | 11 | FS | 0
14 | Subfloor Frame (if Req) | FALSE | 0 | Steel Work | 1 | 2026-06-17 | 2026-06-17 | Dale Psaila, Lachlan Findlay | 0 | 0 | 0 | 12 | FS | 0
15 | Plumbing Rough In (Subfloor) | FALSE | 0 |  | 1 | 2026-06-18 | 2026-06-18 |  | 0 | 0 | 0 | 14 | FS | 0
16 | Sheet Flooring | FALSE | 0 | Steel Work | 1 | 2026-06-19 | 2026-06-19 | Dale Psaila, Lachlan Findlay | 0 | 0 | 0 | 15 | FS | 0
17 | Electrical Rough-In | FALSE | 0 | Internal Works | 2 | 2026-06-23 | 2026-06-24 |  | 0 | 0 | 0 | 16 | FS | 1
18 | Frame Inspection | FALSE | 0 | Steel Work | 1 | 2026-06-23 | 2026-06-23 |  | 0 | 0 | 0 | 13 | FS | 0
19 | Frame Progress Claim | FALSE | 0 | Steel Work | 1 | 2026-06-24 | 2026-06-24 |  | 0 | 0 | 0 | 18 | FS | 0
20 | Plumbing Rough In & SW | FALSE | 0 | Internal Works | 1 | 2026-06-25 | 2026-06-25 |  | 0 | 0 | 0 | 17 | FS | 0
21 | Pre- Insulation Inspection/Camera | FALSE | 0 | Internal Works | 1 | 2026-06-26 | 2026-06-26 |  | 0 | 0 | 0 | 20 | FS | 0
22 | Insulation Install | FALSE | 0 | Internal Works | 1 | 2026-06-29 | 2026-06-29 |  | 0 | 0 | 0 | 21 | FS | 0
23 | Plaster Install | FALSE | 0 | Finishing & Handover | 2 | 2026-06-30 | 2026-07-01 |  | 0 | 0 | 0 | 22 | FS | 0
24 | Waterproofing | FALSE | 0 |  | 2 | 2026-07-02 | 2026-07-03 | Expo Marble & Tiling | 0 | 0 | 0 | 23 | FS | 0
25 | Internal Fixing | FALSE | 0 | Finishing & Handover | 2 | 2026-07-03 | 2026-07-06 | Dale Psaila, Lachlan Findlay | 0 | 0 | 0 | 24 | FS | -1
26 | Prime Walls | FALSE | 0 | Finishing & Handover | 2 | 2026-07-07 | 2026-07-08 |  | 0 | 0 | 0 | 25 | FS | 0
27 | Tiling | FALSE | 0 |  | 5 | 2026-07-09 | 2026-07-15 | Expo Marble & Tiling | 0 | 0 | 0 | 24 | FS | 3
28 | Mirrors and Glasswork | FALSE | 0 | Finishing & Handover | 1 | 2026-07-14 | 2026-07-14 |  | 0 | 0 | 0 | 27 | FS | -2
29 | Electrical Fitoff | FALSE | 0 | Finishing & Handover | 1 | 2026-07-16 | 2026-07-16 |  | 0 | 0 | 0 | 27 | FS | 0
30 | Plumbing Fitoff | FALSE | 0 | Finishing & Handover | 1 | 2026-07-16 | 2026-07-16 |  | 0 | 0 | 0 | 27 | FS | 0
31 | Painting - Interior | FALSE | 0 | Finishing & Handover | 3 | 2026-07-17 | 2026-07-21 |  | 0 | 0 | 0 | 30 | FS | 0 | 29 | FS | 0
32 | TH Pre-Final Inspection | FALSE | 0 | Finishing & Handover | 1 | 2026-07-21 | 2026-07-21 |  | 0 | 0 | 0 | 31 | FS | -1
33 | Interior Hardware Install | FALSE | 0 | Finishing & Handover | 1 | 2026-07-22 | 2026-07-22 | Dale Psaila, Lachlan Findlay | 0 | 0 | 0 | 31 | FS | 0
34 | Final Building Inspection | FALSE | 0 | Finishing & Handover | 1 | 2026-07-23 | 2026-07-23 |  | 0 | 0 | 0 | 33 | FS | 0
35 | Completion/Final Walkthrough | FALSE | 0 | Finishing & Handover | 1 | 2026-07-24 | 2026-07-24 |  | 0 | 0 | 0 | 34 | FS | 0
36 | Final Progress Claim | FALSE | 0 | Finishing & Handover | 1 | 2026-07-27 | 2026-07-27 |  | 0 | 0 | 0 | 35 | FS | 0
37 | HAND OVER | FALSE | 0 | Finishing & Handover | 1 | 2026-07-27 | 2026-07-27 |  | 0 | 0 | 0 | 35 | FS | 0