## Schedules
Schedule - List - 30 Connolly Ave, Coburg - FC (exported on May 13, 2026)
ID # | Title | Complete | Percent Complete | Phase | Duration | Start | End | Assigned To | Accepted | Pending | Declined | Pred 1 Id | Pred 1 Type | Pred 1 Lag | Pred 2 Id | Pred 2 Type | Pred 2 Lag | Pred 3 Id | Pred 3 Type | Pred 3 Lag
1 | Site meeting | TRUE | 100 | Deliveries & Meetings | 1 | 2026-01-13 08:00 | 2026-01-13 | Oliver Trifunovski | 0 | 0 | 0
2 | Client meeting / Delap Photos | TRUE | 100 | Deliveries & Meetings | 1 | 2026-01-16 13:00 | 2026-01-16 | Oliver Trifunovski | 0 | 0 | 0
3 | PRE-CONSTRUCTION | TRUE | 100 | Site Preparation | 1 | 2026-01-19 | 2026-01-19 | John Bainbridge, Oliver Trifunovski | 0 | 0 | 0
4 | Site Setup (Temp Fence, Toilet, Make Safe) | TRUE | 100 | Site Preparation | 4 | 2026-01-19 | 2026-01-22 | John Bainbridge, Oliver Trifunovski | 0 | 0 | 0 | 3 | FS | -1
5 | Electrical make safe | TRUE | 100 | MEP | 1 | 2026-01-21 | 2026-01-21 | DECAV Pty Ltd, Oliver Trifunovski | 0 | 0 | 0
6 | Plumbing make safe | TRUE | 100 | MEP | 1 | 2026-01-21 | 2026-01-21 | JCB Plumbing & Maintenance, Oliver Trifunovski | 0 | 0 | 0
7 | Site setup | TRUE | 100 | Site Preparation | 1 | 2026-01-21 | 2026-01-21 | John Bainbridge, Oliver Trifunovski | 0 | 0 | 0
8 | Demolition & Waste Management | TRUE | 100 | Demolition | 8 | 2026-01-22 | 2026-02-03 | Oliver Trifunovski, Simcat Demolitions | 0 | 0 | 0 | 4 | FS | -1
9 | Demolition Simcat | TRUE | 100 | Demolition | 8 | 2026-01-22 | 2026-02-03 | Oliver Trifunovski, Simcat Demolitions | 0 | 0 | 0
10 | Site Set Out | TRUE | 100 | Site Preparation | 1 | 2026-02-05 | 2026-02-05 | James Quinn, Oliver Trifunovski | 0 | 0 | 0 | 8 | FS | 1
11 | Site setout | TRUE | 100 | Site Preparation | 1 | 2026-02-05 | 2026-02-05 | James Quinn, Oliver Trifunovski | 0 | 0 | 0
12 | Bingo 6m³ Marell | TRUE | 100 |  | 1 | 2026-02-12 | 2026-02-12 | Oliver Trifunovski | 0 | 0 | 0
13 | Bored Piers | TRUE | 100 | Earthworks | 2 | 2026-02-12 | 2026-02-13 | Oliver Trifunovski, RDF Landscaping & Excavation | 1 | 1 | 0
14 | Earthworks & Bored Piers | TRUE | 100 | Earthworks | 2 | 2026-02-12 | 2026-02-13 | Oliver Trifunovski, RDF Landscaping & Excavation | 0 | 0 | 0 | 10 | FS | 4
15 | Concrete Footings & Blinding | TRUE | 100 | Labourers | 1 | 2026-02-17 | 2026-02-17 | James Quinn, Oliver Trifunovski | 0 | 0 | 0 | 14 | FS | 1
16 | Concrete to bored piers | TRUE | 100 |  | 1 | 2026-02-17 | 2026-02-17 | Oliver Trifunovski | 0 | 0 | 0
17 | Steel measure Ron | TRUE | 100 |  | 1 | 2026-02-20 | 2026-02-20 | Oliver Trifunovski | 0 | 0 | 0
18 | Structural Steel Measure | TRUE | 100 | Steel Work | 1 | 2026-02-20 | 2026-02-20 | Oliver Trifunovski, Sutton Steel | 0 | 0 | 0 | 15 | FS | 2
19 | Carpentry | TRUE | 100 |  | 2 | 2026-02-26 | 2026-02-27 | Oliver Trifunovski | 0 | 0 | 0
20 | Subfloor, Stumps, Bearers & Joists | TRUE | 100 | Carpentry | 2 | 2026-02-26 | 2026-02-27 | James Quinn, Oliver Trifunovski | 0 | 0 | 0 | 15 | FS | 6
21 | VM Mini .6m³ 25mpa | TRUE | 100 |  | 1 | 2026-02-26 13:30 | 2026-02-26 | Oliver Trifunovski | 0 | 0 | 0
22 | Steel install | TRUE | 100 |  | 1 | 2026-02-27 | 2026-02-27 | Oliver Trifunovski, Sutton Steel | 0 | 0 | 0
23 | Structural Steel Installation | TRUE | 100 | Steel Work | 1 | 2026-02-27 | 2026-02-27 | Oliver Trifunovski, Sutton Steel | 0 | 0 | 0 | 18 | FS | 4
24 | Subfloor inspection | TRUE | 100 |  | 1 | 2026-02-27 | 2026-02-27 | Oliver Trifunovski | 0 | 0 | 0
25 | Capentry Works | TRUE | 100 |  | 1 | 2026-03-04 | 2026-03-04 | Oliver Trifunovski | 0 | 0 | 0
26 | Carpentry | TRUE | 100 |  | 3 | 2026-03-04 | 2026-03-06 | Oliver Trifunovski | 0 | 0 | 0
27 | Ceiling insulation removal TH boys | TRUE | 100 |  | 1 | 2026-03-04 | 2026-03-04 | Oliver Trifunovski | 0 | 0 | 0
28 | Frame material delivery | TRUE | 100 |  | 1 | 2026-03-05 | 2026-03-05 | Oliver Trifunovski | 0 | 0 | 0
29 | Sheet Flooring Install | TRUE | 100 |  | 1 | 2026-03-05 | 2026-03-05 | Oliver Trifunovski | 0 | 0 | 0
30 | Bored piers Ryhs | TRUE | 100 |  | 1 | 2026-03-12 | 2026-03-12 | Oliver Trifunovski | 0 | 0 | 0
31 | Side deck Bored Piers | TRUE | 100 |  | 1 | 2026-03-12 | 2026-03-12 | James Quinn, Oliver Trifunovski | 0 | 0 | 0
32 | Book Roofers for after Easter install | TRUE | 100 |  | 1 | 2026-03-16 | 2026-03-16 |  | 0 | 0 | 0
33 | Bingo 6m³ Marell | TRUE | 100 |  | 1 | 2026-03-18 | 2026-03-18 | Oliver Trifunovski | 0 | 0 | 0
34 | Carpentry | TRUE | 100 |  | 2 | 2026-03-18 | 2026-03-19 | Oliver Trifunovski | 0 | 1 | 0
35 | External subfloor materials delivery | TRUE | 100 |  | 1 | 2026-03-18 | 2026-03-18 | Oliver Trifunovski | 0 | 0 | 0
36 | Framing | TRUE | 100 |  | 2 | 2026-03-18 | 2026-03-19 | James Quinn, Oliver Trifunovski | 0 | 0 | 0 | 37 | SS | -1 | 23 | FS | 11 | 29 | FS | 0
37 | Roof Construction | TRUE | 100 | Carpentry | 2 | 2026-03-18 | 2026-03-19 | James Quinn, Oliver Trifunovski | 0 | 0 | 0
38 | Roof rafters delivery oliver | TRUE | 100 |  | 1 | 2026-03-18 | 2026-03-18 | Oliver Trifunovski | 0 | 0 | 0
39 | Framing | TRUE | 100 |  | 1 | 2026-03-24 | 2026-03-24 | James Quinn, Oliver Trifunovski | 0 | 0 | 0 | 36 | FS | 2
40 | Deck Construction | TRUE | 100 |  | 1 | 2026-03-25 | 2026-03-25 | James Quinn, Oliver Trifunovski | 0 | 0 | 0 | 37 | FS | 3
41 | Carpentry | TRUE | 100 |  | 2 | 2026-03-26 | 2026-03-27 |  | 0 | 0 | 0
42 | Carpentry | TRUE | 100 |  | 2 | 2026-03-30 | 2026-03-31 | Oliver Trifunovski | 0 | 0 | 0
43 | Carpentry - Works | TRUE | 100 |  | 3 | 2026-03-30 | 2026-04-01 | Oliver Trifunovski | 0 | 0 | 0
44 | Site measure W7 & W8 (TBC) | TRUE | 100 |  | 1 | 2026-03-30 | 2026-03-30 | Oliver Trifunovski | 0 | 0 | 0
45 | Bingo 6m³ Marell change over | TRUE | 100 |  | 1 | 2026-03-31 | 2026-03-31 | Oliver Trifunovski | 0 | 0 | 0
46 | Bingo pick up | TRUE | 100 |  | 1 | 2026-03-31 | 2026-03-31 | Oliver Trifunovski | 0 | 0 | 0
47 | Carpentry | TRUE | 100 |  | 1 | 2026-04-01 | 2026-04-01 | Oliver Trifunovski | 0 | 0 | 0
48 | Concord Mini mix 3.2m³ 7.30am | TRUE | 100 |  | 1 | 2026-04-01 12:00 | 2026-04-01 | Oliver Trifunovski | 0 | 0 | 0
49 | Client meeting | TRUE | 100 |  | 1 | 2026-04-10 | 2026-04-10 | Oliver Trifunovski | 0 | 0 | 0
50 | Carpentry - Frame | TRUE | 100 |  | 2 | 2026-04-13 | 2026-04-14 | James Quinn, Oliver Trifunovski | 0 | 0 | 0
51 | Carpentry / Facia boards ( TBC ) | TRUE | 100 |  | 2 | 2026-04-13 | 2026-04-14 | Oliver Trifunovski | 0 | 0 | 0
52 | Pro Clima wrap to upper half for facia ( TBC ) | TRUE | 100 |  | 2 | 2026-04-13 | 2026-04-14 | Oliver Trifunovski | 0 | 0 | 0
53 | Sutton steel new cleats | TRUE | 100 |  | 1 | 2026-04-13 | 2026-04-13 | Oliver Trifunovski, Sutton Steel | 0 | 0 | 0
54 | Carpentry - Frame/Fascia/Wrap | TRUE | 100 |  | 1 | 2026-04-15 | 2026-04-15 | James Quinn, Oliver Trifunovski | 0 | 0 | 0
55 | FRAME CLAIM | TRUE | 100 | Key Milestones | 1 | 2026-04-15 | 2026-04-15 | Oliver Trifunovski | 0 | 0 | 0 | 39 | FS | 13
56 | Frame inspection | TRUE | 100 |  | 1 | 2026-04-15 | 2026-04-15 | Oliver Trifunovski | 0 | 0 | 0
57 | Scaffold - Erection | TRUE | 100 |  | 2 | 2026-04-15 | 2026-04-16 | Oliver Trifunovski | 0 | 1 | 0 | 43 | FS | 7
58 | Scafolding ( TBC ) | TRUE | 100 |  | 2 | 2026-04-15 | 2026-04-16 | Oliver Trifunovski | 0 | 0 | 0
59 | Windows site measure | TRUE | 100 |  | 1 | 2026-04-15 | 2026-04-15 |  | 0 | 0 | 0
60 | MCG Window Del | TRUE | 100 |  | 1 | 2026-04-16 | 2026-04-16 | Oliver Trifunovski | 0 | 0 | 0
61 | Roof install ( TBC ) | TRUE | 100 |  | 2 | 2026-04-16 | 2026-04-17 | Oliver Trifunovski | 0 | 0 | 0
62 | Roofing, Gutter & Rainheads | TRUE | 100 | Roofing | 5 | 2026-04-16 | 2026-04-22 |  | 0 | 0 | 0 | 57 | FS | -1 | 39 | FS | 3
63 | Electrical rough in | TRUE | 100 |  | 3 | 2026-04-22 | 2026-04-24 | DECAV Pty Ltd, Oliver Trifunovski | 0 | 0 | 0
64 | Electrical Rough-in | TRUE | 100 | MEP | 3 | 2026-04-22 | 2026-04-24 | DECAV Pty Ltd, Oliver Trifunovski | 0 | 0 | 0
65 | AC meeting with Peter | TRUE | 100 |  | 1 | 2026-04-24 19:30 | 2026-04-24 | Oliver Trifunovski | 0 | 0 | 0
66 | External Windows & Doors -Int L/Up | TRUE | 100 | Carpentry | 2 | 2026-04-27 | 2026-04-28 | James Quinn, Oliver Trifunovski | 0 | 0 | 0 | 62 | FS | 2
67 | Plumbing Rough | TRUE | 100 |  | 2 | 2026-04-28 | 2026-04-29 | Oliver Trifunovski | 0 | 0 | 0
68 | Plumbing Rough-in | TRUE | 100 | MEP | 2 | 2026-04-28 | 2026-04-29 | JCB Plumbing & Maintenance, Oliver Trifunovski | 0 | 0 | 0 | 62 | FS | 3 | 64 | SS | 0
69 | Plumbing Subfloor Rough-in | TRUE | 100 | MEP | 2 | 2026-04-28 | 2026-04-29 | JCB Plumbing & Maintenance, Oliver Trifunovski | 0 | 0 | 0 | 62 | FS | 3
70 | Carpentry Window install | TRUE | 100 |  | 1 | 2026-04-29 | 2026-04-29 | Oliver Trifunovski | 0 | 0 | 0
71 | Joinery site measure | TRUE | 100 |  | 1 | 2026-04-29 | 2026-04-29 | Oliver Trifunovski | 0 | 0 | 0
72 | Electrical rough in | TRUE | 100 |  | 1 | 2026-05-01 | 2026-05-01 | Oliver Trifunovski | 0 | 0 | 0
73 | AC rough in | FALSE | 0 |  | 2 | 2026-05-04 | 2026-05-05 | Oliver Trifunovski | 0 | 0 | 0
74 | HVAC Rough-in | FALSE | 0 | MEP | 2 | 2026-05-04 | 2026-05-05 | Everlasting Air, Oliver Trifunovski | 0 | 0 | 0 | 64 | FS | 5
75 | Cladding - Lower Portion Battens | FALSE | 0 | Carpentry | 6 | 2026-05-06 | 2026-05-13 | Dale Psaila, James Quinn, Oliver Trifunovski | 0 | 0 | 0 | 66 | FS | 5
76 | Unblock and camera front storm water | TRUE | 100 |  | 1 | 2026-05-06 | 2026-05-06 | JCB Plumbing & Maintenance, Oliver Trifunovski | 0 | 0 | 0
77 | Carpentry / External battens | FALSE | 0 |  | 4 | 2026-05-07 | 2026-05-12 | Oliver Trifunovski | 0 | 0 | 0
78 | Insulation (Ceiling, Walls) | FALSE | 0 | Insulation | 1 | 2026-05-08 | 2026-05-08 | Oliver Trifunovski, Pride Insulation | 0 | 0 | 0
79 | Sub floor Insulation | FALSE | 0 |  | 1 | 2026-05-08 | 2026-05-08 | Oliver Trifunovski | 0 | 0 | 0
80 | Insulation - Subfloor Install | FALSE | 0 | Insulation | 1 | 2026-05-11 | 2026-05-11 | Oliver Trifunovski, Pride Insulation | 0 | 0 | 0
81 | Ken Floor site visit | FALSE | 0 |  | 1 | 2026-05-13 | 2026-05-13 | Oliver Trifunovski | 0 | 0 | 0
82 | Rod plaster measure | FALSE | 0 |  | 1 | 2026-05-13 | 2026-05-13 | Oliver Trifunovski | 0 | 0 | 0
83 | Battery pre wire | FALSE | 0 |  | 1 | 2026-05-18 | 2026-05-18 | Oliver Trifunovski | 0 | 0 | 0
84 | Cladding - Installation Weathertex | FALSE | 0 |  | 5 | 2026-05-20 | 2026-05-26 |  | 0 | 0 | 0 | 85 | FS | -3
85 | Install of Window Glass (WEEK OF) | FALSE | 0 |  | 3 | 2026-05-20 | 2026-05-22 |  | 0 | 0 | 0
86 | Internal lockup - walls | FALSE | 0 |  | 1 | 2026-05-25 | 2026-05-25 |  | 0 | 0 | 0
87 | Plaster Metal Battens + Patch Ups | FALSE | 0 | Plastering | 2 | 2026-05-25 | 2026-05-26 | Oliver Trifunovski, VLS Plastering | 0 | 0 | 0 | 64 | FS | 20 | 85 | FS | 0
88 | Decking boards | FALSE | 0 |  | 4 | 2026-05-26 | 2026-05-29 |  | 0 | 0 | 0 | 85 | FS | 1
89 | 3D Walkthrough | FALSE | 0 | Labourers | 1 | 2026-05-27 | 2026-05-27 | Greg Paull, Oliver Trifunovski, Tavis King | 0 | 0 | 0
90 | Painting Exterior | FALSE | 0 | Painter | 9 | 2026-06-01 | 2026-06-12 | MS Paterson Painting and Decorating, Oliver Trifunovski | 0 | 0 | 0
91 | Plastering & Internal Walls | FALSE | 0 | Plastering | 8 | 2026-06-05 | 2026-06-17 | Oliver Trifunovski, VLS Plastering | 0 | 0 | 0 | 89 | FS | 6
92 | Painting Interior | FALSE | 0 | Painter | 13 | 2026-06-10 | 2026-06-26 | MS Paterson Painting and Decorating, Oliver Trifunovski | 0 | 0 | 0
93 | Flooring Installation | FALSE | 0 | Floor Coverings | 3 | 2026-06-22 | 2026-06-24 | Oliver Trifunovski | 0 | 0 | 0 | 91 | FS | 2
94 | Carpentry Fix | FALSE | 0 | Carpentry | 5 | 2026-06-25 | 2026-07-01 | Dale Psaila, James Quinn, Oliver Trifunovski | 0 | 0 | 0 | 93 | FS | 0
95 | Carpentry Fitoff | FALSE | 0 | Carpentry | 3 | 2026-06-29 | 2026-07-01 | Dale Psaila, James Quinn, Oliver Trifunovski | 0 | 0 | 0 | 92 | FS | 0
96 | Heating and Cooling - Fitoff | FALSE | 0 | MEP | 2 | 2026-06-29 | 2026-06-30 | Everlasting Air, Oliver Trifunovski | 0 | 0 | 0
97 | Cabinetry Installation, Benchtop Templates | FALSE | 0 | Joinery | 3 | 2026-06-30 | 2026-07-02 | Oliver Trifunovski | 0 | 0 | 0 | 91 | FS | 8
98 | Plumbing Fitoff | FALSE | 0 | MEP | 3 | 2026-07-01 | 2026-07-03 | JCB Plumbing & Maintenance, Oliver Trifunovski | 0 | 0 | 0
99 | Site Clean - pre floor finishes | FALSE | 0 | Labourers | 1 | 2026-07-06 | 2026-07-06 | John Bainbridge, Oliver Trifunovski | 0 | 0 | 0 | 98 | FS | 0
100 | Electrical Fit Off | FALSE | 0 | MEP | 4 | 2026-07-08 | 2026-07-13 | DECAV Pty Ltd, Oliver Trifunovski | 0 | 0 | 0
101 | Floorboards - Polish | FALSE | 0 | Floor Coverings | 4 | 2026-07-08 | 2026-07-13 | Oliver Trifunovski | 0 | 0 | 0 | 99 | FS | 1
102 | Final Inspection | FALSE | 0 | Key Milestones | 1 | 2026-07-15 | 2026-07-15 | Oliver Trifunovski | 0 | 0 | 0 | 101 | FS | 1
103 | Benchtops - Installation | FALSE | 0 | Joinery | 1 | 2026-07-16 | 2026-07-16 | Oliver Trifunovski | 0 | 0 | 0 | 97 | FS | 9
104 | Final Certification Process | FALSE | 0 | Finishing & Handover | 4 | 2026-07-16 | 2026-07-21 | Oliver Trifunovski | 0 | 0 | 0 | 102 | FS | 0
105 | Final Clean | FALSE | 0 | Labourers | 2 | 2026-07-17 | 2026-07-20 | Oliver Trifunovski | 0 | 0 | 0 | 101 | FS | 3
106 | Tiling (Splashbacks) | FALSE | 0 | Tiler | 2 | 2026-07-17 | 2026-07-20 | Expo Marble & Tiling, Oliver Trifunovski | 0 | 0 | 0 | 103 | FS | 0 | 92 | FS | 0
107 | Final Certificate | FALSE | 0 | Key Milestones | 1 | 2026-07-22 | 2026-07-22 | Oliver Trifunovski | 0 | 0 | 0 | 104 | FS | 0
108 | Completion of outstanding Items | FALSE | 0 |  | 41 | 2026-07-23 | 2026-09-17 |  | 0 | 0 | 0 | 107 | FS | 0
109 | Appliances - Install | FALSE | 0 | MEP | 1 | 2026-09-18 | 2026-09-18 | DECAV Pty Ltd, Oliver Trifunovski | 0 | 0 | 0
110 | Handover | FALSE | 0 | Key Milestones | 1 | 2026-09-18 | 2026-09-18 | Oliver Trifunovski | 0 | 0 | 0