## Schedules
Schedule - List - Transform Homes Boys (exported on May 13, 2026)
ID # | Title | Complete | Percent Complete | Phase | Duration | Start | End | Assigned To | Accepted | Pending | Declined
1 | 30 Connolly Coburg | FALSE | 0 |  | 3 | 2026-05-11 | 2026-05-13 | Dale Psaila, James Quinn, Jesse Kendal, Vaughan Haynes-Spence | 0 | 0 | 0
2 | 11 - 15 Station Street 7am | FALSE | 0 |  | 1 | 2026-05-13 | 2026-05-13 | John Bainbridge, Tavis King | 0 | 0 | 0
3 | 17 Glyndon | FALSE | 0 |  | 1 | 2026-05-13 | 2026-05-13 | Dale Psaila, Lachlan Findlay, Zac White | 0 | 0 | 0
4 | 17 Glyndon Ave PM | FALSE | 0 |  | 1 | 2026-05-13 | 2026-05-13 | John Bainbridge, Tavis King | 0 | 2 | 0
5 | 11 - 15 Station St | FALSE | 0 |  | 1 | 2026-05-14 | 2026-05-14 | Dale Psaila, Lachlan Findlay, Zac White | 0 | 0 | 0
6 | 17 Glyndon | FALSE | 0 |  | 4 | 2026-05-14 | 2026-05-19 | Dale Psaila, James Quinn, Vaughan Haynes-Spence | 0 | 0 | 0
7 | 17 Glyndon Ave | FALSE | 0 |  | 1 | 2026-05-14 | 2026-05-14 | John Bainbridge, Tavis King | 0 | 2 | 0
8 | 11 Station | FALSE | 0 |  | 2 | 2026-05-18 | 2026-05-19 | Dale Psaila, Lachlan Findlay, Zac White | 0 | 0 | 0
9 | Site clean up and prep for waterproofing | FALSE | 0 |  | 1 | 2026-05-19 | 2026-05-19 | John Bainbridge, Tavis King | 0 | 0 | 0
10 | 11 station | FALSE | 0 |  | 1 | 2026-05-20 | 2026-05-20 | Dale Psaila, Jesse Kendal, Lachlan Findlay, Zac White | 0 | 0 | 0
11 | 1-55 Melbourne Ave Glenroy (Site Setup) | FALSE | 0 |  | 2 | 2026-05-25 | 2026-05-26 | John Bainbridge, Matt Reid, Tavis King | 0 | 0 | 0
12 | 30 Connolly | FALSE | 0 |  | 3 | 2026-05-25 | 2026-05-27 | Dale Psaila, James Quinn, Jesse Kendal, Vaughan Haynes-Spence | 0 | 0 | 0
13 | 11 Station | FALSE | 0 |  | 8 | 2026-05-26 | 2026-06-04 | Dale Psaila, Lachlan Findlay, Zac White | 0 | 0 | 0
14 | 801 MHBR Hustribridge | FALSE | 0 |  | 1 | 2026-05-26 | 2026-05-26 | Dale Psaila, Lachlan Findlay, Zac White | 0 | 0 | 0
15 | 30 Connolly | FALSE | 0 |  | 8 | 2026-06-01 | 2026-06-11 | Dale Psaila, James Quinn, Jesse Kendal, Vaughan Haynes-Spence | 0 | 0 | 0
16 | 150 Banksia Street Ivanhoe (Site Setup) | FALSE | 0 |  | 2 | 2026-06-09 | 2026-06-10 | John Bainbridge, Matt Reid, Tavis King | 0 | 0 | 0
17 | 17 Glyndon Ave Coburg | FALSE | 0 |  | 4 | 2026-06-16 | 2026-06-19 | Dale Psaila, James Quinn, Jesse Kendal, Lachlan Findlay, Vaughan Haynes-Spence, Zac White | 0 | 0 | 0
18 | 30 Connolly Ave Coburg | FALSE | 0 |  | 5 | 2026-06-29 | 2026-07-03 | Dale Psaila, James Quinn, Jesse Kendal, Lachlan Findlay, Vaughan Haynes-Spence, Zac White | 0 | 0 | 0
19 | 17 Glyndon Ave | FALSE | 0 |  | 2 | 2026-08-24 | 2026-08-25 | John Bainbridge, Tavis King | 0 | 0 | 0