## Purchase Orders
Purchase Orders (exported on Wed, Mar 25, 2026)
Job | PO # | Title | PO Status | Work Status | Performed By | Created Date | Cost | Paid | Cost Code | Variance Code | Est. Complete | Files | RFIs
29 River Gum Close, Diamond Creek FC | 29RIV-0016 | Watertank - Relocation | Sub/Vendor Approved - 23-03-26 | Not Complete | DECAV Pty Ltd | 2026-03-24 06:22 | 159 | Not Paid | Electrical | 72 - Customer change order |  |  | -
37 Robinson St Moonee Ponds - FC | 37ROB-0038 | Hot Water Service | Sub/Vendor Approved - 18-03-26 | Not Complete | Bentons Heidelberg | 2026-03-18 10:30 | 3274.4 | Not Paid | Plumbing - Fixtures & Fittings MATERIALS ONLY Plumbing - Fixtures & Fittings MATERIALS ONLY (+1)... |  |  | 1 | -
17 Glyndon Ave - FC | 17GLYN-0017 | Paving Slab | Sub/Vendor Approved - 17-03-26 | Not Complete | Metro Concrete Works | 2026-03-10 07:18 | 10010 | Not Paid | Concrete - Driveways & Pathways |  | 2026-03-25 | 1 | -
11-15 Station Street, Diamond Creek - FC | 11STA-0023 | Door Furniture | Sub/Vendor Approved - 05-03-26 | Not Complete | All Secure Locksmiths | 2026-03-06 07:13 | 5413 | Partially Paid | Door Hardware MATERIALS ONLY |  |  | 2 | -
29 River Gum Close, Diamond Creek FC | 29RIV-0015 | Insulation - Material | Approved by Dale Psaila - 16-03-26 | Work Complete by Dale Psaila - 16-03-2026 | Pride Insulation | 2026-03-04 18:37 | 1122 | Fully Paid | Insulation - Supply & Install |  |  |  | -
37 Robinson St Moonee Ponds - FC | 37ROB-0035 | Shower Screens | Approved by Dale Psaila - 16-03-26 | Work Complete by Dale Psaila - 16-03-2026 | Stevens Glass | 2026-03-03 11:16 | 2816 | Not Paid | Shower Screens & Mirrors |  | 2026-03-06 | 1 | -
127 O'Hea St, Coburg | OHEA-PT3-0050 | Floor Sanding - Rear | Sub/Vendor Approved - 07-03-26 | Not Complete | Ken Built Timber Floors (T&C 15 Trading Pty Ltd) | 2026-02-28 22:00 | 2640 | Not Paid | Floor Sanding & Polishing |  |  | 1 | -
127 O'Hea St, Coburg | OHEA-PT3-0049 | Flooring Repairs - Front | Sub/Vendor Approved - 05-03-26 | Not Complete | Ken Built Timber Floors (T&C 15 Trading Pty Ltd) | 2026-02-28 21:59 | 2662 | Not Paid | Floor Sanding & Polishing |  |  | 1 | -
30 Connolly Ave, Coburg - FC | 30CON-0009 | Windows and Doors | Sub/Vendor Approved - 03-03-26 | Not Complete | MCG Windows | 2026-02-27 07:10 | 18675 | Partially Paid | Windows & Doors - Aluminium MATERIALS ONLY |  | 2026-03-20 | 5 | -
29 River Gum Close, Diamond Creek FC | 29RIV-0014 | Split System Air Conditioners - reinstallation | Sub/Vendor Approved - 27-02-26 | Not Complete | Everlasting Air | 2026-02-27 06:33 | 3140 | Not Paid | Air Conditioning |  |  | 1 | -
29 River Gum Close, Diamond Creek FC | 29RIV-0013 | Airconditioner - Bed 3 | Sub/Vendor Approved - 27-02-26 | Not Complete | Everlasting Air | 2026-02-27 05:55 | 2510 | Not Paid | Air Conditioning |  |  | 1 | -
29 River Gum Close, Diamond Creek FC | 29RIV-0012 | Electrical - Illume Skylight | Sub/Vendor Approved - 27-02-26 | Not Complete | DECAV Pty Ltd | 2026-02-27 05:50 | 698.85 | Fully Paid | Electrical | 72 - Customer change order |  | 1 | -
29 River Gum Close, Diamond Creek FC | 29RIV-0011 | Roofing - Upper Roof | Sub/Vendor Approved - 27-02-26 | Not Complete | Everlasting Air | 2026-02-26 10:20 | 1570 | Not Paid | Air Conditioning | 72 - Customer change order |  |  | -
29 River Gum Close, Diamond Creek FC | 29RIV-0010 | Roofing - Upper Roof | Sub/Vendor Approved - 26-02-26 | Not Complete | DECAV Pty Ltd | 2026-02-26 10:20 | 500 | Not Paid | Electrical | 72 - Customer change order |  |  | -
29 River Gum Close, Diamond Creek FC | 29RIV-0009 | Roofing - Upper Roof | Sub/Vendor Approved - 28-02-26 | Not Complete | Ahearn Roofing | 2026-02-26 10:20 | 15883 | Fully Paid | Roofing | 72 - Customer change order |  | 1 | -
29 River Gum Close, Diamond Creek FC | 29RIV-0008 | Electrical - First Floor Lighting | Sub/Vendor Approved - 26-02-26 | Work Complete by Dale Psaila - 16-03-2026 | DECAV Pty Ltd | 2026-02-26 10:19 | 1692.35 | Fully Paid | Electrical | 72 - Customer change order |  | 1 | -
11-15 Station Street, Diamond Creek - FC | 11STA-0022 | Plumbing - Kitchen | Sub/Vendor Approved - 28-02-26 | Not Complete | JCB Plumbing & Maintenance | 2026-02-26 10:16 | 638 | Not Paid | Plumbing & Drainage | 72 - Customer change order |  |  | -
37 Robinson St Moonee Ponds - FC | 37ROB-0032 | Painting | Sub/Vendor Approved - 24-02-26 | Not Complete | APS Painting & Decorating Pty Ltd | 2026-02-23 16:00 | 20800 | Not Paid | Painting |  | 2026-04-09 | 1 | -
29 River Gum Close, Diamond Creek FC | 29RIV-0007 | Electrical - Smoke Alarms | Sub/Vendor Approved - 23-02-26 | Work Complete by Dale Psaila - 16-03-2026 | DECAV Pty Ltd | 2026-02-23 09:18 | 1145.8 | Fully Paid | Electrical | 72 - Customer change order |  | 1 | -
29 River Gum Close, Diamond Creek FC | 29RIV-0006 | Electrical - General | Sub/Vendor Approved - 23-02-26 | Not Complete | DECAV Pty Ltd | 2026-02-23 09:18 | 5947.11 | Not Paid | Electrical | 72 - Customer change order |  |  | -
29 River Gum Close, Diamond Creek FC | 29RIV-0005 | Roof Plumbing - Lower Roofs | Sub/Vendor Approved - 02-03-26 | Not Complete | Ahearn Roofing | 2026-02-19 09:23 | 7128 | Partially Paid | Roofing - Fascia & Gutter |  |  | 2 | -
11-15 Station Street, Diamond Creek - FC | 11STA-0021 | Tiles - Supply | Sub/Vendor Approved - 18-02-26 | Work Complete by Dale Psaila - 16-03-2026 | National Tiles (South Morang) | 2026-02-18 11:16 | 744.46 | Fully Paid | Tiles - Supply MATERIALS ONLY |  |  | 3 | -
37 Robinson St Moonee Ponds - FC | 37ROB-0031 | Plumbing works - Tap | Sub/Vendor Approved - 24-02-26 | Work Complete by Jacquie Bell - 2-03-2026 | JCB Plumbing & Maintenance | 2026-02-16 21:36 | 528 | Fully Paid | Plumbing & Drainage | 72 - Customer change order | 2026-02-27 | 1 | -
30 Connolly Ave, Coburg - FC | 30CON-0006 | Concrete Stage 1 Bored Piers | Approved by Dale Psaila - 23-02-26 | Work Complete by Dale Psaila - 23-02-2026 | Trade Alliance | 2026-02-16 18:25 | 1276 | Not Paid | Concrete - Supply MATERIALS ONLY |  | 2026-02-17 | 1 | -
11-15 Station Street, Diamond Creek - FC | 11STA-0019 | **Painting | Sub/Vendor Approved - 12-02-26 | Not Complete | MS Paterson Painting and Decorating | 2026-02-12 11:09 | 26000 | Partially Paid | Painting |  |  | 1 | -
11-15 Station Street, Diamond Creek - FC | 11STA-0017 | Electrical - Security & Access | Sub/Vendor Approved - 12-02-26 | Not Complete | DECAV Pty Ltd | 2026-02-12 10:16 | 936.9 | Not Paid | Electrical | 72 - Customer change order |  |  | -
11-15 Station Street, Diamond Creek - FC | 11STA-0016 | Electrical | Sub/Vendor Approved - 12-02-26 | Work Complete by Dale Psaila - 16-03-2026 | DECAV Pty Ltd | 2026-02-12 10:15 | 8223.42 | Fully Paid | Electrical | 72 - Customer change order |  | 2 | -
11-15 Station Street, Diamond Creek - FC | 11STA-0015 | Plastering | Approved by Dale Psaila - 16-03-26 | Work Complete by Dale Psaila - 16-03-2026 | Stanislovas Gecevicius Plasterer | 2026-02-10 13:47 | 17160 | Fully Paid | Plastering Plastering (+1)... | 21 - Price change |  | 3 | -
17 Glyndon Ave - FC | 17GLYN-0014 | SubFloor Insulation | Approved by Dale Psaila - 11-02-26 | Work Complete by Dale Psaila - 12-02-2026 | Pride Insulation | 2026-02-05 13:39 | 1977.2 | Fully Paid | Insulation - Supply & Install |  | 2026-02-11 | 2 | -
11-15 Station Street, Diamond Creek - FC | 11STA-0014 | Insulation | Approved by Dale Psaila - 20-02-26 | Work Complete by Dale Psaila - 20-02-2026 | Pride Insulation | 2026-02-03 11:32 | 3995.92 | Fully Paid | Insulation - Supply & Install |  | 2026-02-21 | 2 | -
30 Connolly Ave, Coburg - FC | 30CON-0005 | Asbestos Removal | Approved by Dale Psaila - 15-02-26 | Work Complete by Dale Psaila - 16-02-2026 | Simcat Demolitions | 2026-01-29 19:34 | 3190 | Fully Paid | Asbestos Removal Asbestos Removal (+1)... | 21 - Price change | 2026-02-02 |  | -
11-15 Station Street, Diamond Creek - FC | 11STA-0013 | **Air conditioning | Sub/Vendor Approved - 24-02-26 | Not Complete | Everlasting Air | 2026-01-29 12:13 | 16380 | Not Paid | Air Conditioning |  |  | 2 | -
13 Glyndon Ave - FC | 13GLYN-0043 | Caulking | Approved by Jacquie Bell - 01-02-26 | Work Complete by Jacquie Bell - 2-02-2026 | The Caulking Group | 2026-01-27 16:23 | 1442.1 | Fully Paid | Painting |  | 2026-01-27 | 1 | -
29 River Gum Close, Diamond Creek FC | 29RIV-0002 | Flyscreens | Sub/Vendor Approved - 23-02-26 | Not Complete | AAA Windows | 2026-01-27 15:07 | 693 | Not Paid | Windows & Doors - Security / Fly Screens MATERIALS ONLY |  |  | 1 | -
29 River Gum Close, Diamond Creek FC | 29RIV-0001 | Windows | Sub/Vendor Approved - 22-02-26 | Work Complete by Dale Psaila - 16-03-2026 | AAA Windows | 2026-01-27 15:02 | 8400 | Fully Paid | Windows & Doors - Aluminium MATERIALS ONLY |  |  | 2 | -
73 Fenwick St, Carlton North | 73FEN-0002 | Concreting | Sub/Vendor Approved - 27-01-26 | Work Complete by Dale Psaila - 9-02-2026 | Concept Concrete Paving Constructions PTY LTD | 2026-01-27 12:36 | 3300 | Fully Paid | Concrete - Driveways & Pathways |  |  | 2 | -
30 Connolly Ave, Coburg - FC | 30CON-0003 | Electrical | Sub/Vendor Approved - 21-01-26 | Not Complete | DECAV Pty Ltd | 2026-01-21 13:21 | 12828.63 | Not Paid | Electrical |  | 2026-07-10 |  | -
30 Connolly Ave, Coburg - FC | 30CON-0001 | Demolition and removal of demolition waste | Sub/Vendor Approved - 28-01-26 | Work Complete by Dale Psaila - 16-02-2026 | Simcat Demolitions | 2026-01-20 16:54 | 17490 | Fully Paid | Demolition / Rubbish Removal |  | 2026-01-30 | 1 | -
17 Glyndon Ave - FC | 17GLYN-0012 | Tile Roofing | Approved by Jacquie Bell - 12-03-26 | Not Complete | Greens Roofing | 2026-01-20 15:37 | 33840 | Fully Paid | Roofing | 72 - Customer change order | 2026-02-20 | 3 | -
17 Glyndon Ave - FC | 17GLYN-0011 | Windows and Doors | Sub/Vendor Approved - 16-02-26 | Not Complete | AAA Windows | 2026-01-20 15:35 | 34390 | Not Paid | Windows & Doors - Aluminium MATERIALS ONLY |  | 2026-03-16 | 2 | -
17 Glyndon Ave - FC | 17GLYN-0009 | Roof Trusses | Approved by Dale Psaila - 10-02-26 | Work Complete by Dale Psaila - 10-02-2026 | Accurate Roof Trusses | 2026-01-20 15:33 | 14982 | Fully Paid | Timber Supply - Roof Frame & Trusses MATERIALS ONLY |  | 2026-01-30 | 4 | -
17 Glyndon Ave - FC | 17GLYN-0008 | Solar System | Sub/Vendor Approved - 05-02-26 | Work Complete by Dale Psaila - 16-03-2026 | DECAV Pty Ltd | 2026-01-20 15:32 | 13740.36 | Fully Paid | Electrical - Solar Panels |  | 2026-02-20 | 1 | -
17 Glyndon Ave - FC | 17GLYN-0007 | Roofing, Fascia and Gutter | Approved by Dale Psaila - 20-02-26 | Work Complete by Dale Psaila - 20-02-2026 | Ahearn Roofing | 2026-01-20 15:27 | 11275 | Partially Paid | Roofing - Fascia & Gutter |  | 2026-02-19 | 4 | -
11-15 Station Street, Diamond Creek - FC | 11STA-0012 | Guard Rail | Approved by Dale Psaila - 20-02-26 | Work Complete by Dale Psaila - 20-02-2026 | TED Guardrail Pty. Ltd. | 2026-01-19 09:44 | 1633.5 | Fully Paid | Scaffolding |  | 2026-01-21 | 2 | -
11-15 Station Street, Diamond Creek - FC | 11STA-0011 | **Roofing, Fascia & Gutter | Approved by Dale Psaila - 03-02-26 | Work Complete by Dale Psaila - 3-02-2026 | Ahearn Roofing | 2026-01-16 12:29 | 50105 | Partially Paid | Roofing - Fascia & Gutter |  | 2026-02-04 | 2 | -
13 Glyndon Ave - FC | 13GLYN-0042 | Final clean | Sub/Vendor Approved - 15-01-26 | Work Complete by Jacquie Bell - 29-01-2026 | BLAS Maintenance Services | 2026-01-15 15:22 | 1700 | Fully Paid | House Cleaner |  | 2026-01-23 | 1 | -
73 Fenwick St, Carlton North | 73FEN-0001 | Demolition and Waste Management | Approved by Dale Psaila - 01-02-26 | Work Complete by Dale Psaila - 2-02-2026 | Simcat Demolitions | 2026-01-09 08:34 | 4455 | Fully Paid | Demolition / Rubbish Removal |  | 2026-01-22 | 1 | -
399111