## Schedules
Schedule - List - 11-15 Station Street, Diamond Creek - FC (exported on May 14, 2026)
ID # | Title | Complete | Percent Complete | Phase | Duration | Start | End | Assigned To | Accepted | Pending | Declined | Pred 1 Id | Pred 1 Type | Pred 1 Lag | Pred 2 Id | Pred 2 Type | Pred 2 Lag | Pred 3 Id | Pred 3 Type | Pred 3 Lag | Pred 4 Id | Pred 4 Type | Pred 4 Lag
1 | Critical Path | TRUE | 100 | Critical Path | 4 | 2025-11-10 | 2025-11-13 | Matt Reid | 0 | 0 | 0 | 4 | SS | 0
2 | Demolition Site Meeting & Walk through | TRUE | 100 | Site Preparation | 1 | 2025-11-10 | 2025-11-10 | Matt Reid, Simcat Demolitions | 0 | 0 | 0
3 | Make Safe | TRUE | 100 | MEP | 1 | 2025-11-10 | 2025-11-10 | DECAV Pty Ltd, JCB Plumbing & Maintenance, Matt Reid | 0 | 0 | 0 | 4 | FS | -3
4 | Site Establishment/Setup | TRUE | 100 | Site Preparation | 3 | 2025-11-10 | 2025-11-12 | John Bainbridge, Matt Reid | 0 | 0 | 0
5 | Temp Power & Water (toilet etc) | TRUE | 100 | Site Preparation | 3 | 2025-11-10 | 2025-11-12 | John Bainbridge, Matt Reid | 0 | 0 | 0 | 4 | FS | -3
6 | Asbestos removal (Laundry, WC, and eaves) | TRUE | 100 | Demolition | 4 | 2025-11-11 | 2025-11-14 | Matt Reid, Simcat Demolitions | 0 | 0 | 0 | 2 | FS | 0
7 | Critical Path | TRUE | 100 | Critical Path | 14 | 2025-11-11 | 2025-11-28 | Matt Reid | 0 | 0 | 0 | 6 | SS | 0
8 | Demolition - Pt 1 | TRUE | 100 | Demolition | 5 | 2025-11-17 | 2025-11-21 | Matt Reid, Simcat Demolitions | 0 | 0 | 0 | 6 | FS | 0
9 | Power Abolishment Week TBC | TRUE | 100 | MEP | 5 | 2025-11-24 | 2025-11-28 | DECAV Pty Ltd, Matt Reid | 0 | 0 | 0
10 | Electrical - Power Disconnect | TRUE | 100 | MEP | 1 | 2025-11-28 | 2025-11-28 | DECAV Pty Ltd, Matt Reid | 0 | 0 | 0
11 | Critical Path | TRUE | 100 | Critical Path | 6 | 2025-12-01 | 2025-12-08 | Matt Reid | 0 | 0 | 0 | 7 | FS | 0
12 | Demolition - Complete Demolition | TRUE | 100 | Demolition | 2 | 2025-12-01 | 2025-12-02 | Matt Reid, Simcat Demolitions | 0 | 0 | 0
13 | Demolition - Pt 2 | TRUE | 100 | Demolition | 2 | 2025-12-01 | 2025-12-02 | Matt Reid, Simcat Demolitions | 0 | 0 | 0 | 8 | FS | 5
14 | Demolition Claim Stage | TRUE | 100 | Key Milestones | 1 | 2025-12-02 | 2025-12-02 | Greg Paull, Matt Reid | 0 | 0 | 0 | 13 | FS | -1
15 | Groundworks & Spoil Removal | TRUE | 100 | Earthworks | 1 | 2025-12-03 | 2025-12-03 | Matt Reid | 0 | 0 | 0 | 13 | FS | 0
16 | Plumbing - Under Slab Rough In | TRUE | 100 | Plumber | 1 | 2025-12-03 | 2025-12-03 | JCB Plumbing & Maintenance, Matt Reid | 0 | 0 | 0
17 | Internal Framing | TRUE | 100 | Carpentry | 3 | 2025-12-04 | 2025-12-08 | Lachlan Findlay, Matt Reid | 0 | 0 | 0
18 | Survey - Re-establishment Survey | TRUE | 100 | Other | 1 | 2025-12-04 | 2025-12-04 | Matt Reid | 0 | 0 | 0
19 | Survey - Site Set Out | TRUE | 100 | Other | 1 | 2025-12-08 | 2025-12-08 | Matt Reid | 0 | 0 | 0
20 | Concrete & Footing Works | TRUE | 100 | Concrete | 4 | 2025-12-09 | 2025-12-12 | Matt Reid, Metro Concrete Works | 0 | 0 | 0 | 15 | FS | 3
21 | Concreting - Prep and Pour Slab Extension | TRUE | 100 | Concrete | 4 | 2025-12-09 | 2025-12-12 | Matt Reid, Metro Concrete Works | 0 | 0 | 0
22 | Critical Path | TRUE | 100 | Critical Path | 4 | 2025-12-09 | 2025-12-12 | Matt Reid | 0 | 0 | 0 | 20 | SS | 0 | 11 | FS | -1
23 | Order Windows | TRUE | 100 | Deliveries & Meetings | 1 | 2025-12-15 | 2025-12-15 | Matt Reid | 0 | 0 | 0
24 | Chaulk out slab | TRUE | 100 | Carpentry | 1 | 2025-12-16 | 2025-12-16 | Lachlan Findlay, Matt Reid | 0 | 0 | 0 | 20 | FS | 1
25 | Timber Framing | TRUE | 100 | Carpentry | 3 | 2025-12-16 | 2025-12-18 | Lachlan Findlay, Matt Reid | 0 | 0 | 0 | 24 | FS | -1
26 | Truss Measure | TRUE | 100 | Deliveries & Meetings | 1 | 2025-12-16 | 2025-12-16 | Matt Reid | 0 | 0 | 0 | 24 | FS | -1
27 | Industry Shutdown | TRUE | 100 | Other | 7 | 2025-12-22 | 2026-01-02 | Matt Reid | 0 | 0 | 0
28 | Critical Path | TRUE | 100 | Critical Path | 15 | 2026-01-05 | 2026-01-23 | Matt Reid | 0 | 0 | 0 | 30 | SS | 0
29 | Plumbing Rough-in Sub-floor | TRUE | 100 | MEP | 3 | 2026-01-05 | 2026-01-07 | JCB Plumbing & Maintenance, Matt Reid | 0 | 0 | 0
30 | Timber Framing | TRUE | 100 | Carpentry | 10 | 2026-01-05 | 2026-01-16 | Lachlan Findlay, Matt Reid | 0 | 0 | 0 | 25 | FS | 8
31 | Carport Steel Measure | TRUE | 100 | Deliveries & Meetings | 1 | 2026-01-09 | 2026-01-09 | Matt Reid, Sutton Steel | 0 | 0 | 0 | 67 | FS | -50
32 | Roof Truss Delivery | TRUE | 100 | Deliveries & Meetings | 1 | 2026-01-12 | 2026-01-12 | Matt Reid | 0 | 0 | 0
33 | Critical Path | TRUE | 100 | Critical Path | 13 | 2026-01-15 | 2026-02-03 | Matt Reid | 0 | 0 | 0 | 35 | SS | -1
34 | Apply for power Upgrades as required | TRUE | 100 | MEP | 1 | 2026-01-16 | 2026-01-16 | DECAV Pty Ltd, Matt Reid | 0 | 0 | 0 | 30 | FS | -1
35 | Fascia & Gutter | TRUE | 100 | Roofing | 6 | 2026-01-16 | 2026-01-23 | Ahearn Roofing, Matt Reid | 0 | 0 | 0 | 30 | FS | -1
36 | Guardrail Scaffold | TRUE | 100 | Deliveries & Meetings | 2 | 2026-01-21 | 2026-01-22 | Matt Reid | 0 | 0 | 0
37 | Steel Install | TRUE | 100 | Steel Work | 1 | 2026-01-21 | 2026-01-21 | Matt Reid, Sutton Steel | 0 | 0 | 0 | 31 | FS | 7
38 | Simcat Remove Roof Tiles | TRUE | 100 | Demolition | 1 | 2026-01-28 | 2026-01-28 | Matt Reid, Simcat Demolitions | 0 | 0 | 0
39 | Roof Sheet Install - Main | TRUE | 100 | Roofing | 4 | 2026-01-29 | 2026-02-03 | Ahearn Roofing, Matt Reid | 0 | 0 | 0
40 | Termite Spray | TRUE | 100 | Other | 1 | 2026-01-29 | 2026-01-29 | Matt Reid | 0 | 0 | 0
41 | Hebel Delivery | TRUE | 100 | Deliveries & Meetings | 1 | 2026-02-02 | 2026-02-02 | Matt Reid | 0 | 0 | 0
42 | Hebel Delivery (week of) | TRUE | 100 | Deliveries & Meetings | 1 | 2026-02-02 | 2026-02-02 | Matt Reid | 0 | 0 | 0
43 | Wall Wrap | TRUE | 100 | Carpentry | 1 | 2026-02-04 | 2026-02-04 | Lachlan Findlay, Matt Reid | 0 | 1 | 0
44 | Window Delivery (Later in week) | TRUE | 100 | Deliveries & Meetings | 1 | 2026-02-04 | 2026-02-04 | Matt Reid | 0 | 1 | 0
45 | Window Installation | TRUE | 100 | Carpentry | 3 | 2026-02-04 | 2026-02-06 | Lachlan Findlay, Matt Reid | 0 | 2 | 0 | 43 | SS | 0
46 | Lock-Up/External Battens | TRUE | 100 | Carpentry | 3 | 2026-02-05 | 2026-02-09 | Lachlan Findlay, Matt Reid | 0 | 0 | 0 | 45 | FS | -2
47 | Critical Path | TRUE | 100 | Critical Path | 5 | 2026-02-09 | 2026-02-13 | Matt Reid | 0 | 0 | 0
48 | Electrical Rough-in (upgrade) | TRUE | 100 | MEP | 5 | 2026-02-09 | 2026-02-13 | DECAV Pty Ltd, Matt Reid | 0 | 0 | 0 | 35 | FS | 5 | 34 | FS | 10 | 46 | FS | -5 | 49 | SS | 0
49 | Plumbing Int Roughin | TRUE | 100 | MEP | 2 | 2026-02-09 | 2026-02-10 | JCB Plumbing & Maintenance, Matt Reid | 0 | 0 | 0 | 47 | SS | 0
50 | AC Rough-in | TRUE | 100 | MEP | 1 | 2026-02-12 | 2026-02-12 | Everlasting Air, Matt Reid | 0 | 0 | 0 | 48 | SS | 3
51 | Internal Lock-Up | TRUE | 100 |  | 5 | 2026-02-13 | 2026-02-19 | Lachlan Findlay, Matt Reid | 0 | 0 | 0
52 | Plastering - Battens | TRUE | 100 |  | 1 | 2026-02-16 | 2026-02-16 | Matt Reid, VLS Plastering | 0 | 0 | 0
53 | 3D Camera of Internal | TRUE | 100 | Labourers | 1 | 2026-02-19 | 2026-02-19 | Matt Reid, Tavis King | 0 | 0 | 0 | 52 | FS | 2 | 51 | FS | -1
54 | Insulation | TRUE | 100 | Insulation | 1 | 2026-02-20 | 2026-02-20 | Matt Reid, Pride Insulation | 0 | 0 | 0 | 52 | FS | 3
55 | Plaster Delivery | TRUE | 100 |  | 1 | 2026-02-20 | 2026-02-20 | Matt Reid, VLS Plastering | 0 | 0 | 0
56 | Critical Path | TRUE | 100 | Critical Path | 11 | 2026-02-23 | 2026-03-10 | Matt Reid | 0 | 0 | 0
57 | Plastering | TRUE | 100 | Plastering | 11 | 2026-02-23 | 2026-03-10 | Matt Reid, VLS Plastering | 0 | 0 | 0 | 54 | FS | 0 | 56 | SS | -8
58 | External Cladding - Eaves | TRUE | 100 | Carpentry | 2 | 2026-03-02 | 2026-03-03 | Lachlan Findlay, Matt Reid | 0 | 0 | 0 | 45 | FS | 15
59 | OTS - Floor tiles for installation | TRUE | 100 | Deliveries & Meetings | 1 | 2026-03-03 | 2026-03-03 | Matt Reid | 0 | 0 | 0
60 | Tile Delivery | TRUE | 100 |  | 1 | 2026-03-03 | 2026-03-03 | Matt Reid | 0 | 0 | 0
61 | Critical Path | TRUE | 100 | Critical Path | 7 | 2026-03-11 | 2026-03-19 | Matt Reid | 0 | 0 | 0
62 | Painting Int | TRUE | 100 | Painter | 36 | 2026-03-11 | 2026-05-01 | Matt Reid, MS Paterson Painting and Decorating | 0 | 0 | 0 | 61 | SS | 0
63 | Electrical Fitoff Stage 1 | TRUE | 100 |  | 2 | 2026-03-19 | 2026-03-20 | DECAV Pty Ltd, Matt Reid | 0 | 0 | 0
64 | Carpentry Fix | TRUE | 100 | Carpentry | 1 | 2026-03-20 | 2026-03-20 | Lachlan Findlay, Matt Reid | 0 | 0 | 0 | 57 | FS | 7
65 | Critical Path | TRUE | 100 | Critical Path | 1 | 2026-03-20 | 2026-03-20 | Matt Reid | 0 | 0 | 0 | 64 | SS | 0
66 | Critical Path | TRUE | 100 | Critical Path | 7 | 2026-03-23 | 2026-03-31 | Matt Reid | 0 | 0 | 0
67 | Trigger BP Part 2 | TRUE | 100 | Other | 1 | 2026-03-23 | 2026-03-23 | Greg Paull, Matt Reid | 0 | 0 | 0
68 | Waterproofing & Tiling | TRUE | 100 | Tiler | 7 | 2026-03-23 | 2026-03-31 | Expo Marble & Tiling, Matt Reid | 0 | 0 | 0 | 57 | FS | 8 | 59 | FS | 5
69 | Pad Footings (dig and pour) Carport | TRUE | 100 | Concrete | 4 | 2026-04-07 | 2026-04-10 | John Bainbridge, Matt Reid | 0 | 0 | 0 | 70 | SS | -1 | 31 | FS | 0
70 | Commencement (STAGE 2) | TRUE | 100 | Other | 1 | 2026-04-08 | 2026-04-08 | Greg Paull, Matt Reid | 0 | 0 | 0 | 67 | FS | 9
71 | Plumbing Fitoff | TRUE | 100 | MEP | 7 | 2026-04-10 | 2026-04-20 | JCB Plumbing & Maintenance, Matt Reid | 0 | 0 | 0 | 62 | FS | -16
72 | Critical Path | TRUE | 100 | Critical Path | 9 | 2026-04-17 | 2026-04-29 | Matt Reid | 0 | 0 | 0 | 73 | SS | 0
73 | Electrical Fitoff Stage 2 | TRUE | 100 | MEP | 9 | 2026-04-17 | 2026-04-29 | DECAV Pty Ltd, Matt Reid | 0 | 0 | 0 | 62 | FS | -11
74 | Steel Measure (Week of) | TRUE | 100 |  | 1 | 2026-04-21 | 2026-04-21 |  | 0 | 0 | 0 | 69 | FS | 6
75 | Scaffold - Carport | TRUE | 100 |  | 1 | 2026-04-23 | 2026-04-23 | John Bainbridge, Matt Reid | 0 | 0 | 0
76 | External Cladding - Eaves | TRUE | 100 |  | 5 | 2026-04-27 | 2026-05-01 | Lachlan Findlay, Matt Reid | 0 | 0 | 0
77 | HVAC Fitoff | TRUE | 100 | MEP | 2 | 2026-04-30 | 2026-05-01 | Everlasting Air, Matt Reid | 0 | 0 | 0 | 62 | FS | -2
78 | OTS - Hot water system, tank and pump | TRUE | 100 | Finishing & Handover | 1 | 2026-05-01 | 2026-05-01 | Matt Reid | 0 | 0 | 0 | 62 | FS | -1
79 | Steel Installation | TRUE | 100 |  | 8 | 2026-05-01 | 2026-05-12 | Matt Reid | 0 | 0 | 0 | 74 | FS | 7
80 | Carpentry Fitoff/Final Cladding/Eaves | TRUE | 100 | Carpentry | 5 | 2026-05-04 | 2026-05-08 | Dale Psaila, Lachlan Findlay, Matt Reid | 0 | 0 | 0 | 62 | FS | 0
81 | Door Hardware Installation | TRUE | 100 |  | 5 | 2026-05-04 | 2026-05-08 | Matt Reid | 0 | 0 | 0
82 | Timber Framing to Carport (Incs Wall Wrap) | FALSE | 0 | Carpentry | 5 | 2026-05-11 | 2026-05-15 | Dale Psaila, Lachlan Findlay, Matt Reid | 0 | 0 | 0 | 79 | FS | -2
83 | Garage Roofing Measure Up | TRUE | 100 |  | 1 | 2026-05-12 | 2026-05-12 | Ahearn Roofing, Matt Reid | 0 | 0 | 0 | 79 | FS | -1
84 | Plaster Patch ups | TRUE | 100 |  | 2 | 2026-05-12 | 2026-05-13 |  | 0 | 0 | 0
85 | Garage Roofing Install | FALSE | 0 |  | 3 | 2026-05-13 | 2026-05-15 | Ahearn Roofing, Matt Reid | 0 | 0 | 0 | 83 | FS | 0
86 | External expasion joint caulk | FALSE | 0 |  | 1 | 2026-05-15 | 2026-05-15 |  | 0 | 0 | 0
87 | Critical Path | FALSE | 0 | Critical Path | 8 | 2026-05-18 | 2026-05-27 | Matt Reid | 0 | 0 | 0
88 | External Cladding (Carport Hebel) | FALSE | 0 | Carpentry | 8 | 2026-05-18 | 2026-05-27 | Dale Psaila, Lachlan Findlay, Matt Reid | 0 | 0 | 0 | 82 | FS | 0 | 85 | FS | -3
89 | Rendering | FALSE | 0 | Renderer | 9 | 2026-05-20 | 2026-06-01 | Matt Reid | 0 | 0 | 0 | 88 | FS | -6
90 | Electrical Carport Roughin | FALSE | 0 | MEP | 2 | 2026-05-21 | 2026-05-22 | DECAV Pty Ltd, Matt Reid | 0 | 0 | 0 | 82 | FS | 3
91 | Painting Ext | FALSE | 0 | Painter | 5 | 2026-05-25 | 2026-05-29 | Matt Reid, MS Paterson Painting and Decorating | 0 | 0 | 0 | 76 | FS | 15
92 | Plaster Install Carport | FALSE | 0 | Plastering | 4 | 2026-05-27 | 2026-06-01 | Matt Reid | 0 | 0 | 0 | 90 | FS | 2
93 | Carpet (Commercial Grade) | FALSE | 0 | Finishing & Handover | 3 | 2026-05-29 | 2026-06-02 | Matt Reid | 0 | 0 | 0 | 62 | FS | 19
94 | Install Carport Doors (Entry & Rear) | FALSE | 0 | Carpentry | 1 | 2026-06-02 | 2026-06-02 | Dale Psaila, Lachlan Findlay, Matt Reid | 0 | 0 | 0 | 89 | FS | 0 | 92 | FS | 0
95 | Ramp/Entry Tiling | FALSE | 0 |  | 4 | 2026-06-02 | 2026-06-05 | Expo Marble & Tiling, Matt Reid | 0 | 0 | 0
96 | Painting to Carport | FALSE | 0 | Finishing & Handover | 4 | 2026-06-03 | 2026-06-09 | Matt Reid, MS Paterson Painting and Decorating | 0 | 0 | 0 | 94 | FS | 0 | 92 | FS | 1
97 | Final TH Inspection (Defects) | FALSE | 0 | Carpentry | 5 | 2026-06-04 | 2026-06-11 | Dale Psaila, Lachlan Findlay, Matt Reid | 0 | 0 | 0 | 93 | FS | 1
98 | Carport Fitoff | FALSE | 0 | Carpentry | 1 | 2026-06-10 | 2026-06-10 | Dale Psaila, Lachlan Findlay, Matt Reid | 0 | 0 | 0 | 96 | FS | 0
99 | Garage Roller Door Install Carport | FALSE | 0 | Finishing & Handover | 1 | 2026-06-10 | 2026-06-10 | Matt Reid | 0 | 0 | 0 | 96 | FS | 0
100 | Cleaner | FALSE | 0 | Finishing & Handover | 2 | 2026-06-12 | 2026-06-15 | Matt Reid | 0 | 0 | 0 | 97 | FS | 0
101 | Final Building Inspection | FALSE | 0 | Key Milestones | 1 | 2026-06-12 | 2026-06-12 | Matt Reid | 0 | 0 | 0 | 93 | FS | 3 | 99 | FS | 1
102 | Client Walkthrough (Final) | FALSE | 0 | Finishing & Handover | 1 | 2026-06-15 | 2026-06-15 | Matt Reid | 0 | 0 | 0 | 101 | FS | 0
103 | Completion of all outstanding items | FALSE | 0 |  | 71 | 2026-06-16 | 2026-09-22 | Matt Reid | 0 | 0 | 0 | 100 | FS | 0
104 | Decomission SIte | FALSE | 0 | Key Milestones | 1 | 2026-09-23 | 2026-09-23 | Matt Reid | 0 | 0 | 0 | 105 | SS | 0
105 | PROJECT Handover | FALSE | 0 | Finishing & Handover | 1 | 2026-09-23 | 2026-09-23 | Matt Reid | 0 | 0 | 0