## Schedules
Schedule - List - 17 Glyndon Ave - FC (exported on May 14, 2026)
ID # | Title | Complete | Percent Complete | Phase | Duration | Start | End | Assigned To | Accepted | Pending | Declined | Pred 1 Id | Pred 1 Type | Pred 1 Lag | Pred 2 Id | Pred 2 Type | Pred 2 Lag | Pred 3 Id | Pred 3 Type | Pred 3 Lag | Pred 4 Id | Pred 4 Type | Pred 4 Lag | Pred 5 Id | Pred 5 Type | Pred 5 Lag
1 | Deposit Progress Claim | TRUE | 100 | Key Milestones | 1 | 2025-11-14 | 2025-11-14 | Clive Webster, Oliver Trifunovski | 0 | 0 | 0
2 | Mains upgrade to the property | TRUE | 100 | MEP | 1 | 2025-11-14 | 2025-11-14 | Hardwire, Oliver Trifunovski | 0 | 0 | 0
3 | Plumbing make safe | TRUE | 100 | MEP | 1 | 2025-11-14 | 2025-11-14 | JCB Plumbing & Maintenance, Oliver Trifunovski | 0 | 0 | 0
4 | Asbestos Testing (if req'd) | TRUE | 100 | Demolition | 1 | 2025-11-17 | 2025-11-17 | Oliver Trifunovski, Simcat Demolitions | 0 | 0 | 0
5 | Electrical make safe | TRUE | 100 | MEP | 1 | 2025-11-17 | 2025-11-17 | Hardwire, Oliver Trifunovski | 0 | 0 | 0
6 | Electrical Make Safe | TRUE | 100 | MEP | 1 | 2025-11-17 | 2025-11-17 | Hardwire, Oliver Trifunovski | 0 | 0 | 0
7 | Neighbour Notification | TRUE | 100 | Site Preparation | 1 | 2025-11-17 | 2025-11-17 | Oliver Trifunovski | 0 | 0 | 0
8 | Plumbing Make Safe | TRUE | 100 | MEP | 1 | 2025-11-17 | 2025-11-17 | JCB Plumbing & Maintenance, Oliver Trifunovski | 0 | 0 | 0
9 | Site Setup / Protection/ Cameras etc | TRUE | 100 | Site Preparation | 3 | 2025-11-17 | 2025-11-19 | Oliver Trifunovski | 0 | 0 | 0 | 1 | FS | 0 | 7 | SS | 0 | 6 | SS | 0 | 8 | SS | 0 | 4 | SS | 0
10 | Demolition - Simcat Pt 1 | TRUE | 100 | Demolition | 14 | 2025-11-18 | 2025-12-05 | Oliver Trifunovski, Simcat Demolitions | 0 | 0 | 0 | 11 | FS | -1
11 | Pre-Demo Meeting | TRUE | 100 | Demolition | 1 | 2025-11-18 | 2025-11-18 | Oliver Trifunovski, Simcat Demolitions | 0 | 0 | 0 | 9 | FS | -2
12 | Sub-Floor Plumbing Camera/Test | TRUE | 100 | MEP | 1 | 2025-11-18 | 2025-11-18 | JCB Plumbing & Maintenance, Oliver Trifunovski | 0 | 0 | 0 | 8 | SS | 1
13 | Under Slab Plumbing | TRUE | 100 | MEP | 2 | 2025-12-10 | 2025-12-11 | JCB Plumbing & Maintenance, Oliver Trifunovski | 0 | 0 | 0 | 10 | FS | 2
14 | 3 Phase upgrade pole to pit | TRUE | 100 | MEP | 1 | 2025-12-15 | 2025-12-15 | Hardwire, Oliver Trifunovski | 0 | 0 | 0
15 | Concrete slab works | TRUE | 100 | Concrete | 4 | 2025-12-15 | 2025-12-18 | Metro Concrete Works, Oliver Trifunovski | 0 | 0 | 0
16 | Concreting | TRUE | 100 | Concrete | 5 | 2025-12-15 | 2025-12-19 | Metro Concrete Works, Oliver Trifunovski | 0 | 0 | 0
17 | Pre slab inspection PM | TRUE | 100 | Key Milestones | 1 | 2025-12-16 | 2025-12-16 | Oliver Trifunovski | 0 | 0 | 0
18 | Steel inspection PM | TRUE | 100 | Key Milestones | 1 | 2025-12-18 | 2025-12-18 | Oliver Trifunovski | 0 | 0 | 0
19 | Annual Holidays | TRUE | 100 | Other | 8 | 2025-12-19 | 2026-01-02 | Oliver Trifunovski | 0 | 0 | 0
20 | Base Progress Claim | TRUE | 100 | Key Milestones | 1 | 2025-12-19 | 2025-12-19 | Clive Webster, Oliver Trifunovski | 0 | 0 | 0 | 16 | FS | -1
21 | Pier/Pad Inspection | TRUE | 100 | Key Milestones | 1 | 2025-12-19 | 2025-12-19 | Oliver Trifunovski | 0 | 0 | 0 | 16 | SS | 4
22 | Re-new Existing Subfloor areas | TRUE | 100 | Carpentry | 5 | 2026-01-05 | 2026-01-09 | James Quinn, Oliver Trifunovski | 0 | 0 | 0 | 19 | FS | 0
23 | Slab Mark-out | TRUE | 100 | Carpentry | 1 | 2026-01-05 | 2026-01-05 | James Quinn, Oliver Trifunovski | 0 | 0 | 0 | 19 | FS | 0 | 16 | FS | 7
24 | Truss Measure Up | TRUE | 100 | Deliveries & Meetings | 1 | 2026-01-06 | 2026-01-06 | Clive Webster, Oliver Trifunovski | 0 | 0 | 0
25 | Frameworks | TRUE | 100 | Carpentry | 15 | 2026-01-12 | 2026-02-02 | James Quinn, Oliver Trifunovski | 0 | 0 | 0
26 | Steel measure | TRUE | 100 | Deliveries & Meetings | 1 | 2026-01-12 | 2026-01-12 | Oliver Trifunovski | 0 | 0 | 0
27 | Steel Measure Up | TRUE | 100 | Steel Work | 1 | 2026-01-12 | 2026-01-12 | Oliver Trifunovski, Sutton Steel | 0 | 0 | 0 | 23 | FS | 4
28 | Subfloor Inspection | TRUE | 100 | Key Milestones | 1 | 2026-01-12 | 2026-01-12 | Oliver Trifunovski | 0 | 0 | 0 | 22 | FS | 0
29 | Truss measure | TRUE | 100 | Deliveries & Meetings | 1 | 2026-01-12 | 2026-01-12 | Oliver Trifunovski | 0 | 0 | 0
30 | Carpentry | TRUE | 100 | Carpentry | 1 | 2026-01-16 | 2026-01-16 | James Quinn, Oliver Trifunovski | 0 | 0 | 0
31 | M10 subfloor material del | TRUE | 100 | Deliveries & Meetings | 1 | 2026-01-16 | 2026-01-16 | Oliver Trifunovski | 0 | 0 | 0
32 | Carpentry | TRUE | 100 | Carpentry | 15 | 2026-01-19 | 2026-02-09 | James Quinn, Oliver Trifunovski | 0 | 0 | 0
33 | Carpentry - Subfloor, Frame & Trusses | TRUE | 100 | Carpentry | 17 | 2026-01-19 | 2026-02-11 | James Quinn, Oliver Trifunovski | 0 | 0 | 0
34 | Steel install | TRUE | 100 | Steel Work | 1 | 2026-01-20 | 2026-01-20 | Oliver Trifunovski, Sutton Steel | 0 | 0 | 0
35 | Steel Install | TRUE | 100 | Steel Work | 2 | 2026-01-20 | 2026-01-21 | Oliver Trifunovski, Sutton Steel | 0 | 0 | 0 | 27 | FS | 5
36 | Australia Day Public Holiday | TRUE | 100 | Other | 1 | 2026-01-27 | 2026-01-27 | Oliver Trifunovski | 0 | 0 | 0
37 | Client meeting | TRUE | 100 | Deliveries & Meetings | 1 | 2026-01-28 12:00 | 2026-01-28 | Clive Webster, Oliver Trifunovski | 0 | 0 | 0
38 | Peter Brick layer site visit and quote | TRUE | 100 | Deliveries & Meetings | 1 | 2026-01-29 10:00 | 2026-01-29 11:00 | Oliver Trifunovski | 0 | 0 | 0
39 | Bingo 6m³ mixed marrell | TRUE | 100 | Deliveries & Meetings | 1 | 2026-01-30 | 2026-01-30 | Oliver Trifunovski | 0 | 0 | 0
40 | Stump hole inspection (AM) (Pased) | TRUE | 100 | Key Milestones | 1 | 2026-02-02 | 2026-02-02 | Oliver Trifunovski | 0 | 0 | 0
41 | Subfloor framing | TRUE | 100 | Carpentry | 3 | 2026-02-02 | 2026-02-04 | James Quinn, Oliver Trifunovski | 0 | 0 | 0
42 | Scaffold Fall Protection | TRUE | 100 | Labourers | 1 | 2026-02-03 | 2026-02-03 | John Bainbridge, Oliver Trifunovski | 0 | 0 | 0 | 25 | FS | 0
43 | Truss Delivery | TRUE | 100 | Deliveries & Meetings | 1 | 2026-02-04 | 2026-02-04 | Clive Webster, Oliver Trifunovski | 0 | 0 | 0
44 | Truss delivery | TRUE | 100 | Deliveries & Meetings | 1 | 2026-02-04 12:00 | 2026-02-04 | Oliver Trifunovski | 0 | 0 | 0
45 | Client electrical subfloor | TRUE | 100 | Deliveries & Meetings | 1 | 2026-02-05 | 2026-02-05 | Oliver Trifunovski | 0 | 0 | 0
46 | Inspection to subfloor am | TRUE | 100 | Key Milestones | 1 | 2026-02-06 | 2026-02-06 | Oliver Trifunovski | 0 | 0 | 0
47 | Plumbing Subfloor Rough in | TRUE | 100 | MEP | 1 | 2026-02-06 | 2026-02-06 | JCB Plumbing & Maintenance, Oliver Trifunovski | 0 | 0 | 0
48 | Subfloor - Frame Inspection | TRUE | 100 | Key Milestones | 1 | 2026-02-06 | 2026-02-06 | Clive Webster, Oliver Trifunovski | 0 | 0 | 0 | 25 | FS | 3
49 | Subfloor plumbing | TRUE | 100 | MEP | 1 | 2026-02-06 | 2026-02-06 | JCB Plumbing & Maintenance, Oliver Trifunovski | 0 | 0 | 0
50 | Window & Door Orders | TRUE | 100 | Deliveries & Meetings | 1 | 2026-02-06 | 2026-02-06 | Oliver Trifunovski | 0 | 0 | 0 | 16 | FS | 30
51 | Electrical Subflor Roughin | TRUE | 100 | MEP | 1 | 2026-02-09 | 2026-02-09 | Hardwire, Oliver Trifunovski | 0 | 0 | 0
52 | Electrical to subfloor | TRUE | 100 | MEP | 2 | 2026-02-09 | 2026-02-10 | Hardwire, Oliver Trifunovski | 0 | 0 | 0
53 | Sheet Flooring | TRUE | 100 | Carpentry | 3 | 2026-02-11 | 2026-02-13 | James Quinn, Oliver Trifunovski | 0 | 0 | 0 | 54 | SS | 0
54 | Sheeting to subfloor | TRUE | 100 | Carpentry | 5 | 2026-02-11 | 2026-02-17 | James Quinn, Oliver Trifunovski | 0 | 0 | 0
55 | Sub Floor Insulation | TRUE | 100 | Insulation | 1 | 2026-02-11 | 2026-02-11 | Pride Insulation | 0 | 0 | 0 | 51 | FS | 1
56 | Subfloor insulation ( confirmed ) | TRUE | 100 | Carpentry | 1 | 2026-02-11 | 2026-02-11 | Oliver Trifunovski, Pride Insulation | 0 | 0 | 0
57 | Framing (Int & Ext) | TRUE | 100 |  | 6 | 2026-02-16 | 2026-02-23 | James Quinn, Oliver Trifunovski | 0 | 0 | 0
58 | AC walk-through with Brett | TRUE | 100 |  | 1 | 2026-02-17 09:00 | 2026-02-17 | Oliver Trifunovski | 0 | 1 | 0
59 | Carpentry | TRUE | 100 |  | 3 | 2026-02-18 | 2026-02-20 | Oliver Trifunovski | 0 | 0 | 0
60 | Fascia & Gutter Install | TRUE | 100 | Roofing | 1 | 2026-02-18 | 2026-02-18 | Oliver Trifunovski | 0 | 0 | 0 | 25 | FS | 4 | 42 | FS | 10
61 | Gutters to existing roof | TRUE | 100 |  | 1 | 2026-02-18 | 2026-02-18 | Oliver Trifunovski | 0 | 0 | 0
62 | Facia & gutters | TRUE | 100 |  | 2 | 2026-02-20 | 2026-02-23 | Oliver Trifunovski | 0 | 0 | 0
63 | Fascia & Gutter Install | TRUE | 100 |  | 1 | 2026-02-20 | 2026-02-20 | Oliver Trifunovski | 0 | 0 | 0
64 | Client meeting | TRUE | 100 |  | 1 | 2026-02-20 07:30 | 2026-02-20 | Oliver Trifunovski | 0 | 0 | 0
65 | Site Clean - Rubble remove etc | TRUE | 100 |  | 1 | 2026-02-23 | 2026-02-23 | Oliver Trifunovski | 0 | 0 | 0
66 | Tavis Brick cleaning and site rubbish removal. | TRUE | 100 |  | 1 | 2026-02-23 | 2026-02-23 | Oliver Trifunovski | 0 | 0 | 0
67 | Reminder to call Paul for kitchen measure | TRUE | 100 |  | 1 | 2026-02-23 10:00 | 2026-02-23 | Oliver Trifunovski | 0 | 0 | 0
68 | 6m³ mixed Marell | TRUE | 100 |  | 1 | 2026-02-25 | 2026-02-25 | Oliver Trifunovski | 0 | 0 | 0
69 | Carpentry Works | TRUE | 100 |  | 1 | 2026-02-25 | 2026-02-25 | Oliver Trifunovski | 0 | 0 | 0
70 | Scaffold - Front | TRUE | 100 |  | 3 | 2026-02-25 | 2026-02-27 |  | 0 | 0 | 0
71 | Scaffolding site clean-up | TRUE | 100 |  | 3 | 2026-02-25 | 2026-02-27 | Oliver Trifunovski | 0 | 0 | 0
72 | Bingo 4m³ masonry bin | TRUE | 100 |  | 1 | 2026-02-26 | 2026-02-26 | Oliver Trifunovski | 0 | 0 | 0
73 | Frame inspection AM | TRUE | 100 |  | 1 | 2026-02-26 | 2026-02-26 | Oliver Trifunovski | 0 | 0 | 0
74 | Frame Progress Claim | TRUE | 100 | Key Milestones | 1 | 2026-02-27 | 2026-02-27 | Clive Webster, Oliver Trifunovski | 0 | 0 | 0 | 25 | FS | 18
75 | Roof tile delivery | TRUE | 100 |  | 1 | 2026-03-04 | 2026-03-04 | Greens Roofing, Oliver Trifunovski | 0 | 0 | 0
76 | Roof Tile Delivery | TRUE | 100 |  | 1 | 2026-03-04 | 2026-03-04 | Oliver Trifunovski | 0 | 0 | 0
77 | Roof tile install | TRUE | 100 |  | 3 | 2026-03-04 | 2026-03-06 | Greens Roofing, Oliver Trifunovski | 0 | 0 | 0
78 | Roofing Works | TRUE | 100 | Roofing | 3 | 2026-03-04 | 2026-03-06 | Oliver Trifunovski | 0 | 0 | 0 | 60 | FS | 7 | 63 | FS | 5 | 76 | FS | -1 | 70 | FS | 0
79 | Electrical rough-in | TRUE | 100 |  | 4 | 2026-03-10 | 2026-03-13 | Hardwire, Oliver Trifunovski | 0 | 0 | 0
80 | Electrical Rough-In | TRUE | 100 | MEP | 4 | 2026-03-10 | 2026-03-13 | Hardwire, Oliver Trifunovski | 0 | 0 | 0 | 78 | FS | 0
81 | Joinery Measure Up | TRUE | 100 | Deliveries & Meetings | 1 | 2026-03-10 | 2026-03-10 | Borella Kitchens & Joinery, Oliver Trifunovski | 0 | 0 | 0 | 78 | FS | 0
82 | Solar install | TRUE | 100 |  | 1 | 2026-03-10 | 2026-03-10 | DECAV Pty Ltd, Oliver Trifunovski | 0 | 0 | 0
83 | Solar install | TRUE | 100 | MEP | 1 | 2026-03-10 | 2026-03-10 | DECAV Pty Ltd, Oliver Trifunovski | 0 | 0 | 0 | 78 | FS | 0
84 | Joinery measure | TRUE | 100 |  | 1 | 2026-03-10 09:00 | 2026-03-10 | Oliver Trifunovski | 0 | 0 | 0
85 | Capentry Works (Roof) | TRUE | 100 |  | 1 | 2026-03-13 | 2026-03-13 | Oliver Trifunovski | 0 | 0 | 0
86 | Gable carpentry | TRUE | 100 |  | 1 | 2026-03-13 | 2026-03-13 | Oliver Trifunovski | 0 | 0 | 0
87 | Roof tiler | TRUE | 100 |  | 1 | 2026-03-17 | 2026-03-17 | Oliver Trifunovski | 0 | 0 | 0
88 | Electrical Rough In | TRUE | 100 |  | 3 | 2026-03-18 | 2026-03-20 | Oliver Trifunovski | 0 | 0 | 0
89 | Electrical rough in | TRUE | 100 |  | 1 | 2026-03-18 | 2026-03-18 | Hardwire, Oliver Trifunovski | 0 | 0 | 0
90 | Scaffold removal | TRUE | 100 |  | 2 | 2026-03-18 | 2026-03-19 | Oliver Trifunovski | 0 | 0 | 0 | 83 | FS | 5
91 | Scaffolding removal | TRUE | 100 |  | 2 | 2026-03-18 | 2026-03-19 | Oliver Trifunovski | 0 | 0 | 0
92 | AC Rough in | TRUE | 100 |  | 2 | 2026-03-19 | 2026-03-20 | Comfort Heating & Cooling, Oliver Trifunovski | 0 | 0 | 0
93 | H&C Rough In | TRUE | 100 | MEP | 2 | 2026-03-19 | 2026-03-20 | Comfort Heating & Cooling, Oliver Trifunovski | 0 | 0 | 0 | 78 | FS | 7
94 | Electrical rough in | TRUE | 100 |  | 1 | 2026-03-20 | 2026-03-20 | Hardwire, Oliver Trifunovski | 0 | 0 | 0
95 | Concrete to pergola | TRUE | 100 | Concrete | 2 | 2026-03-24 | 2026-03-25 | Metro Concrete Works, Oliver Trifunovski | 0 | 0 | 0
96 | Paving Slab Concrete | TRUE | 100 | Concrete | 3 | 2026-03-24 | 2026-03-26 | Metro Concrete Works, Oliver Trifunovski | 0 | 0 | 0 | 90 | FS | 2
97 | Stormwater underground | TRUE | 100 |  | 1 | 2026-03-24 | 2026-03-24 | JCB Plumbing & Maintenance, Oliver Trifunovski | 0 | 0 | 0
98 | B&C Cavity del | TRUE | 100 |  | 1 | 2026-03-30 | 2026-03-30 | Oliver Trifunovski | 0 | 0 | 0
99 | AAA Window del | TRUE | 100 |  | 1 | 2026-03-31 | 2026-03-31 | Oliver Trifunovski | 0 | 0 | 0
100 | House Wrap | TRUE | 100 | Carpentry | 1 | 2026-04-01 | 2026-04-01 | John Bainbridge, Oliver Trifunovski | 0 | 0 | 0
101 | Installation of Windows/Doors | TRUE | 100 | Carpentry | 2 | 2026-04-01 | 2026-04-02 | James Quinn, Oliver Trifunovski | 0 | 0 | 0
102 | Internal Lock up | TRUE | 100 | Carpentry | 16 | 2026-04-01 | 2026-04-24 | Dale Psaila, James Quinn, Oliver Trifunovski | 0 | 0 | 0
103 | Proclima wrap | TRUE | 100 |  | 2 | 2026-04-01 | 2026-04-02 | Oliver Trifunovski | 0 | 0 | 0
104 | All timber window del | TRUE | 100 |  | 1 | 2026-04-02 | 2026-04-02 | Oliver Trifunovski | 0 | 0 | 0
105 | Carpentry | TRUE | 100 |  | 1 | 2026-04-02 | 2026-04-02 | Oliver Trifunovski | 0 | 0 | 0
106 | Carpentry | TRUE | 100 |  | 2 | 2026-04-07 | 2026-04-08 | Oliver Trifunovski | 0 | 0 | 0
107 | Slide door del | TRUE | 100 |  | 1 | 2026-04-13 | 2026-04-13 | Oliver Trifunovski | 0 | 0 | 0
108 | Sutton steel T lintle del | TRUE | 100 |  | 1 | 2026-04-13 | 2026-04-13 | Oliver Trifunovski | 0 | 0 | 0
109 | Arch door del | TRUE | 100 |  | 1 | 2026-04-14 | 2026-04-14 | Oliver Trifunovski | 0 | 0 | 0
110 | Eaves materials and shower base del | TRUE | 100 |  | 1 | 2026-04-15 | 2026-04-15 | Oliver Trifunovski | 0 | 1 | 0
111 | Carpentry | TRUE | 100 |  | 4 | 2026-04-17 | 2026-04-22 | Oliver Trifunovski | 0 | 1 | 0
112 | External Cladding | TRUE | 100 | Carpentry | 6 | 2026-04-17 | 2026-04-24 | Dale Psaila, James Quinn, Oliver Trifunovski | 0 | 0 | 0 | 100 | FS | 9 | 101 | FS | 0
113 | Thermawood confirmation measure | TRUE | 100 |  | 1 | 2026-04-17 08:00 | 2026-04-17 | Oliver Trifunovski | 0 | 1 | 0
114 | Plumbing & Electrical week of | TRUE | 100 |  | 6 | 2026-04-20 | 2026-04-27 | Hardwire, JCB Plumbing & Maintenance, Oliver Trifunovski | 0 | 0 | 0
115 | Plumbing rough in | TRUE | 100 |  | 2 | 2026-04-20 | 2026-04-21 | JCB Plumbing & Maintenance, Oliver Trifunovski | 0 | 0 | 0
116 | Plumbing SW | TRUE | 100 | MEP | 2 | 2026-04-20 | 2026-04-21 | JCB Plumbing & Maintenance, Oliver Trifunovski | 0 | 0 | 0
117 | Electrical rough in | TRUE | 100 |  | 2 | 2026-04-22 | 2026-04-23 | Hardwire, Oliver Trifunovski | 0 | 0 | 0
118 | Electrical rough in pt2 | TRUE | 100 |  | 4 | 2026-04-22 | 2026-04-27 | Hardwire, Oliver Trifunovski | 0 | 0 | 0
119 | Scaffold Adjustment (Cladding) | TRUE | 100 | Labourers | 1 | 2026-04-22 | 2026-04-22 | John Bainbridge, Oliver Trifunovski | 0 | 0 | 0
120 | Sash window install | TRUE | 100 |  | 1 | 2026-04-27 | 2026-04-27 | Oliver Trifunovski | 0 | 0 | 0
121 | Brick laying | TRUE | 100 |  | 4 | 2026-04-28 | 2026-05-01 | Oliver Trifunovski | 0 | 0 | 0
122 | Brick/Block Works | TRUE | 100 | Bricklayers | 3 | 2026-04-28 | 2026-04-30 | Brick on Brick Pty Ltd, Oliver Trifunovski | 0 | 0 | 0 | 100 | FS | 16 | 101 | FS | 0
123 | Ceiling battens | TRUE | 100 |  | 3 | 2026-04-29 | 2026-05-01 | Oliver Trifunovski | 0 | 0 | 0
124 | Plaster Battens | TRUE | 100 |  | 3 | 2026-04-29 | 2026-05-01 | Oliver Trifunovski | 0 | 0 | 0
125 | 3D Camera Internal | TRUE | 100 | Labourers | 1 | 2026-05-04 | 2026-05-04 | Clive Webster, Greg Paull | 0 | 0 | 0
126 | Carpentry | TRUE | 100 |  | 5 | 2026-05-04 | 2026-05-08 | Oliver Trifunovski | 0 | 0 | 0
127 | Insulation Install | TRUE | 100 | Insulation | 1 | 2026-05-05 | 2026-05-05 | Oliver Trifunovski, Pride Insulation | 0 | 0 | 0 | 80 | FS | 34
128 | Insululation | TRUE | 100 |  | 1 | 2026-05-05 | 2026-05-05 | Oliver Trifunovski | 0 | 0 | 0
129 | Plaster delivery | TRUE | 100 |  | 2 | 2026-05-05 | 2026-05-06 |  | 0 | 0 | 0
130 | Arch door delivery | TRUE | 100 |  | 1 | 2026-05-07 | 2026-05-07 | Oliver Trifunovski | 0 | 0 | 0
131 | Electrical Trench | TRUE | 100 |  | 2 | 2026-05-07 | 2026-05-08 | Oliver Trifunovski | 0 | 0 | 0
132 | Slide door install | TRUE | 100 |  | 1 | 2026-05-07 | 2026-05-07 | Oliver Trifunovski | 0 | 0 | 0
133 | Bathtub mixer install and reloaction | TRUE | 100 |  | 1 | 2026-05-08 | 2026-05-08 | Oliver Trifunovski | 0 | 0 | 0
134 | Bingo 6m³ Marrel | TRUE | 100 |  | 1 | 2026-05-08 | 2026-05-08 | Oliver Trifunovski | 0 | 1 | 0
135 | Plaster Install | FALSE | 0 | Plastering | 12 | 2026-05-08 | 2026-05-25 | Oliver Trifunovski, VLS Plastering | 0 | 0 | 0 | 125 | FS | -1 | 124 | FS | 4
136 | Plastering | FALSE | 0 |  | 12 | 2026-05-08 | 2026-05-25 | Oliver Trifunovski | 0 | 0 | 0
137 | Stormwater unblock | TRUE | 100 |  | 1 | 2026-05-11 | 2026-05-11 | Oliver Trifunovski | 0 | 0 | 0
138 | Carpentry | FALSE | 0 |  | 6 | 2026-05-13 | 2026-05-20 | Oliver Trifunovski | 0 | 0 | 0
139 | Electrical conduit into Trench | TRUE | 100 |  | 1 | 2026-05-14 | 2026-05-14 | Hardwire, Oliver Trifunovski | 1 | 1 | 0
140 | External Cladding | FALSE | 0 |  | 5 | 2026-05-14 | 2026-05-20 | Dale Psaila, Oliver Trifunovski | 0 | 2 | 0
141 | Solar conection to main meter box | TRUE | 100 |  | 1 | 2026-05-14 | 2026-05-14 | Oliver Trifunovski | 0 | 0 | 0
142 | AC register cutouts | FALSE | 0 |  | 1 | 2026-05-18 | 2026-05-18 | Oliver Trifunovski | 0 | 0 | 0
143 | Electrical cut outs | FALSE | 0 |  | 1 | 2026-05-18 | 2026-05-18 | Hardwire, Oliver Trifunovski | 0 | 0 | 0
144 | Lock Up Progress Claim | FALSE | 0 | Key Milestones | 1 | 2026-05-18 | 2026-05-18 | Clive Webster, Oliver Trifunovski | 0 | 0 | 0 | 112 | FS | 15
145 | Waterproofing, Tiling & Caulking | FALSE | 0 | Tiler | 15 | 2026-05-20 | 2026-06-10 | Expo Marble & Tiling, Oliver Trifunovski | 0 | 0 | 0 | 135 | FS | -4
146 | Painting - Exterior | FALSE | 0 | Painter | 5 | 2026-05-21 | 2026-05-27 | MS Paterson Painting and Decorating, Oliver Trifunovski | 0 | 0 | 0 | 112 | FS | 18
147 | Joinery Install | FALSE | 0 | Joinery | 5 | 2026-05-26 | 2026-06-01 | Borella Kitchens & Joinery, Oliver Trifunovski | 0 | 0 | 0 | 135 | FS | 0
148 | Carpentry - Fix | FALSE | 0 |  | 5 | 2026-06-01 | 2026-06-05 | Dale Psaila, Oliver Trifunovski | 0 | 0 | 0
149 | Stone Measure-up | FALSE | 0 | Deliveries & Meetings | 1 | 2026-06-02 | 2026-06-02 | Oliver Trifunovski | 0 | 0 | 0 | 147 | FS | 0
150 | Showerscreen/Mirrors Measure | FALSE | 0 | Finishing & Handover | 1 | 2026-06-05 | 2026-06-05 | Oliver Trifunovski, Rocbilt | 0 | 0 | 0 | 145 | FS | -3
151 | Prime Walls | FALSE | 0 | Painter | 2 | 2026-06-15 | 2026-06-16 | MS Paterson Painting and Decorating, Oliver Trifunovski | 0 | 0 | 0 | 147 | FS | 8
152 | Painting - Interior | FALSE | 0 | Painter | 8 | 2026-06-17 | 2026-06-26 | MS Paterson Painting and Decorating, Oliver Trifunovski | 0 | 0 | 0 | 151 | FS | 0
153 | Countertop Install | FALSE | 0 | Joinery | 2 | 2026-06-18 | 2026-06-19 | Oliver Trifunovski | 0 | 0 | 0 | 149 | FS | 10
154 | Fixing Progress Claim | FALSE | 0 | Key Milestones | 1 | 2026-06-22 | 2026-06-22 | Clive Webster, Oliver Trifunovski | 0 | 0 | 0 | 153 | FS | 0
155 | Showerscreen/Mirrors Install | FALSE | 0 | Finishing & Handover | 1 | 2026-06-22 | 2026-06-22 | Oliver Trifunovski | 0 | 0 | 0 | 150 | FS | 9
156 | Carpet Installation | FALSE | 0 | Floor Coverings | 3 | 2026-06-29 | 2026-07-01 | Oliver Trifunovski | 0 | 0 | 0
157 | Electrical Fitoff | FALSE | 0 | MEP | 5 | 2026-06-29 | 2026-07-03 | Hardwire, Oliver Trifunovski | 0 | 0 | 0 | 152 | FS | 0
158 | Plumbing Fitoff | FALSE | 0 | MEP | 5 | 2026-06-29 | 2026-07-03 | JCB Plumbing & Maintenance, Oliver Trifunovski | 0 | 0 | 0 | 152 | FS | 0
159 | H&C Fitoff | FALSE | 0 | MEP | 3 | 2026-07-01 | 2026-07-03 | Comfort Heating & Cooling, Oliver Trifunovski | 0 | 0 | 0 | 152 | FS | 2
160 | Power upgrade truck app | FALSE | 0 |  | 1 | 2026-07-01 09:30 | 2026-07-01 | Hardwire, Oliver Trifunovski | 0 | 0 | 0
161 | Final Touch-up & Clean | FALSE | 0 | Finishing & Handover | 5 | 2026-07-02 | 2026-07-08 | Dale Psaila, James Quinn, Oliver Trifunovski | 0 | 0 | 0 | 156 | FS | 0
162 | Interior Hardware Install | FALSE | 0 | Carpentry | 3 | 2026-07-06 | 2026-07-08 | Dale Psaila, James Quinn, Oliver Trifunovski | 0 | 0 | 0 | 159 | FS | 0
163 | Floorboard installation | FALSE | 0 | Floor Coverings | 5 | 2026-07-10 | 2026-07-16 | Oliver Trifunovski | 0 | 0 | 0 | 162 | FS | 1
164 | Cleaner | FALSE | 0 | Finishing & Handover | 2 | 2026-07-20 | 2026-07-21 | Oliver Trifunovski | 0 | 0 | 0 | 161 | FS | 7
165 | Completion of Final Items | FALSE | 0 | Finishing & Handover | 63 | 2026-07-24 | 2026-10-21 | Oliver Trifunovski | 0 | 0 | 0 | 164 | FS | 2
166 | Final Building Inspection | FALSE | 0 | Key Milestones | 1 | 2026-07-24 | 2026-07-24 | Oliver Trifunovski | 0 | 0 | 0 | 164 | FS | 2
167 | Appliance Installation | FALSE | 0 | Finishing & Handover | 1 | 2026-10-15 | 2026-10-15 | Hardwire, Oliver Trifunovski | 0 | 0 | 0
168 | Final Progress Claim | FALSE | 0 | Key Milestones | 1 | 2026-10-15 | 2026-10-15 | Clive Webster, Oliver Trifunovski | 0 | 0 | 0
169 | Handover | FALSE | 0 | Key Milestones | 1 | 2026-10-15 | 2026-10-15 | Clive Webster, Oliver Trifunovski | 0 | 0 | 0 | 167 | SS | 0 | 168 | SS | 0