## Schedules
Schedule - List - 1/55 Melbourne Ave, Glenroy Vic 3046 (exported on May 14, 2026)
ID # | Title | Complete | Percent Complete | Phase | Duration | Start | End | Assigned To | Accepted | Pending | Declined | Pred 1 Id | Pred 1 Type | Pred 1 Lag
1 | Pre-Con + Procurement | FALSE | 0 |  | 5 | 2026-05-18 | 2026-05-22 | Matt Reid | 0 | 0 | 0
2 | Site Setup/Demolition/Strip-out | FALSE | 0 |  | 2 | 2026-05-25 | 2026-05-26 | John Bainbridge, Matt Reid | 0 | 0 | 0 | 1 | FS | 0
3 | Substrate Prep - Screed to Falls | FALSE | 0 |  | 3 | 2026-05-28 | 2026-06-01 | Expo Marble & Tiling, Matt Reid | 0 | 0 | 0 | 2 | FS | 1
4 | Screed Cure time - QA Checklist | FALSE | 0 |  | 3 | 2026-06-02 | 2026-06-04 | Matt Reid | 0 | 0 | 0 | 3 | FS | 0
5 | Waterproofing Buytonol Membrane Install | FALSE | 0 |  | 3 | 2026-06-05 | 2026-06-10 | Matt Reid | 0 | 0 | 0 | 4 | FS | 0
6 | Membrane Cure + Flood Test Hold Point | FALSE | 0 |  | 3 | 2026-06-11 | 2026-06-15 | Matt Reid | 0 | 0 | 0 | 5 | FS | 0
7 | Door Jamb Reinstall + Door Install | FALSE | 0 |  | 2 | 2026-06-16 | 2026-06-17 | Dale Psaila, Lachlan Findlay, Matt Reid | 0 | 0 | 0 | 6 | FS | 0
8 | Pedestals + Pavers + Skirting Tiles | FALSE | 0 |  | 3 | 2026-06-18 | 2026-06-22 | Expo Marble & Tiling, Matt Reid | 0 | 0 | 0 | 7 | FS | 0
9 | Architraves + Internal Skirting | FALSE | 0 |  | 3 | 2026-06-19 | 2026-06-23 | Dale Psaila, Lachlan Findlay, Matt Reid | 0 | 0 | 0
10 | Painting & Finishes | FALSE | 0 |  | 4 | 2026-06-23 | 2026-06-26 | Matt Reid | 0 | 0 | 0 | 9 | FS | -1
11 | Handover | FALSE | 0 |  | 2 | 2026-06-29 | 2026-06-30 | Matt Reid | 0 | 0 | 0