## Schedules
Schedule - List - 801 Main Hurstbridge Road FC (exported on May 14, 2026)
ID # | Title | Complete | Percent Complete | Phase | Duration | Start | End | Assigned To | Accepted | Pending | Declined | Pred 1 Id | Pred 1 Type | Pred 1 Lag | Pred 2 Id | Pred 2 Type | Pred 2 Lag
1 | Pre-Con + Procurement | TRUE | 100 |  | 3 | 2026-04-23 | 2026-04-27 | Matt Reid | 0 | 0 | 0
2 | Structural Carpentry & Framing | TRUE | 100 |  | 2 | 2026-04-28 | 2026-04-29 | Matt Reid | 0 | 0 | 0
3 | Demolition & Strip-Out | TRUE | 100 |  | 2 | 2026-04-30 | 2026-05-01 | Matt Reid | 0 | 0 | 0
4 | Electrical Rough In | TRUE | 100 |  | 2 | 2026-04-30 | 2026-05-01 | Matt Reid | 0 | 0 | 0
5 | Plaster Cieling Grid Install | TRUE | 100 |  | 1 | 2026-05-04 | 2026-05-04 | Matt Reid | 0 | 0 | 0
6 | Plumbing Rough-in (Subfloor) | TRUE | 100 |  | 1 | 2026-05-04 | 2026-05-04 | Matt Reid | 0 | 0 | 0
7 | A/C Rough In (Week of) | TRUE | 100 |  | 1 | 2026-05-06 | 2026-05-06 | Matt Reid | 0 | 0 | 0 | 4 | FS | 2
8 | Joinery Measure up | TRUE | 100 |  | 1 | 2026-05-06 | 2026-05-06 | Matt Reid | 0 | 0 | 0
9 | Plumbing Rough In | TRUE | 100 |  | 2 | 2026-05-07 | 2026-05-08 | Matt Reid | 0 | 0 | 0 | 2 | FS | 5 | 6 | FS | 2
10 | Carpentry | TRUE | 100 |  | 2 | 2026-05-11 | 2026-05-12 | Dale Psaila, Matt Reid | 0 | 0 | 0
11 | Electrical Rough in Cont... | TRUE | 100 |  | 2 | 2026-05-11 | 2026-05-12 | Matt Reid | 0 | 0 | 0 | 5 | FS | 4
12 | Plastering | FALSE | 0 |  | 3 | 2026-05-13 | 2026-05-15 |  | 0 | 0 | 0 | 10 | FS | 0
13 | Carpentry Fix | FALSE | 0 |  | 1 | 2026-05-19 | 2026-05-19 | Dale Psaila, Matt Reid | 0 | 0 | 0
14 | Painting Stage 1 | FALSE | 0 |  | 3 | 2026-05-20 | 2026-05-22 | Matt Reid | 0 | 0 | 0 | 13 | FS | 0
15 | Floor Levelling | FALSE | 0 |  | 2 | 2026-05-21 | 2026-05-22 | Matt Reid | 0 | 0 | 0
16 | Joinery / Cabinetry Install | FALSE | 0 |  | 2 | 2026-05-25 | 2026-05-26 | Matt Reid | 0 | 0 | 0 | 8 | FS | 12
17 | Flooring - Vinyl | FALSE | 0 |  | 3 | 2026-05-27 | 2026-05-29 | Matt Reid | 0 | 0 | 0 | 14 | FS | 2
18 | Tiling - Splashbacks | FALSE | 0 |  | 2 | 2026-06-01 | 2026-06-02 | Expo Marble & Tiling, Matt Reid | 0 | 0 | 0 | 17 | FS | 0
19 | Plumbing fit-off | FALSE | 0 |  | 2 | 2026-06-04 | 2026-06-05 | Matt Reid | 0 | 0 | 0 | 18 | FS | 1
20 | Electrical fit-off | FALSE | 0 |  | 4 | 2026-06-09 | 2026-06-12 | Matt Reid | 0 | 0 | 0 | 19 | FS | 0
21 | Carpentry Fitoff | FALSE | 0 |  | 3 | 2026-06-15 | 2026-06-17 | Dale Psaila, Matt Reid | 0 | 0 | 0 | 20 | FS | 0
22 | Cleaner | FALSE | 0 |  | 2 | 2026-06-18 | 2026-06-19 | Matt Reid | 0 | 0 | 0 | 21 | FS | 0
23 | Completion of all Outstanding Items | FALSE | 0 |  | 3 | 2026-06-22 | 2026-06-24 | Matt Reid | 0 | 0 | 0 | 22 | FS | 0
24 | Handover | FALSE | 0 |  | 1 | 2026-06-30 | 2026-06-30 | Matt Reid | 0 | 0 | 0