## Change Orders
Change Orders (exported on Thu, May 14, 2026)
Client | Job | CO ID# | Created date | Status | Status change date | Delay Days* | Contract Date* | Client last viewed | Deadline | % Invoiced | Builder cost | Client Price | Total markup
Serene Ho | 30 Connolly Ave, Coburg - FC | 30CON-0010 | 2026-05-05 | Approved on 5-13 | 2026-05-13 07:49 | 20 | 2025-12-05 | 2026-05-13 | 2026-05-14 | 0% | 4620 | 6108 | 1488
Rachel Shepheard | 17 Glyndon Ave - FC | 17GLYN-0022 | 2026-05-08 | Approved on 5-11 | 2026-05-11 10:00 | 1 | 2025-10-30 | 2026-05-11 | 2026-05-12 | 0% | 0 | 0 | 0
Rachel Shepheard | 17 Glyndon Ave - FC | 17GLYN-0018 | 2026-04-24 | Approved on 5-11 | 2026-05-11 09:40 | 2 | 2025-10-30 | 2026-05-11 | 2026-05-12 | 0% | 506 | 556 | 50
Sandra Wing | 29 River Gum Close, Diamond Creek FC | 29RIV-0014 | 2026-05-06 | Approved on 5-7 | 2026-05-07 17:13 | 1 | 2025-12-11 | 2026-05-07 |  | 0% | 220.95 | 315.64 | 94.69
Gino Marone | 801 Main Hurstbridge Road FC | 801MN-0007 | 2026-05-02 | Approved on 5-6 | 2026-05-06 17:49 | 2 | 2026-04-23 | 2026-05-06 |  | 0% | 215 | 687.2 | 472.2
Rachel Shepheard | 17 Glyndon Ave - FC | 17GLYN-0021 | 2026-05-06 | Approved on 5-6 | 2026-05-06 10:34 | 1 | 2025-10-30 | 2026-05-06 | 2026-05-07 | 0% | 649.85 | 869.85 | 220
Mick Hall | 11-15 Station Street, Diamond Creek - FC | 11STA-0020 | 2026-04-29 | Approved on 5-6 | 2026-05-06 08:05 | 1 | 2025-10-31 | 2026-05-07 | 2026-05-08 | 0% | 231.41 | 330.59 | 99.18
Mick Hall | 11-15 Station Street, Diamond Creek - FC | 11STA-0021 | 2026-04-29 | Approved on 5-6 | 2026-05-06 08:04 | 1 | 2025-10-31 | 2026-05-06 | 2026-05-08 | 0% | 2832.5 | 4046.43 | 1213.93
Gino Marone | 801 Main Hurstbridge Road FC | 801MN-0008 | 2026-05-03 | Approved on 5-5 | 2026-05-05 07:05 | 1 | 2026-04-23 | 2026-05-05 |  | 0% | 2463.21 | 3518.87 | 1055.66
Mick Hall | 11-15 Station Street, Diamond Creek - FC | 11STA-0022 | 2026-04-29 | Approved on 5-4 | 2026-05-04 18:51 | 1 | 2025-10-31 | 2026-05-06 | 2026-05-05 | 0% | 6877.8 | 9628.92 | 2751.12
Mick Hall | 11-15 Station Street, Diamond Creek - FC | 11STA-0023 | 2026-05-03 | Approved on 5-4 | 2026-05-04 18:50 | 1 | 2025-10-31 | 2026-05-06 |  | 0% | 1989.57 | 2842.24 | 852.67
Serene Ho | 30 Connolly Ave, Coburg - FC | 30CON-0007 | 2026-04-30 | Approved on 5-4 | 2026-05-04 11:21 | 3 | 2025-12-05 | 2026-05-04 | 2026-05-06 | 0% | 612 | 826.2 | 214.2
Serene Ho | 30 Connolly Ave, Coburg - FC | 30CON-0005 | 2026-04-30 | Approved on 5-4 | 2026-05-04 11:19 | 5 | 2025-12-05 | 2026-05-04 | 2026-05-05 | 0% | 550 | 742.5 | 192.5
Rachel Shepheard | 17 Glyndon Ave - FC | 17GLYN-0020 | 2026-05-01 | Approved on 5-1 | 2026-05-01 12:04 | 1 | 2025-10-30 | 2026-05-01 | 2026-05-05 | 0% | 866 | 1169.1 | 303.1
Gino Marone | 801 Main Hurstbridge Road FC | 801MN-0003 | 2026-04-24 | Approved on 4-30 | 2026-04-30 08:06 | 0 | 2026-04-23 | 2026-04-30 |  | 0% | 821.76 | 1173.94 | 352.18
Gino Marone | 801 Main Hurstbridge Road FC | 801MN-0005 | 2026-04-29 | Approved on 4-30 | 2026-04-30 08:05 | 2 | 2026-04-23 | 2026-04-30 | 2026-05-02 | 0% | 4503.89 | 6435.05 | 1931.16
Gino Marone | 801 Main Hurstbridge Road FC | 801MN-0004 | 2026-04-29 | Approved on 4-30 | 2026-04-30 08:04 | 1 | 2026-04-23 | 2026-04-30 | 2026-05-03 | 0% | 4050 | 6428.57 | 2378.57
Rachel Shepheard | 17 Glyndon Ave - FC | 17GLYN-0019 | 2026-04-29 | Approved on 4-29 | 2026-04-29 20:12 | 1 | 2025-10-30 | 2026-04-29 |  | 0% | 5230.5 | 7322.7 | 2092.2
Gino Marone | 801 Main Hurstbridge Road FC | 801MN-0001 | 2026-04-24 | Approved manually on 4-29 by Greg Paull | 2026-04-29 16:19 | 0 | 2026-04-23 |  |  | 0% | -7045 | -9784.8 | -2739.8
Stefano Scalzo | 89 Glen Park Road, Eltham North FC | 89GP-0047 | 2026-04-22 | Approved on 4-26 | 2026-04-26 09:20 | 1 | 2025-04-28 | 2026-04-26 | 2026-04-27 | 0% | 1238 | 1847.75 | 609.75
Gino Marone | 801 Main Hurstbridge Road FC | 801MN-0002 | 2026-04-24 | Approved manually on 4-24 by Greg Paull | 2026-04-24 12:54 | 0 | 2026-04-23 |  |  | 0% | -5280 | -5744.57 | -464.57
Tom Moore | 49 Kamarooka Drive Wattle Glen 3096 | 49KAM-0001 | 2026-04-19 | Approved on 4-19 | 2026-04-19 20:14 | 1 | 2026-02-12 | 2026-04-19 | 2026-04-20 | 100% | 660 | 942.86 | 282.86
Suzi & Chris Harris | 37 Robinson St Moonee Ponds - FC | 37ROB-0028 | 2026-04-17 | Approved on 4-17 | 2026-04-17 11:30 | 1 | 2025-06-25 | 2026-04-17 |  | 0% | 2924 | 3742.72 | 818.72
Sandra Wing | 29 River Gum Close, Diamond Creek FC | 29RIV-0013 | 2026-04-14 | Approved on 4-14 | 2026-04-14 18:56 | 1 | 2025-12-11 | 2026-04-15 |  | 100% | 185 | 276.12 | 91.12
Mick Hall | 11-15 Station Street, Diamond Creek - FC | 11STA-0019 | 2026-03-31 | Approved on 4-2 | 2026-04-02 20:15 | 1 | 2025-10-31 | 2026-04-02 | 2026-04-07 | 0% | 1738 | 2482.86 | 744.86
Rachel Shepheard | 17 Glyndon Ave - FC | 17GLYN-0017 | 2026-03-23 | Approved on 3-26 | 2026-03-26 09:00 | 1 | 2025-10-30 | 2026-03-26 |  | 0% | 9110 | 12298.5 | 3188.5
Mick Hall | 11-15 Station Street, Diamond Creek - FC | 11STA-0017 | 2026-03-24 | Approved manually on 3-25 by Greg Paull | 2026-03-25 17:11 | 1 | 2025-10-01 |  |  | 0% | 825 | 925 | 100
Mick Hall | 11-15 Station Street, Diamond Creek - FC | 11STA-0006 | 2025-12-12 | Approved manually on 3-25 by Greg Paull | 2026-03-25 17:10 | 0 | 2025-10-31 |  |  | 0% | -3300 | -3205 | 95
Suzi & Chris Harris | 37 Robinson St Moonee Ponds - FC | 37ROB-0024 | 2026-02-19 | Approved on 3-19 | 2026-03-19 22:50 | 1 | 2025-06-25 | 2026-03-19 | 2026-03-23 | 100% | 3760 | 6204 | 2444
Sandra Wing | 29 River Gum Close, Diamond Creek FC | 29RIV-0009 | 2026-02-19 | Approved on 3-19 | 2026-03-19 19:58 | 1 | 2025-12-11 | 2026-03-31 |  | 100% | 5174 | 6991.89 | 1817.89
Suzi & Chris Harris | 37 Robinson St Moonee Ponds - FC | 37ROB-0026 | 2026-03-17 | Approved on 3-17 | 2026-03-17 18:50 | 4 | 2025-06-30 | 2026-03-17 |  | 100% | 5134.66 | 6418.33 | 1283.67
Rachel Shepheard | 17 Glyndon Ave - FC | 17GLYN-0015 | 2026-03-06 | Approved on 3-14 | 2026-03-14 14:36 | 2 | 2025-10-30 | 2026-03-14 | 2026-03-16 | 0% | 1069 | 1443.15 | 374.15
Rachel Shepheard | 17 Glyndon Ave - FC | 17GLYN-0009 | 2026-02-20 | Approved on 3-13 | 2026-03-13 21:38 | 1 | 2025-10-30 | 2026-03-13 |  | 0% | 2950 | 3982.5 | 1032.5
Rachel Shepheard | 17 Glyndon Ave - FC | 17GLYN-0016 | 2026-03-12 | Approved on 3-13 | 2026-03-13 21:37 | 1 | 2025-10-30 | 2026-03-13 |  | 0% | 2175 | 2936.25 | 761.25
Rachel Shepheard | 17 Glyndon Ave - FC | 17GLYN-0008 | 2026-02-20 | Approved on 3-13 | 2026-03-13 21:37 | 1 | 2025-10-30 | 2026-03-13 |  | 0% | 685 | 924.75 | 239.75
Rachel Shepheard | 17 Glyndon Ave - FC | 17GLYN-0014 | 2026-03-05 | Approved on 3-6 | 2026-03-06 09:41 | 2 | 2025-10-30 | 2026-03-06 | 2026-03-08 | 0% | 1375 | 1925 | 550
Mick Hall | 11-15 Station Street, Diamond Creek - FC | 11STA-0016 | 2026-02-12 | Approved on 3-2 | 2026-03-02 09:01 | 1 | 2025-10-31 | 2026-03-04 |  | 0% | 434.5 | 620.71 | 186.21
Serene Ho | 30 Connolly Ave, Coburg - FC | 30CON-0003 | 2026-02-26 | Approved on 2-27 | 2026-02-27 17:02 | 0 | 2025-12-05 | 2026-02-27 |  | 100% | 252 | 387.69 | 135.69
Rachel Shepheard | 17 Glyndon Ave - FC | 17GLYN-0011 | 2026-02-24 | Approved on 2-26 | 2026-02-26 20:31 | 1 | 2025-10-30 | 2026-02-26 |  | 0% | -555 | -555 | 0
Serene Ho | 30 Connolly Ave, Coburg - FC | 30CON-0004 | 2026-02-26 | Approved on 2-26 | 2026-02-26 16:51 | 5 | 2025-12-05 | 2026-03-01 |  | 100% | 500 | 714.29 | 214.29
Sandra Wing | 29 River Gum Close, Diamond Creek FC | 29RIV-0008 | 2026-02-19 | Approved on 2-26 | 2026-02-26 15:37 | 1 | 2025-12-11 | 2026-02-26 |  | 100% | 698.85 | 1164.75 | 465.9
Sandra Wing | 29 River Gum Close, Diamond Creek FC | 29RIV-0011 | 2026-02-19 | Approved on 2-26 | 2026-02-26 15:33 | 2 | 2025-12-11 | 2026-03-25 |  | 100% | 600 | 857.14 | 257.14
Sandra Wing | 29 River Gum Close, Diamond Creek FC | 29RIV-0010 | 2026-02-19 | Approved on 2-26 | 2026-02-26 15:33 | 3 | 2025-12-11 | 2026-03-25 |  | 100% | 1930 | 2757.2 | 827.2
Mick Hall | 11-15 Station Street, Diamond Creek - FC | 11STA-0015 | 2026-02-12 | Approved manually on 2-26 by Matt Reid | 2026-02-26 10:15 | 1 | 2025-10-31 | 2026-02-26 |  | 0% | 638 | 911.43 | 273.43
Mick Hall | 11-15 Station Street, Diamond Creek - FC | 11STA-0014 | 2026-02-12 | Approved on 2-26 | 2026-02-26 08:44 | 1 | 2025-10-31 | 2026-03-12 |  | 0% | 800 | 1040 | 240
Mick Hall | 11-15 Station Street, Diamond Creek - FC | 11STA-0013 | 2026-02-12 | Approved on 2-26 | 2026-02-26 08:43 | 1 | 2025-10-31 | 2026-02-26 |  | 0% | 500 | 650 | 150
Mick Hall | 11-15 Station Street, Diamond Creek - FC | 11STA-0010 | 2026-02-06 | Approved on 2-26 | 2026-02-26 08:43 | 2 | 2025-10-31 | 2026-03-12 |  | 0% | 3307.75 | 4454.88 | 1147.13
Sandra Wing | 29 River Gum Close, Diamond Creek FC | 29RIV-0003 | 2026-02-18 | Approved on 2-25 | 2026-02-25 13:30 | 1 | 2025-12-11 | 2026-02-25 |  | 100% | 1692.35 | 2286.96 | 594.61
Sandra Wing | 29 River Gum Close, Diamond Creek FC | 29RIV-0001 | 2026-02-17 | Approved on 2-25 | 2026-02-25 13:25 | 5 | 2025-12-11 | 2026-03-25 |  | 100% | 22143 | 31243.11 | 9100.11
Suzi & Chris Harris | 37 Robinson St Moonee Ponds - FC | 37ROB-0025 | 2026-02-20 | Approved on 2-24 | 2026-02-24 18:47 | 1 | 2025-07-30 | 2026-02-24 |  | 100% | 2343 | 3457.3 | 1114.3
Sandra Wing | 29 River Gum Close, Diamond Creek FC | 29RIV-0004 | 2026-02-18 | Approved on 2-23 | 2026-02-23 09:05 | 1 | 2025-12-11 | 2026-02-23 | 2026-02-25 | 100% | 1145.8 | 1569.59 | 423.79
Rachel Shepheard | 17 Glyndon Ave - FC | 17GLYN-0010 | 2026-02-20 | Approved on 2-20 | 2026-02-20 14:44 | 1 | 2025-10-30 | 2026-02-20 |  | 0% | 900 | 1215 | 315
Sandra Wing | 29 River Gum Close, Diamond Creek FC | 29RIV-0006 | 2026-02-18 | Approved on 2-20 | 2026-02-20 08:13 | 1 | 2025-12-11 | 2026-02-20 |  | 100% | -2875 | -2875 | 0
Sandra Wing | 29 River Gum Close, Diamond Creek FC | 29RIV-0005 | 2026-02-18 | Approved on 2-20 | 2026-02-20 08:12 | 3 | 2025-12-11 | 2026-02-20 |  | 100% | 5947.11 | 8376.21 | 2429.1
Suzi & Chris Harris | 37 Robinson St Moonee Ponds - FC | 37ROB-0023 | 2026-02-19 | Approved on 2-19 | 2026-02-19 21:55 | 1 | 2025-06-25 | 2026-02-19 |  | 100% | 342 | 342 | 0
Suzi & Chris Harris | 37 Robinson St Moonee Ponds - FC | 37ROB-0022 | 2026-02-17 | Approved on 2-18 | 2026-02-18 07:36 | 1 | 2025-06-25 | 2026-02-18 |  | 100% | -665.36 | -2025.93 | -1360.57
Mick Hall | 11-15 Station Street, Diamond Creek - FC | 11STA-0012 | 2026-02-12 | Approved on 2-12 | 2026-02-12 13:10 | 1 | 2025-10-31 | 2026-02-13 |  | 0% | 0 | 0 | 0
Mick Hall | 11-15 Station Street, Diamond Creek - FC | 11STA-0011 | 2026-02-09 | Approved on 2-11 | 2026-02-11 07:57 | 2 | 2025-10-31 | 2026-02-12 |  | 0% | 8223.42 | 11747.74 | 3524.32
Mick Hall | 11-15 Station Street, Diamond Creek - FC | 11STA-0009 | 2026-01-21 | Approved on 2-11 | 2026-02-11 07:57 | 1 | 2025-10-31 | 2026-02-11 |  | 0% | 6121.28 | 8324.94 | 2203.66
Rachel Shepheard | 17 Glyndon Ave - FC | 17GLYN-0006 | 2026-02-09 | Approved on 2-10 | 2026-02-10 21:00 | 1 | 2025-10-30 | 2026-02-10 |  | 0% | 7050 | 9517.5 | 2467.5
Rachel Shepheard | 17 Glyndon Ave - FC | 17GLYN-0007 | 2026-02-09 | Approved on 2-10 | 2026-02-10 20:59 | 1 | 2025-10-30 | 2026-02-10 |  | 0% | 4894 | 6606.9 | 1712.9
Rachel Shepheard | 17 Glyndon Ave - FC | 17GLYN-0005 | 2026-02-09 | Approved on 2-10 | 2026-02-10 20:59 | 3 | 2025-10-30 | 2026-02-10 |  | 0% | 16950 | 22882.5 | 5932.5
Suzi & Chris Harris | 37 Robinson St Moonee Ponds - FC | 37ROB-0020 | 2026-02-06 | Approved on 2-8 | 2026-02-08 20:50 | 2 | 2025-06-25 | 2026-02-08 |  | 100% | 858 | 1201.2 | 343.2
Suzi & Chris Harris | 37 Robinson St Moonee Ponds - FC | 37ROB-0017 | 2026-01-27 | Approved on 2-5 | 2026-02-05 22:03 | 4 | 2025-06-25 | 2026-02-05 |  | 100% | 1427 | 2058 | 631
Suzi & Chris Harris | 37 Robinson St Moonee Ponds - FC | 37ROB-0019 | 2026-02-03 | Approved on 2-5 | 2026-02-05 06:47 | 1 | 2025-06-25 | 2026-02-05 |  | 100% | 528 | 712.8 | 184.8
Serene Ho | 30 Connolly Ave, Coburg - FC | 30CON-0002 | 2026-01-29 | Approved on 1-29 | 2026-01-29 19:04 | 4 | 2025-12-08 | 2026-01-29 | 2026-01-30 | 100% | 2200 | 2904 | 704
Mick Hall | 11-15 Station Street, Diamond Creek - FC | 11STA-0007 | 2026-01-07 | Approved on 1-29 | 2026-01-29 06:53 | 1 | 2025-10-31 | 2026-01-29 |  | 0% | 2433.84 | 3407.38 | 973.54
Mick Hall | 11-15 Station Street, Diamond Creek - FC | 11STA-0008 | 2026-01-07 | Approved on 1-29 | 2026-01-29 06:52 | 1 | 2025-10-31 | 2026-01-30 | 2026-02-03 | 0% | 3850.75 | 5198.51 | 1347.76
Suzi & Chris Harris | 37 Robinson St Moonee Ponds - FC | 37ROB-0015 | 2026-01-15 | Approved on 1-27 | 2026-01-27 19:58 | 4 | 2025-06-25 | 2026-01-27 | 2026-01-30 | 100% | 4208 | 5680.8 | 1472.8
Rachel Shepheard | 17 Glyndon Ave - FC | 17GLYN-0003 | 2026-01-20 | Approved on 1-22 | 2026-01-22 12:54 | 1 | 2025-10-30 | 2026-01-22 | 2026-01-23 | 0% | 5174 | 7048.3 | 1874.3
Suzi & Chris Harris | 37 Robinson St Moonee Ponds - FC | 37ROB-0016 | 2026-01-21 | Approved on 1-21 | 2026-01-21 22:04 | 2 | 2025-06-25 | 2026-01-21 | 2026-01-23 | 0% | 0 | 0 | 0
Suzi & Chris Harris | 37 Robinson St Moonee Ponds - FC | 37ROB-0013 | 2026-01-14 | Approved on 1-15 | 2026-01-15 14:40 | 3 | 2025-06-25 | 2026-01-15 | 2026-01-16 | 100% | 880 | 1188 | 308
Suzi & Chris Harris | 37 Robinson St Moonee Ponds - FC | 37ROB-0014 | 2026-01-14 | Approved on 1-15 | 2026-01-15 14:40 | 1 | 2025-06-25 | 2026-01-15 | 2026-01-19 | 0% | 0 | 0 | 0
Mick Hall | 11-15 Station Street, Diamond Creek - FC | 11STA-0005 | 2025-12-06 | Approved on 1-13 | 2026-01-13 18:57 | 1 | 2025-10-31 | 2026-01-29 |  | 0% | 1793.74 | 2511.24 | 717.5
Suzi & Chris Harris | 37 Robinson St Moonee Ponds - FC | 37ROB-0007 | 2025-10-14 | Approved on 1-1 | 2026-01-01 20:23 | 1 | 2025-06-25 | 2026-01-01 |  | 100% | 275 | 440 | 165
Rachel Shepheard | 17 Glyndon Ave - FC | 17GLYN-0002 | 2025-12-23 | Approved on 23-12-2025 | 2025-12-23 10:40 | 1 | 2025-10-30 | 2025-12-23 |  | 0% | 5544 | 6930 | 1386
Suzi & Chris Harris | 37 Robinson St Moonee Ponds - FC | 37ROB-0009 | 2025-10-29 | Approved on 16-12-2025 | 2025-12-16 22:22 | 3 | 2025-06-25 | 2025-12-16 |  | 100% | 1825 | 4322.5 | 2497.5
Jeremy & Anna Beaumont | 26 Mooltan St - Sewer | 26-MOOLTAN-0001 | 2025-12-14 | Approved on 15-12-2025 | 2025-12-15 12:36 | 1 | 2025-12-14 | 2025-12-15 |  | 0% | 460 | 586.25 | 126.25
Martin & Lois Kesselring | 5 Woodhill Close, Research FC | 5WOODFC-0023 | 2025-10-06 | Approved manually on 15-12-2025 by Greg Paull | 2025-12-15 11:28 | 0 | 2025-05-20 | 2025-10-06 | 2025-10-10 | 100% | -2041.8 | -2654.34 | -612.54
Alanna Vivian and Michael Juttner | 73 Somers Ave, Macleod FC | 73SOM-0017 | 2025-12-14 | Approved on 15-12-2025 | 2025-12-15 11:16 | 1 | 2025-04-21 | 2025-12-15 | 2025-12-16 | 0% | 2068 | 2398.88 | 330.88
Alanna Vivian and Michael Juttner | 73 Somers Ave, Macleod FC | 73SOM-0018 | 2025-12-14 | Approved on 15-12-2025 | 2025-12-15 10:59 | 1 | 2025-04-21 | 2025-12-15 | 2025-12-16 | 0% | 264 | 356.4 | 92.4
Michael Strachan | 3 Uvadale Grove, Kew | 3UVADALE-0003 | 2025-11-10 | Approved manually on 14-12-2025 by Clive Webster | 2025-12-14 11:08 | 1 | 2025-08-17 |  |  | 0% | 1688.37 | 2363.72 | 675.35
Suzi & Chris Harris | 37 Robinson St Moonee Ponds - FC | 37ROB-0012 | 2025-12-12 | Approved on 12-12-2025 | 2025-12-12 13:04 | 1 | 2025-06-25 | 2025-12-12 |  | 100% | 438.3 | 591.71 | 153.41
Michael Strachan | 3 Uvadale Grove, Kew | 3UVADALE-0001 | 2025-11-07 | Approved manually on 12-12-2025 by Clive Webster | 2025-12-12 11:40 | 1 | 2025-08-17 | 2025-11-26 |  | 0% | 1130.96 | 1526.8 | 395.84
Rachel Shepheard | 17 Glyndon Ave - FC | 17GLYN-0001 | 2025-12-09 | Approved on 11-12-2025 | 2025-12-11 14:15 | 1 | 2025-10-30 | 2025-12-11 |  | 0% | -95.18 | -95.18 | 0
Mick Hall | 11-15 Station Street, Diamond Creek - FC | 11STA-0002 | 2025-11-12 | Approved manually on 5-12-2025 by Greg Paull | 2025-12-05 07:19 | 1 | 2025-10-31 | 2025-12-02 | 2025-12-07 | 0% | 0 | 0 | 0
Mick Hall | 11-15 Station Street, Diamond Creek - FC | 11STA-0003 | 2025-11-12 | Approved manually on 5-12-2025 by Greg Paull | 2025-12-05 07:19 | 1 | 2025-10-31 | 2025-12-05 | 2025-12-07 | 0% | 0 | 0 | 0
Stefano Scalzo | 89 Glen Park Road, Eltham North FC | 89GP-0045 | 2025-11-27 | Approved on 4-12-2025 | 2025-12-04 21:52 | 1 | 2025-04-08 | 2025-12-04 |  | 100% | 1280 | 1740.8 | 460.8
Stefano Scalzo | 89 Glen Park Road, Eltham North FC | 89GP-0046 | 2025-11-28 | Approved on 4-12-2025 | 2025-12-04 21:52 | 1 | 2025-04-08 | 2025-12-04 |  | 100% | 880 | 1232 | 352
Martin & Lois Kesselring | 5 Woodhill Close, Research FC | 5WOODFC-0024 | 2025-11-28 | Approved manually on 3-12-2025 by Matt Reid | 2025-12-03 12:17 | 1 | 2025-05-20 | 2025-12-03 |  | 100% | 1650 | 2194.5 | 544.5
Alanna Vivian and Michael Juttner | 73 Somers Ave, Macleod FC | 73SOM-0016 | 2025-11-28 | Approved on 2-12-2025 | 2025-12-02 21:33 | 1 | 2025-04-21 | 2025-12-15 |  | 0% | 1450 | 2175 | 725
Mick Hall | 11-15 Station Street, Diamond Creek - FC | 11STA-0001 | 2025-11-12 | Approved manually on 2-12-2025 by Greg Paull | 2025-12-02 12:37 | 2 | 2025-10-31 | 2025-12-02 | 2025-12-03 | 0% | 1298 | 1817.2 | 519.2
Stefano Scalzo | 89 Glen Park Road, Eltham North FC | 89GP-0038 | 2025-10-28 | Approved manually on 1-12-2025 by Greg Paull | 2025-12-01 16:33 | 2 | 2025-04-08 |  | 2025-11-21 | 100% | 2254 | 2760 | 506
Suzi & Chris Harris | 37 Robinson St Moonee Ponds - FC | 37ROB-0010 | 2025-11-12 | Approved on 26-11-2025 | 2025-11-26 22:37 | 5 | 2025-06-25 | 2025-11-26 |  | 100% | 11395 | 17885.5 | 6490.5
Alanna Vivian and Michael Juttner | 73 Somers Ave, Macleod FC | 73SOM-0013 | 2025-10-10 | Approved manually on 21-11-2025 by Greg Paull | 2025-11-21 13:57 | 0 | 2025-04-21 | 2025-10-14 |  | 0% | -144.9 | -144.9 | 0
Alanna Vivian and Michael Juttner | 73 Somers Ave, Macleod FC | 73SOM-0014 | 2025-10-10 | Approved manually on 21-11-2025 by Greg Paull | 2025-11-21 13:57 | 0 | 2025-04-21 | 2025-10-14 |  | 0% | -1139.03 | -1139.03 | 0
Alanna Vivian and Michael Juttner | 73 Somers Ave, Macleod FC | 73SOM-0012 | 2025-10-10 | Approved manually on 21-11-2025 by Greg Paull | 2025-11-21 13:56 | 0 | 2025-04-21 | 2025-10-14 |  | 0% | 2659 | 3057.95 | 398.95
Alanna Vivian and Michael Juttner | 73 Somers Ave, Macleod FC | 73SOM-0011 | 2025-09-23 | Approved manually on 21-11-2025 by Greg Paull | 2025-11-21 13:56 | 0 | 2025-04-21 | 2025-09-29 |  | 0% | 375 | 525 | 150
Alanna Vivian and Michael Juttner | 73 Somers Ave, Macleod FC | 73SOM-0015 | 2025-11-17 | Approved manually on 21-11-2025 by Matt Reid | 2025-11-21 13:44 | 1 | 2025-04-21 | 2025-11-18 | 2025-11-21 | 0% | 149.6 | 219.6 | 70
Suzi & Chris Harris | 37 Robinson St Moonee Ponds - FC | 37ROB-0011 | 2025-11-20 | Approved on 20-11-2025 | 2025-11-20 17:01 | 1 | 2025-06-25 | 2025-11-26 |  | 100% | 1155.04 | 1605.04 | 450
Stefano Scalzo | 89 Glen Park Road, Eltham North FC | 89GP-0044 | 2025-11-13 | Approved on 17-11-2025 | 2025-11-17 12:35 | 1 | 2025-04-08 | 2025-11-17 | 2025-11-17 | 100% | 2607 | 3166.05 | 559.05
Stefano Scalzo | 89 Glen Park Road, Eltham North FC | 89GP-0031 | 2025-09-18 | Approved on 17-11-2025 | 2025-11-17 12:34 | 12 | 2025-04-08 | 2025-11-17 | 2025-11-17 | 100% | 14352 | 21180.15 | 6828.15
Martin & Lois Kesselring | 5 Woodhill Close, Research FC | 5WOODFC-0008 | 2025-08-29 | Approved manually on 17-11-2025 by Greg Paull | 2025-11-17 09:22 | 1 | 2025-05-05 | 2025-09-02 | 2025-09-12 | 100% | 2719.73 | 3671.64 | 951.91
Michael Strachan | 3 Uvadale Grove, Kew | 3UVADALE-0002 | 2025-11-10 | Approved manually on 11-11-2025 by Clive Webster | 2025-11-11 11:15 | 5 | 2025-08-17 | 2025-11-10 |  | 0% | 1987.5 | 2662.5 | 675
Suzi & Chris Harris | 37 Robinson St Moonee Ponds - FC | 37ROB-0008 | 2025-10-16 | Approved on 16-10-2025 | 2025-10-16 15:52 | 10 | 2025-06-25 | 2025-10-16 | 2025-10-17 | 100% | 7270 | 9814.5 | 2544.5
Stefano Scalzo | 89 Glen Park Road, Eltham North FC | 89GP-0036 | 2025-10-07 | Approved on 8-10-2025 | 2025-10-08 07:28 | 1 | 2025-04-08 | 2025-10-08 | 2025-10-09 | 100% | 155 | 217 | 62
Stefano Scalzo | 89 Glen Park Road, Eltham North FC | 89GP-0033 | 2025-10-03 | Approved on 8-10-2025 | 2025-10-08 07:28 | 1 | 2025-04-08 | 2025-10-08 | 2025-10-10 | 100% | 341.5 | 464.44 | 122.94
Stefano Scalzo | 89 Glen Park Road, Eltham North FC | 89GP-0029 | 2025-09-15 | Approved manually on 7-10-2025 by Matt Reid | 2025-10-07 17:02 | 1 | 2025-04-08 | 2025-10-02 | 2025-10-10 | 100% | 1294.98 | 1755.67 | 460.69
Stefano Scalzo | 89 Glen Park Road, Eltham North FC | 89GP-0032 | 2025-09-22 | Approved manually on 6-10-2025 by Greg Paull | 2025-10-06 11:57 | 5 | 2025-04-08 | 2025-10-02 | 2025-10-03 | 100% | 2221.64 | 2871.5 | 649.86
Stefano Scalzo | 89 Glen Park Road, Eltham North FC | 89GP-0030 | 2025-09-18 | Approved manually on 2-10-2025 by Matt Reid | 2025-10-02 08:50 | 10 | 2025-04-08 | 2025-10-01 | 2025-10-03 | 100% | 5631 | 6191 | 560
Martin & Lois Kesselring | 5 Woodhill Close, Research FC | 5WOODFC-0021 | 2025-09-29 | Approved manually on 30-09-2025 by Clive Webster | 2025-09-30 15:06 | 2 | 2025-05-20 | 2025-09-30 | 2025-10-01 | 100% | 866.8 | 1213.52 | 346.72
Martin & Lois Kesselring | 5 Woodhill Close, Research FC | 5WOODFC-0019 | 2025-09-23 | Approved manually on 30-09-2025 by Matt Reid | 2025-09-30 14:20 | 5 | 2025-05-20 | 2025-09-30 |  | 100% | 880 | 1320 | 440
Alanna Vivian and Michael Juttner | 73 Somers Ave, Macleod FC | 73SOM-0010 | 2025-09-17 | Approved manually on 23-09-2025 by Greg Paull | 2025-09-23 16:49 | 0 | 2025-04-21 | 2025-09-19 |  | 0% | 2145 | 2788.5 | 643.5
Suzi & Chris Harris | 37 Robinson St Moonee Ponds - FC | 37ROB-0005 | 2025-09-17 | Approved on 19-09-2025 | 2025-09-19 15:58 | 4 | 2025-06-25 | 2026-01-13 | 2025-09-20 | 100% | 6214 | 8388.9 | 2174.9
Suzi & Chris Harris | 37 Robinson St Moonee Ponds - FC | 37ROB-0006 | 2025-09-19 | Approved on 19-09-2025 | 2025-09-19 14:37 | 2 | 2025-06-25 | 2025-09-19 |  | 100% | 2339 | 3428.35 | 1089.35
Alanna Vivian and Michael Juttner | 73 Somers Ave, Macleod FC | 73SOM-0008 | 2025-09-11 | Approved manually on 18-09-2025 by Greg Paull | 2025-09-18 16:00 | 1 | 2025-04-08 | 2025-09-15 | 2025-09-17 | 0% | 1574 | 2093.42 | 519.42
Suzi & Chris Harris | 37 Robinson St Moonee Ponds - FC | 37ROB-0004 | 2025-09-17 | Approved on 18-09-2025 | 2025-09-18 11:33 | 3 | 2025-06-25 | 2026-01-13 | 2025-09-19 | 100% | 4067 | 5490.45 | 1423.45
Stefano Scalzo | 89 Glen Park Road, Eltham North FC | 89GP-0028 | 2025-09-09 | Approved on 11-09-2025 | 2025-09-11 07:12 | 1 | 2025-04-08 | 2025-09-11 | 2025-09-13 | 0% | 0 | 0 | 0
Stefano Scalzo | 89 Glen Park Road, Eltham North FC | 89GP-0025 | 2025-09-08 | Approved on 11-09-2025 | 2025-09-11 07:12 | 1 | 2025-04-08 | 2025-09-11 |  | 100% | 244.2 | 285.62 | 41.42
Stefano Scalzo | 89 Glen Park Road, Eltham North FC | 89GP-0026 | 2025-09-08 | Approved on 11-09-2025 | 2025-09-11 07:11 | 1 | 2025-04-08 | 2025-09-11 |  | 100% | 164.93 | 198.42 | 33.49
Stefano Scalzo | 89 Glen Park Road, Eltham North FC | 89GP-0024 | 2025-09-08 | Approved on 11-09-2025 | 2025-09-11 07:11 | 1 | 2025-04-08 | 2025-09-11 | 2025-09-11 | 100% | 1033.5 | 1136.85 | 103.35
Martin & Lois Kesselring | 5 Woodhill Close, Research FC | 5WOODFC-0018 | 2025-09-10 | Approved manually on 10-09-2025 by Greg Paull | 2025-09-10 16:54 | 0 | 2025-05-20 |  |  | 100% | -749.06 | -749.06 | 0
Stefano Scalzo | 89 Glen Park Road, Eltham North FC | 89GP-0021 | 2025-08-18 | Approved on 10-09-2025 | 2025-09-10 07:59 | 1 | 2025-04-08 | 2025-09-10 |  | 0% | 0 | 0 | 0
Stefano Scalzo | 89 Glen Park Road, Eltham North FC | 89GP-0020 | 2025-08-18 | Approved on 10-09-2025 | 2025-09-10 07:58 | 1 | 2025-04-08 | 2025-09-10 |  | 0% | 0 | 0 | 0
Stefano Scalzo | 89 Glen Park Road, Eltham North FC | 89GP-0027 | 2025-09-09 | Approved on 9-09-2025 | 2025-09-09 07:09 | 1 | 2025-04-08 | 2025-09-09 |  | 100% | 1132.56 | 1506.3 | 373.74
Stefano Scalzo | 89 Glen Park Road, Eltham North FC | 89GP-0023 | 2025-09-02 | Approved on 9-09-2025 | 2025-09-09 07:06 | 1 | 2025-04-08 | 2025-09-09 | 2025-09-13 | 0% | 1870 | 2337.5 | 467.5
Martin & Lois Kesselring | 5 Woodhill Close, Research FC | 5WOODFC-0015 | 2025-09-05 | Approved on 7-09-2025 | 2025-09-07 09:50 | 1 | 2025-05-20 | 2025-09-07 | 2025-09-07 | 0% | 0 | 0 | 0
Suzi & Chris Harris | 37 Robinson St Moonee Ponds - FC | 37ROB-0003 | 2025-09-03 | Approved on 3-09-2025 | 2025-09-03 19:58 | 4 | 2025-06-25 | 2025-09-03 |  | 100% | 673 | 1119 | 446
Martin & Lois Kesselring | 5 Woodhill Close, Research FC | 5WOODFC-0011 | 2025-09-01 | Approved on 2-09-2025 | 2025-09-02 09:48 | 1 | 2025-05-05 | 2025-09-02 | 2025-09-12 | 100% | 293 | 366.25 | 73.25
Martin & Lois Kesselring | 5 Woodhill Close, Research FC | 5WOODFC-0010 | 2025-08-29 | Approved on 2-09-2025 | 2025-09-02 09:48 | 1 | 2025-05-05 | 2025-09-02 | 2025-09-06 | 100% | 8230.48 | 10699.62 | 2469.14
Martin & Lois Kesselring | 5 Woodhill Close, Research FC | 5WOODFC-0006 | 2025-08-29 | Approved on 2-09-2025 | 2025-09-02 09:46 | 1 | 2025-05-20 | 2025-09-02 | 2025-09-13 | 100% | 420 | 554.4 | 134.4
Stefano Scalzo | 89 Glen Park Road, Eltham North FC | 89GP-0019 | 2025-08-13 | Approved on 28-08-2025 | 2025-08-28 10:17 | 0 | 2025-04-08 | 2025-08-28 |  | 100% | 385 | 450 | 65
Stefano Scalzo | 89 Glen Park Road, Eltham North FC | 89GP-0022 | 2025-08-27 | Approved on 28-08-2025 | 2025-08-28 10:17 | 2 | 2025-04-08 | 2025-08-28 |  | 100% | 3355 | 4631 | 1276
David Chuter | 22 Longstaff St - Boundary Wall - FC | 22LONG-WALL-0002 | 2025-08-19 | Approved on 26-08-2025 | 2025-08-26 21:35 | 1 | 2025-07-08 | 2025-08-26 |  | 0% | -740 | -740 | 0
Suzi & Chris Harris | 37 Robinson St Moonee Ponds - FC | 37ROB-0002 | 2025-08-21 | Approved on 21-08-2025 | 2025-08-21 18:40 | 1 | 2025-06-25 | 2025-08-21 |  | 100% | 247.5 | 329.99 | 82.49
Alanna Vivian and Michael Juttner | 73 Somers Ave, Macleod FC | 73SOM-0007 | 2025-08-15 | Approved manually on 20-08-2025 by Greg Paull | 2025-08-20 11:37 | 0 | 2025-04-20 | 2025-08-18 |  | 0% | -300 | 145 | 445
Alanna Vivian and Michael Juttner | 73 Somers Ave, Macleod FC | 73SOM-0006 | 2025-07-31 | Approved manually on 15-08-2025 by Greg Paull | 2025-08-15 16:03 | 4 | 2025-04-20 | 2025-08-01 |  | 0% | 3510 | 5270 | 1760
Alanna Vivian and Michael Juttner | 73 Somers Ave, Macleod FC | 73SOM-0004 | 2025-06-17 | Approved manually on 15-08-2025 by Greg Paull | 2025-08-15 16:01 | 1 | 2025-04-21 | 2025-08-05 |  | 0% | 3050 | 4225 | 1175
Suzi & Chris Harris | 37 Robinson St Moonee Ponds - FC | 37ROB-0001 | 2025-07-28 | Approved on 6-08-2025 | 2025-08-06 21:53 | 5 | 2025-06-25 | 2026-03-01 | 2025-08-11 | 100% | 3724.5 | 4965.88 | 1241.38
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0064 | 2025-08-04 | Approved manually on 4-08-2025 by Clive Webster | 2025-08-04 11:55 | 1 | 2025-08-04 |  |  | 0% | 223.49 | 257.01 | 33.52
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0063 | 2025-08-04 | Approved manually on 4-08-2025 by Clive Webster | 2025-08-04 11:41 | 1 | 2025-08-04 |  |  | 0% | 11013.96 | 13524.81 | 2510.85
Stefano Scalzo | 89 Glen Park Road, Eltham North FC | 89GP-0018 | 2025-07-29 | Approved on 1-08-2025 | 2025-08-01 06:47 | 1 | 2025-04-08 | 2025-08-01 | 2025-08-08 | 100% | 3450 | 4732.5 | 1282.5
Stefano Scalzo | 89 Glen Park Road, Eltham North FC | 89GP-0017 | 2025-07-18 | Approved on 1-08-2025 | 2025-08-01 06:47 | 1 | 2025-04-08 | 2025-08-01 | 2025-08-08 | 100% | 393 | 491.25 | 98.25
Stefano Scalzo | 89 Glen Park Road, Eltham North FC | 89GP-0016 | 2025-07-18 | Approved on 1-08-2025 | 2025-08-01 06:46 | 1 | 2025-04-08 | 2025-08-01 | 2025-08-08 | 100% | 341 | 446 | 105
Alanna Vivian and Michael Juttner | 73 Somers Ave, Macleod FC | 73SOM-0005 | 2025-06-17 | Approved manually on 31-07-2025 by Greg Paull | 2025-07-31 10:46 | 0 | 2025-04-21 |  |  | 0% | 880 | 880 | 0
David Chuter | 22 Longstaff St - Boundary Wall - FC | 22LONG-WALL-0001 | 2025-07-24 | Approved on 28-07-2025 | 2025-07-28 07:24 | 1 | 2025-07-08 | 2025-07-28 |  | 0% | 3490 | 4676.6 | 1186.6
Martin & Lois Kesselring | 5 Woodhill Close, Research FC | 5WOODFC-0004 | 2025-07-18 | Approved on 18-07-2025 | 2025-07-18 18:41 | 1 | 2025-05-20 | 2025-07-18 | 2025-07-20 | 0% | 0 | 0 | 0
Martin & Lois Kesselring | 5 Woodhill Close, Research FC | 5WOODFC-0003 | 2025-07-18 | Approved on 18-07-2025 | 2025-07-18 18:40 | 1 | 2025-05-20 | 2025-07-18 | 2025-07-23 | 0% | 0 | 0 | 0
Martin & Lois Kesselring | 5 Woodhill Close, Research FC | 5WOODFC-0005 | 2025-07-18 | Approved on 18-07-2025 | 2025-07-18 18:40 | 1 | 2025-05-20 | 2025-07-18 | 2025-07-20 | 0% | 0 | 0 | 0
Martin & Lois Kesselring | 5 Woodhill Close, Research FC | 5WOODFC-0002 | 2025-07-09 | Approved on 17-07-2025 | 2025-07-17 09:00 | 3 | 2025-05-20 | 2025-07-17 |  | 0% | 0 | 0 | 0
Stefano Scalzo | 89 Glen Park Road, Eltham North FC | 89GP-0008 | 2025-06-17 | Approved on 13-07-2025 | 2025-07-13 14:25 | 1 | 2025-04-08 | 2025-07-13 | 2025-07-15 | 100% | 2240 | 2912 | 672
Stefano Scalzo | 89 Glen Park Road, Eltham North FC | 89GP-0015 | 2025-07-08 | Approved on 13-07-2025 | 2025-07-13 14:24 | 2 | 2025-04-08 | 2025-07-13 | 2025-07-16 | 0% | 860 | 1118 | 258
Martin & Lois Kesselring | 5 Woodhill Close, Research FC | 5WOODFC-0001 | 2025-06-17 | Approved manually on 9-07-2025 by Dale Psaila | 2025-07-09 12:13 | 3 | 2025-05-20 |  |  | 100% | 2200 | 2200 | 0
Stefano Scalzo | 89 Glen Park Road, Eltham North FC | 89GP-0013 | 2025-06-23 | Approved on 23-06-2025 | 2025-06-23 21:21 | 1 | 2025-04-08 | 2025-06-23 | 2025-06-24 | 100% | 948 | 980 | 32
Stefano Scalzo | 89 Glen Park Road, Eltham North FC | 89GP-0014 | 2025-06-23 | Approved on 23-06-2025 | 2025-06-23 21:21 | 1 | 2025-04-08 | 2025-06-23 | 2025-06-24 | 100% | 684.6 | 730 | 45.4
Stefano Scalzo | 89 Glen Park Road, Eltham North FC | 89GP-0012 | 2025-06-23 | Approved on 23-06-2025 | 2025-06-23 21:19 | 0 | 2025-04-08 | 2025-06-23 | 2025-06-27 | 100% | -3095 | -2695 | 400
Stefano Scalzo | 89 Glen Park Road, Eltham North FC | 89GP-0007 | 2025-06-10 | Approved on 19-06-2025 | 2025-06-19 11:09 | 1 | 2025-04-08 | 2025-06-19 |  | 0% | 1155 | 1617 | 462
Stefano Scalzo | 89 Glen Park Road, Eltham North FC | 89GP-0009 | 2025-06-17 | Approved on 19-06-2025 | 2025-06-19 11:07 | 0 | 2025-04-08 | 2025-06-19 |  | 0% | 0 | 0 | 0
Stefano Scalzo | 89 Glen Park Road, Eltham North FC | 89GP-0006 | 2025-05-20 | Approved on 16-06-2025 | 2025-06-16 20:55 | 3 | 2025-04-08 | 2025-06-16 |  | 0% | 10715 | 12954.2 | 2239.2
Alanna Vivian and Michael Juttner | 73 Somers Ave, Macleod FC | 73SOM-0003 | 2025-06-03 | Approved on 13-06-2025 | 2025-06-13 15:17 | 25 | 2025-04-21 | 2025-06-13 | 2025-06-16 | 100% | 1243.87 | 1243.87 | 0
Umut Akcelik | 105 Greythorn Rd - Downstairs Works | 105GREY-0022 | 2025-06-11 | Approved on 11-06-2025 | 2025-06-11 14:26 | 1 | 2025-06-11 | 2025-06-11 |  | 100% | 2870 | 3731 | 861
Alanna Vivian and Michael Juttner | 73 Somers Ave, Macleod FC | 73SOM-0001 | 2025-04-30 | Approved manually on 20-05-2025 by Greg Paull | 2025-05-20 15:17 | 0 | 2025-04-20 |  | 2025-05-05 | 100% | 1100 | 1265 | 165
Stefano Scalzo | 89 Glen Park Road, Eltham North FC | 89GP-0005 | 2025-05-15 | Approved on 16-05-2025 | 2025-05-16 10:52 | 0 | 2025-04-08 | 2025-05-16 | 2025-05-19 | 100% | 660 | 820 | 160
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0041 | 2025-05-09 | Approved manually on 9-05-2025 by Clive Webster | 2025-05-09 15:46 | 1 | 2023-08-15 |  |  | 0% | 2732.81 | 2732.81 | 0
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0062 | 2025-05-09 | Approved manually on 9-05-2025 by Clive Webster | 2025-05-09 15:43 | 1 | 2023-08-15 |  |  | 0% | -1176.45 | -1176.45 | 0
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0061 | 2025-05-09 | Approved manually on 9-05-2025 by Clive Webster | 2025-05-09 15:40 | 1 | 2023-08-15 |  |  | 0% | 163.3 | 163.3 | 0
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0059 | 2025-05-09 | Approved manually on 9-05-2025 by Clive Webster | 2025-05-09 15:38 | 1 | 2023-08-15 |  |  | 0% | -1165.13 | -1165.13 | 0
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0058 | 2025-05-09 | Approved manually on 9-05-2025 by Clive Webster | 2025-05-09 15:37 | 1 | 2023-08-15 |  |  | 0% | 16500.01 | 16500.01 | 0
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0056 | 2025-05-09 | Approved manually on 9-05-2025 by Clive Webster | 2025-05-09 15:33 | 1 | 2023-08-15 |  |  | 0% | 326.6 | 326.6 | 0
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0055 | 2025-02-25 | Approved manually on 9-05-2025 by Clive Webster | 2025-05-09 15:04 | 1 | 2023-08-15 |  |  | 0% | -1957 | -1957 | 0
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0053 | 2024-12-29 | Approved manually on 9-05-2025 by Clive Webster | 2025-05-09 15:00 | 0 | 2023-08-15 |  |  | 0% | -746.35 | -746.35 | 0
Rudy Pilotto | 119 McIlwraith St - FC | 119MCIL-FC-0007 | 2025-05-06 | Approved on 7-05-2025 | 2025-05-07 08:08 | 1 | 2024-08-05 | 2025-05-07 |  | 0% | 11385 | 11385 | 0
Stefano Scalzo | 89 Glen Park Road, Eltham North FC | 89GP-0001 | 2025-05-01 | Approved on 2-05-2025 | 2025-05-02 17:15 | 0 | 2025-04-08 | 2025-05-02 |  | 100% | 925 | 925 | 0
Rudy Pilotto | 119 McIlwraith St - FC | 119MCIL-FC-0005 | 2025-03-20 | Approved on 10-04-2025 | 2025-04-10 11:19 | 1 | 2024-08-05 | 2025-04-10 |  | 0% | 2211 | 2211 | 0
Rudy Pilotto | 119 McIlwraith St - FC | 119MCIL-FC-0006 | 2025-04-08 | Approved on 10-04-2025 | 2025-04-10 11:18 | 1 | 2024-08-05 | 2025-04-10 |  | 0% | 18280 | 18280 | 0
Rudy Pilotto | 119 McIlwraith St - FC | 119MCIL-FC-0004 | 2025-03-06 | Approved on 6-03-2025 | 2025-03-06 08:47 | 1 | 2024-08-05 | 2025-03-06 |  | 0% | 16266.8 | 16266.8 | 0
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0054 | 2024-12-29 | Approved manually on 29-12-2024 by Clive Webster | 2024-12-29 14:24 | 0 | 2023-08-15 |  |  | 0% | 2024.88 | 2328.61 | 303.73
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0050 | 2024-12-29 | Approved manually on 29-12-2024 by Clive Webster | 2024-12-29 14:09 | 0 | 2023-08-15 |  |  | 0% | 4413.4 | 6012.92 | 1599.52
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0052 | 2024-12-29 | Approved manually on 29-12-2024 by Clive Webster | 2024-12-29 13:58 | 0 | 2023-08-15 |  |  | 0% | 1342 | 1543.3 | 201.3
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0051 | 2024-12-29 | Approved manually on 29-12-2024 by Clive Webster | 2024-12-29 13:55 | 0 | 2023-08-15 |  |  | 0% | 1100 | 1265 | 165
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0049 | 2024-12-29 | Approved manually on 29-12-2024 by Clive Webster | 2024-12-29 13:53 | 0 | 2023-08-15 |  |  | 0% | 2904 | 3339.6 | 435.6
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0048 | 2024-12-29 | Approved manually on 29-12-2024 by Clive Webster | 2024-12-29 13:49 | 0 | 2023-08-15 |  |  | 0% | 19848.79 | 22826.11 | 2977.32
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0047 | 2024-08-26 | Approved manually on 27-12-2024 by Clive Webster | 2024-12-27 15:36 | 0 | 2023-08-15 |  |  | 0% | 749.99 | 862.49 | 112.5
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0046 | 2024-12-27 | Approved manually on 27-12-2024 by Clive Webster | 2024-12-27 15:34 | 0 | 2023-08-15 |  |  | 0% | -14691 | -6417.15 | 8273.85
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0045 | 2024-05-29 | Approved manually on 27-12-2024 by Clive Webster | 2024-12-27 15:31 | 0 | 2023-08-15 |  |  | 0% | 2350 | 2702.5 | 352.5
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0044 | 2024-12-27 | Approved manually on 27-12-2024 by Clive Webster | 2024-12-27 15:29 | 0 | 2023-08-15 |  |  | 0% | -1610 | -1610 | 0
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0043 | 2024-12-27 | Approved manually on 27-12-2024 by Clive Webster | 2024-12-27 15:27 | 0 | 2023-08-15 |  |  | 0% | 182.6 | 209.99 | 27.39
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0042 | 2024-07-30 | Approved manually on 27-12-2024 by Clive Webster | 2024-12-27 15:24 | 0 | 2023-08-15 |  |  | 0% | 2416.21 | 13645.47 | 11229.26
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0040 | 2024-12-27 | Approved manually on 27-12-2024 by Clive Webster | 2024-12-27 13:15 | 0 | 2023-08-15 |  |  | 0% | 330 | 379.5 | 49.5
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0039 | 2024-07-30 | Approved manually on 27-12-2024 by Clive Webster | 2024-12-27 13:12 | 0 | 2023-08-15 |  |  | 0% | 33381.96 | 38389.26 | 5007.3
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0036 | 2024-07-30 | Approved manually on 27-12-2024 by Clive Webster | 2024-12-27 13:01 | 0 | 2023-08-15 |  |  | 0% | 3527.06 | 4056.12 | 529.06
Rudy Pilotto | 119 McIlwraith St - FC | 119MCIL-FC-0002 | 2024-12-16 | Approved on 24-12-2024 | 2024-12-24 16:03 | 1 | 2024-08-05 | 2024-12-24 |  | 0% | 5830 | 8328.74 | 2498.74
Rudy Pilotto | 119 McIlwraith St - FC | 119MCIL-FC-0001 | 2024-11-20 | Approved on 22-11-2024 | 2024-11-22 13:22 | 1 | 2024-08-05 | 2024-11-22 |  | 0% | 20735 | 20735 | 0
Umut Akcelik | 105 Greythorn Rd - Downstairs Works | 105GREY-0019 | 2024-08-08 | Approved on 8-08-2024 | 2024-08-08 18:04 | 1 | 2023-09-13 | 2024-08-08 | 2024-08-13 | 100% | 840 | 1054.5 | 214.5
Umut Akcelik | 105 Greythorn Rd - Downstairs Works | 105GREY-0020 | 2024-08-08 | Approved on 8-08-2024 | 2024-08-08 18:02 | 1 | 2023-09-13 | 2024-08-08 | 2024-08-13 | 100% | 130 | 169 | 39
Umut Akcelik | 105 Greythorn Rd - Downstairs Works | 105GREY-0018 | 2024-07-10 | Approved on 10-07-2024 | 2024-07-10 11:00 | 1 | 2023-09-13 | 2024-07-10 | 2024-07-11 | 100% | 259 | 336.7 | 77.7
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0035 | 2024-07-08 | Approved manually on 8-07-2024 by Clive Webster | 2024-07-08 12:47 | 0 | 2023-08-15 |  |  | 0% | 869 | 999.35 | 130.35
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0034 | 2024-07-08 | Approved manually on 8-07-2024 by Clive Webster | 2024-07-08 12:44 | 0 | 2023-08-15 |  |  | 0% | 1870 | 2150.5 | 280.5
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0033 | 2024-07-08 | Approved manually on 8-07-2024 by Clive Webster | 2024-07-08 12:42 | 0 | 2023-08-15 |  |  | 0% | 693 | 796.95 | 103.95
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0028 | 2024-07-08 | Approved manually on 8-07-2024 by Clive Webster | 2024-07-08 12:38 | 0 | 2023-08-15 |  |  | 0% | -17672.47 | -16179.59 | 1492.88
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0029 | 2024-07-08 | Approved manually on 8-07-2024 by Clive Webster | 2024-07-08 12:35 | 0 | 2023-08-15 |  |  | 0% | 1908.5 | 2194.78 | 286.28
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0027 | 2024-07-08 | Approved manually on 8-07-2024 by Clive Webster | 2024-07-08 12:29 | 0 | 2023-08-15 |  |  | 0% | 8296.2 | 9540.64 | 1244.44
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0025 | 2024-07-08 | Approved manually on 8-07-2024 by Clive Webster | 2024-07-08 12:25 | 0 | 2023-08-15 |  |  | 0% | 1274 | 1465.1 | 191.1
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0024 | 2024-07-08 | Approved manually on 8-07-2024 by Clive Webster | 2024-07-08 12:22 | 0 | 2023-08-15 |  |  | 0% | 10000 | 15156.25 | 5156.25
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0023 | 2024-07-08 | Approved manually on 8-07-2024 by Clive Webster | 2024-07-08 12:20 | 0 | 2023-08-15 |  |  | 0% | 4615.7 | 5496.31 | 880.61
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0022 | 2024-07-08 | Approved manually on 8-07-2024 by Clive Webster | 2024-07-08 12:14 | 0 | 2023-08-15 |  |  | 0% | 5972.1 | 6867.92 | 895.82
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0021 | 2024-07-08 | Approved manually on 8-07-2024 by Clive Webster | 2024-07-08 10:58 | 0 | 2023-08-15 |  |  | 0% | 19687.72 | 24911.5 | 5223.78
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0026 | 2024-05-06 | Approved manually on 8-07-2024 by Clive Webster | 2024-07-08 10:47 | 1 | 2024-05-06 |  |  | 0% | 2684.4 | 3300.66 | 616.26
Umut Akcelik | 105 Greythorn Rd - Downstairs Works | 105GREY-0017 | 2024-07-04 | Approved on 4-07-2024 | 2024-07-04 12:44 | 1 | 2023-09-13 | 2024-07-04 | 2024-07-09 | 100% | 675 | 840 | 165
Umut Akcelik | 105 Greythorn Rd - Downstairs Works | 105GREY-0016 | 2024-07-02 | Approved on 3-07-2024 | 2024-07-03 11:12 | 1 | 2023-09-13 | 2024-07-03 |  | 100% | 998 | 1277.44 | 279.44
Umut Akcelik | 105 Greythorn Rd - Downstairs Works | 105GREY-0015 | 2024-06-19 | Approved on 29-06-2024 | 2024-06-29 12:07 | 1 | 2023-09-13 | 2024-06-29 |  | 100% | 5827 | 7485.1 | 1658.1
Umut Akcelik | 105 Greythorn Rd - Downstairs Works | 105GREY-0014 | 2024-06-18 | Approved on 18-06-2024 | 2024-06-18 17:35 | 1 | 2023-09-12 | 2024-06-18 |  | 100% | 5577 | 7138.56 | 1561.56
Umut Akcelik | 105 Greythorn Rd - Downstairs Works | 105GREY-0013 | 2024-06-13 | Approved on 13-06-2024 | 2024-06-13 16:28 | 1 | 2023-09-12 | 2024-06-13 |  | 100% | 2000 | 2488 | 488
Umut Akcelik | 105 Greythorn Rd - Downstairs Works | 105GREY-0011 | 2024-06-03 | Approved on 3-06-2024 | 2024-06-03 07:57 | 1 | 2023-09-12 | 2024-06-03 |  | 100% | 1420 | 1813.1 | 393.1
Umut Akcelik | 105 Greythorn Rd - Downstairs Works | 105GREY-0010 | 2024-05-24 | Approved on 29-05-2024 | 2024-05-29 11:11 | 1 | 2023-09-12 | 2024-05-29 |  | 100% | 1405 | 1789 | 384
Umut Akcelik | 105 Greythorn Rd - Downstairs Works | 105GREY-0007 | 2024-05-07 | Approved on 7-05-2024 | 2024-05-07 18:38 | 0 | 2023-09-12 | 2024-05-07 |  | 100% | 231 | 300.3 | 69.3
Umut Akcelik | 105 Greythorn Rd - Downstairs Works | 105GREY-0006 | 2024-04-17 | Approved on 30-04-2024 | 2024-04-30 11:47 | 1 | 2023-09-12 | 2024-04-30 |  | 90.7% | 30415 | 40226 | 9811
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0014 | 2024-04-26 | Approved manually on 26-04-2024 by Clive Webster | 2024-04-26 09:33 | 2 | 2023-08-15 |  |  | 0% | 95 | 4520.26 | 4425.26
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0019 | 2024-02-09 | Approved manually on 26-04-2024 by Clive Webster | 2024-04-26 09:22 | 1 | 2023-08-15 |  |  | 0% | 4031 | 5873.02 | 1842.02
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0020 | 2024-04-23 | Approved manually on 23-04-2024 by Clive Webster | 2024-04-23 10:46 | 0 | 2023-08-15 |  |  | 0% | 1650 | 1897.5 | 247.5
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0017 | 2024-03-20 | Approved manually on 20-03-2024 by Clive Webster | 2024-03-20 14:35 | 0 | 2023-08-15 |  |  | 0% | -6580 | -6580 | 0
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0013 | 2024-03-20 | Approved manually on 20-03-2024 by Clive Webster | 2024-03-20 14:32 | 2 | 2023-08-15 |  |  | 0% | 6680.56 | 7495.83 | 815.27
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0015 | 2024-02-09 | Approved manually on 20-03-2024 by Clive Webster | 2024-03-20 14:17 | 1 | 2023-08-15 |  |  | 0% | 3609.7 | 4151.16 | 541.46
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0012 | 2024-02-28 | Approved manually on 28-02-2024 by Clive Webster | 2024-02-28 13:27 | 0 | 2023-08-15 |  |  | 0% | 605 | 695.75 | 90.75
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0011 | 2024-02-28 | Approved manually on 28-02-2024 by Clive Webster | 2024-02-28 13:24 | 0 | 2023-08-15 |  |  | 0% | -2005.57 | -2005.57 | 0
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0010 | 2024-01-23 | Approved manually on 28-02-2024 by Clive Webster | 2024-02-28 13:14 | 0 | 2023-08-15 |  |  | 0% | -238.15 | 1709.13 | 1947.28
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0008 | 2024-01-23 | Approved manually on 23-01-2024 by Clive Webster | 2024-01-23 18:46 | 10 | 2023-08-15 |  |  | 0% | -733 | 5366.51 | 6099.51
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0006 | 2024-01-23 | Approved manually on 23-01-2024 by Clive Webster | 2024-01-23 18:46 | 1 | 2023-08-15 |  |  | 0% | 1730.25 | 2283.93 | 553.68
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0007 | 2024-01-23 | Approved manually on 23-01-2024 by Clive Webster | 2024-01-23 18:45 | 10 | 2023-08-15 |  |  | 0% | 2230 | 2820.95 | 590.95
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0003 | 2024-01-23 | Approved manually on 23-01-2024 by Clive Webster | 2024-01-23 18:45 | 30 | 2023-08-15 |  |  | 0% | 0 | 0 | 0
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0002 | 2024-01-23 | Approved manually on 23-01-2024 by Clive Webster | 2024-01-23 18:44 | 0 | 2023-08-15 |  |  | 0% | 479 | 632.28 | 153.28
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0005 | 2024-01-23 | Approved manually on 23-01-2024 by Clive Webster | 2024-01-23 18:42 | 0 | 2023-08-15 |  |  | 0% | -20931.09 | -20117.31 | 813.78
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0004 | 2024-01-23 | Approved manually on 23-01-2024 by Clive Webster | 2024-01-23 18:41 | 5 | 2023-08-15 |  |  | 0% | 8400.15 | 8400.15 | 0
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0001 | 2024-01-23 | Approved manually on 23-01-2024 by Clive Webster | 2024-01-23 18:39 | 0 | 2023-08-15 |  |  | 0% | 572 | 755.04 | 183.04
Umut Akcelik | 105 Greythorn Rd - Downstairs Works | 105GREY-0005 | 2023-11-21 | Approved on 23-11-2023 | 2023-11-23 17:02 | 1 | 2023-09-12 | 2023-11-23 |  | 100% | 345 | 400 | 55
Umut Akcelik | 105 Greythorn Rd - Downstairs Works | 105GREY-0004 | 2023-11-14 | Approved on 14-11-2023 | 2023-11-14 12:40 | 1 | 2023-09-12 | 2023-11-14 |  | 100% | 658.49 | 658.49 | 0
Umut Akcelik | 105 Greythorn Rd - Downstairs Works | 105GREY-0003 | 2023-11-03 | Approved on 3-11-2023 | 2023-11-03 12:24 | 1 | 2023-09-12 | 2023-11-03 | 2023-11-06 | 100% | 635 | 731.25 | 96.25
Umut Akcelik | 105 Greythorn Rd - Downstairs Works | 105GREY-0002 | 2023-10-30 | Approved on 30-10-2023 | 2023-10-30 18:21 | 1 | 2023-09-12 | 2023-10-30 |  | 100% | 265.1 | 344.63 | 79.53
Umut Akcelik | 105 Greythorn Rd - Downstairs Works | 105GREY-0001 | 2023-10-09 | Approved on 9-10-2023 | 2023-10-09 17:29 | 3 | 2023-09-12 | 2023-10-09 |  | 100% | 1965 | 2425 | 460
Umut Akcelik | 105 Greythorn Rd - Downstairs Works | 105GREY-0023 | 2026-04-08 | Sent / Pending | 2026-04-08 17:00 | 1 | 2026-04-08 | 2026-04-08 |  | 0% | 7075 | 9964.8 | 2889.8
Michael Strachan | 3 Uvadale Grove, Kew | 3UVADALE-0004 | 2025-11-19 | Sent / Pending | 2026-01-19 11:38 | 1 | 2025-08-17 | 2026-01-20 |  | 0% | 4565 | 6391 | 1826
Michael Strachan | 3 Uvadale Grove, Kew | 3UVADALE-0005 | 2026-01-16 | Sent / Pending | 2026-01-19 11:37 | 1 | 2025-08-17 | 2026-01-20 |  | 0% | 800 | 1120 | 320
Alanna Vivian and Michael Juttner | 73 Somers Ave, Macleod FC | 73SOM-0020 | 2025-12-16 | Sent / Pending | 2025-12-16 09:03 | 0 | 2025-04-21 | 2025-12-16 |  | 0% | -1320 | -1320 | 0
Stefano Scalzo | 89 Glen Park Road, Eltham North FC | 89GP-0043 | 2025-11-07 | Sent / Pending | 2025-11-12 14:57 | 1 | 2025-04-08 | 2025-11-12 |  | 0% | 14020 | 18061 | 4041
Stefano Scalzo | 89 Glen Park Road, Eltham North FC | 89GP-0042 | 2025-11-07 | Sent / Pending | 2025-11-12 14:56 | 1 | 2025-04-08 | 2026-01-04 |  | 0% | 12820 | 16501 | 3681
Stefano Scalzo | 89 Glen Park Road, Eltham North FC | 89GP-0041 | 2025-11-07 | Sent / Pending | 2025-11-12 14:56 | 1 | 2025-04-08 |  |  | 0% | 13820 | 17801 | 3981
Stefano Scalzo | 89 Glen Park Road, Eltham North FC | 89GP-0040 | 2025-11-07 | Sent / Pending | 2025-11-12 14:56 | 1 | 2025-04-08 | 2026-01-04 |  | 0% | 12540 | 12540 | 0
Stefano Scalzo | 89 Glen Park Road, Eltham North FC | 89GP-0039 | 2025-11-07 | Sent / Pending | 2025-11-12 14:55 | 1 | 2025-04-08 | 2026-01-10 |  | 0% | 10510 | 13498 | 2988
David Chuter | 22 Longstaff St - Boundary Wall - FC | 22LONG-WALL-0003 | 2025-10-02 | Sent / Pending | 2025-10-03 07:21 | 1 | 2025-07-08 | 2025-11-06 |  | 0% | 4358 | 5879.04 | 1521.04
Alanna Vivian and Michael Juttner | 73 Somers Ave, Macleod FC | 73SOM-0019 | 2025-12-15 | Past due | 2025-12-16 08:58 | 1 | 2025-04-21 |  | 2025-12-18 | 0% | 361.58 | 419.43 | 57.85
Stefano Scalzo | 89 Glen Park Road, Eltham North FC | 89GP-0034 | 2025-10-03 | Past due | 2025-10-06 11:55 | 1 | 2025-04-08 | 2025-10-08 | 2025-10-10 | 0% | 76.54 | 107.16 | 30.62
Stefano Scalzo | 89 Glen Park Road, Eltham North FC | 89GP-0037 | 2025-10-07 | Past due | 2025-10-07 16:57 | 1 | 2025-04-08 | 2025-10-08 | 2025-10-09 | 0% | 183.56 | 256.98 | 73.42
Martin & Lois Kesselring | 5 Woodhill Close, Research FC | 5WOODFC-0013 | 2025-09-04 | Past due | 2025-09-15 08:38 | 7 | 2025-05-20 | 2025-09-04 | 2025-09-18 | 0% | 3320 | 4415.6 | 1095.6
Martin & Lois Kesselring | 5 Woodhill Close, Research FC | 5WOODFC-0014 | 2025-09-04 | Past due | 2025-09-15 08:39 | 7 | 2025-05-20 |  | 2025-09-18 | 0% | 2630 | 3497.9 | 867.9
Martin & Lois Kesselring | 5 Woodhill Close, Research FC | 5WOODFC-0017 | 2025-09-10 | Past due | 2025-09-15 08:40 | 7 | 2025-05-20 | 2025-09-11 | 2025-09-18 | 0% | 4535 | 6031.55 | 1496.55
Martin & Lois Kesselring | 5 Woodhill Close, Research FC | 5WOODFC-0016 | 2025-09-07 | Past due | 2025-09-15 08:40 | 7 | 2025-05-20 | 2025-09-09 | 2025-09-18 | 0% | 3690 | 4907.7 | 1217.7
Rachel Shepheard | 17 Glyndon Ave - FC | 17GLYN-0023 | 2026-05-14 | Not sent | 2026-05-14 07:29 | 1 | 2026-05-14 |  |  | 0% | 550 | 550 | 0
Suzi & Chris Harris | 37 Robinson St Moonee Ponds - FC | 37ROB-0029 | 2026-05-11 | Recalled | 2026-05-11 14:59 | 1 | 2026-05-05 | 2026-05-11 |  | 0% | 1628 | 2429.85 | 801.85
Gino Marone | 801 Main Hurstbridge Road FC | 801MN-0010 | 2026-05-07 | Not sent | 2026-05-07 14:21 | 1 | 2026-04-27 |  |  | 0% | -4479.23 | -6121.05 | -1641.82
Gino Marone | 801 Main Hurstbridge Road FC | 801MN-0009 | 2026-05-06 | Not sent | 2026-05-06 13:02 | 1 | 2026-04-23 |  |  | 0% | 0 | 0 | 0
Serene Ho | 30 Connolly Ave, Coburg - FC | 30CON-0008 | 2026-04-30 | Not sent | 2026-04-30 21:53 | 7 | 2025-12-05 |  |  | 0% | 125 | 165 | 40
Michael Strachan | 3 Uvadale Grove, Kew | 3UVADALE-0006 | 2026-04-21 | Not sent | 2026-04-21 17:26 | 5 | 2026-04-21 |  |  | 0% | 46225 | 56476.43 | 10251.43
Mick Hall | 11-15 Station Street, Diamond Creek - FC | 11STA-0018 | 2026-03-30 | Not sent | 2026-03-30 10:01 | 2 | 2025-10-01 |  |  | 0% | 1996.5 | 1996.5 | 0
Rachel Shepheard | 17 Glyndon Ave - FC | 17GLYN-0004 | 2026-01-22 | Not sent | 2026-01-22 11:20 | 5 | 2025-10-30 |  |  | 0% | 0 | 0 | 0
Mick Hall | 11-15 Station Street, Diamond Creek - FC | 11STA-0004 | 2025-12-05 | Not sent | 2025-12-05 07:04 | 1 | 2025-10-31 |  |  | 0% | 1100 | 1485 | 385
Umut Akcelik | 105 Greythorn Rd - Downstairs Works | 105GREY-0021 | 2024-08-12 | Client requested | 2024-08-12 11:14 |  |  |  |  | 0% | 0 | 0 | 0
Umut Akcelik | 105 Greythorn Rd - Downstairs Works | 105GREY-0012 | 2024-06-12 | Client requested | 2024-06-12 18:09 |  |  |  |  | 0% | 0 | 0 | 0
Umut Akcelik | 105 Greythorn Rd - Downstairs Works | 105GREY-0009 | 2024-05-16 | Client requested | 2024-05-16 14:26 |  |  |  |  | 0% | 0 | 0 | 0
Umut Akcelik | 105 Greythorn Rd - Downstairs Works | 105GREY-0008 | 2024-05-14 | Client requested | 2024-05-14 17:41 |  |  |  |  | 0% | 0 | 0 | 0
Serene Ho | 30 Connolly Ave, Coburg - FC | 30CON-0011 | 2026-05-08 | Declined on 5-12 | 2026-05-12 16:57 | 5 | 2025-12-05 | 2026-05-12 |  | 0% | 2940 | 3969 | 1029
Gino Marone | 801 Main Hurstbridge Road FC | 801MN-0006 | 2026-05-02 | Declined on 5-6 | 2026-05-06 17:49 | 2 | 2026-04-23 | 2026-05-06 |  | 0% | 290 | 794.62 | 504.62
Serene Ho | 30 Connolly Ave, Coburg - FC | 30CON-0009 | 2026-05-05 | Declined on 5-6 | 2026-05-06 16:31 | 15 | 2025-12-05 | 2026-05-06 | 2026-05-07 | 0% | 7680 | 10239 | 2559
Tom Moore | 49 Kamarooka Drive Wattle Glen 3096 | 49KAM-0003 | 2026-04-22 | Declined on 4-24 | 2026-04-24 20:15 | 1 | 2026-02-12 | 2026-04-24 |  | 0% | 1790 | 2671.64 | 881.64
Tom Moore | 49 Kamarooka Drive Wattle Glen 3096 | 49KAM-0002 | 2026-04-22 | Declined on 4-24 | 2026-04-24 20:15 | 1 | 2026-02-12 | 2026-04-24 |  | 0% | 2816 | 4332.31 | 1516.31
Suzi & Chris Harris | 37 Robinson St Moonee Ponds - FC | 37ROB-0027 | 2026-04-08 | Declined on 4-8 | 2026-04-08 21:16 | 5 | 2025-06-30 | 2026-04-08 |  | 0% | 2672.31 | 3988.52 | 1316.21
Rachel Shepheard | 17 Glyndon Ave - FC | 17GLYN-0013 | 2026-03-05 | Declined on 3-13 | 2026-03-13 21:38 | 10 | 2025-10-30 | 2026-03-13 |  | 0% | 5850 | 7897.5 | 2047.5
Sandra Wing | 29 River Gum Close, Diamond Creek FC | 29RIV-0012 | 2026-02-23 | Declined on 2-26 | 2026-02-26 15:28 | 1 | 2025-12-11 | 2026-02-26 |  | 0% | 2960 | 4228.57 | 1268.57
Sandra Wing | 29 River Gum Close, Diamond Creek FC | 29RIV-0002 | 2026-02-18 | Declined on 2-26 | 2026-02-26 15:25 | 1 | 2025-12-11 | 2026-02-26 |  | 0% | 1627 | 2198.65 | 571.65
Sandra Wing | 29 River Gum Close, Diamond Creek FC | 29RIV-0007 | 2026-02-18 | Declined on 2-25 | 2026-02-25 13:32 | 2 | 2025-12-11 | 2026-02-25 |  | 0% | 1121 | 1601.43 | 480.43
Suzi & Chris Harris | 37 Robinson St Moonee Ponds - FC | 37ROB-0021 | 2026-02-17 | Declined on 2-18 | 2026-02-18 07:47 | 1 | 2025-06-25 | 2026-02-18 |  | 0% | 1606 | 2328.7 | 722.7
Suzi & Chris Harris | 37 Robinson St Moonee Ponds - FC | 37ROB-0018 | 2026-01-27 | Declined on 1-27 | 2026-01-27 19:43 | 4 | 2025-06-25 | 2026-01-27 | 2026-01-30 | 0% | 3310 | 4468.5 | 1158.5
Serene Ho | 30 Connolly Ave, Coburg - FC | 30CON-0001 | 2026-01-21 | Declined on 1-21 | 2026-01-21 21:40 | 0 | 2025-12-08 | 2026-01-21 | 2026-01-30 | 0% | 3523.78 | 3523.78 | 0
Martin & Lois Kesselring | 5 Woodhill Close, Research FC | 5WOODFC-0022 | 2025-09-29 | Declined on 30-09-2025 | 2025-09-30 13:56 | 2 | 2025-05-20 | 2025-09-30 | 2025-10-01 | 0% | 1563.36 | 2110.54 | 547.18
Martin & Lois Kesselring | 5 Woodhill Close, Research FC | 5WOODFC-0020 | 2025-09-24 | Declined on 25-09-2025 | 2025-09-25 12:15 | 5 | 2025-05-08 | 2025-09-25 | 2025-09-26 | 0% | 2017.2 | 2682.88 | 665.68
Alanna Vivian and Michael Juttner | 73 Somers Ave, Macleod FC | 73SOM-0009 | 2025-09-16 | Declined manually on 18-09-2025 by Greg Paull | 2025-09-18 15:59 | 0 | 2025-04-08 |  |  | 0% | 4422 | 5707.35 | 1285.35
Martin & Lois Kesselring | 5 Woodhill Close, Research FC | 5WOODFC-0012 | 2025-09-04 | Declined on 4-09-2025 | 2025-09-04 18:15 | 1 | 2025-05-20 | 2025-09-04 | 2025-09-06 | 0% | 650.55 | 1338.43 | 687.88
Martin & Lois Kesselring | 5 Woodhill Close, Research FC | 5WOODFC-0009 | 2025-08-29 | Declined on 2-09-2025 | 2025-09-02 09:47 | 1 | 2025-05-05 | 2025-09-02 | 2025-09-12 | 0% | 1377.59 | 1859.75 | 482.16
Martin & Lois Kesselring | 5 Woodhill Close, Research FC | 5WOODFC-0007 | 2025-08-29 | Declined on 1-09-2025 | 2025-09-01 09:52 | 1 | 2025-05-05 | 2025-09-01 | 2025-09-13 | 0% | 3592.5 | 4742.1 | 1149.6
Stefano Scalzo | 89 Glen Park Road, Eltham North FC | 89GP-0011 | 2025-06-19 | Declined manually on 24-06-2025 by Greg Paull | 2025-06-24 13:26 | 0 | 2025-04-08 | 2025-06-21 | 2025-06-27 | 0% | -3095 | -2695 | 400
Stefano Scalzo | 89 Glen Park Road, Eltham North FC | 89GP-0010 | 2025-06-17 | Declined on 21-06-2025 | 2025-06-21 16:50 | 1 | 2025-04-04 | 2025-06-21 | 2025-06-27 | 0% | 1083.75 | 1571.44 | 487.69
Stefano Scalzo | 89 Glen Park Road, Eltham North FC | 89GP-0004 | 2025-05-15 | Declined on 21-06-2025 | 2025-06-21 16:50 | 0 | 2025-04-08 | 2025-06-21 |  | 0% | 11775 | 14130 | 2355
Stefano Scalzo | 89 Glen Park Road, Eltham North FC | 89GP-0003 | 2025-05-15 | Declined on 21-06-2025 | 2025-06-21 16:50 | 0 | 2025-04-08 | 2025-06-21 |  | 0% | 15545 | 18654 | 3109
Stefano Scalzo | 89 Glen Park Road, Eltham North FC | 89GP-0002 | 2025-05-15 | Declined on 21-06-2025 | 2025-06-21 16:49 | 0 | 2025-04-08 | 2025-06-21 |  | 0% | 10445 | 12534 | 2089
Rudy Pilotto | 119 McIlwraith St - FC | 119MCIL-FC-0003 | 2025-02-26 | Declined on 6-03-2025 | 2025-03-06 08:48 | 1 | 2024-08-05 | 2025-03-06 |  | 0% | 25196 | 25196 | 0
[11 empty] | 822599.23 | 1094766.97 | 272167.74