## Customer Invoices
Invoices (exported on Thu, May 14, 2026)
OwnerName | Job | ID# | Title | Status | Invoice Amount | Amount Paid | Invoice Balance | Deadline | Date Paid | Date released | CreatedDate | Related COs
Jordan Crundwell | 1/55 Melbourne Ave, Glenroy Vic 3046 | MEL55-0001 | Deposit | Paid | 1070 | 1070 | 0 | 2026-03-31 | 2026-03-27 | 2026-03-24 | 2026-03-24 15:25
Tom Moore | 49 Kamarooka Drive Wattle Glen 3096 | 49KAM-0001 | Deposit | Paid | 1179.66 | 1179.66 | 0 | 2026-03-09 | 2026-03-02 | 2026-03-02 | 2026-03-02 18:06
Sophie Beaumont | 73 Fenwick St, Carlton North | 73FEN-0001 | Deposit | Paid | 1370.27 | 1370.27 | 0 | 2026-02-11 | 2026-02-11 | 2026-02-04 | 2026-02-04 17:32
Sandra Wing | 29 River Gum Close, Diamond Creek FC | 29RIV-0001 | Deposit | Paid | 12642.39 | 12642.39 | 0 | 2025-12-22 | 2025-12-15 | 2025-12-15 | 2025-12-15 09:00
Serene Ho | 30 Connolly Ave, Coburg - FC | 30CON-0001 | Deposit | Paid | 21954.99 | 21954.99 | 0 | 2025-12-15 | 2025-12-11 | 2025-12-08 | 2025-12-08 14:15
Hui Shi Peh | 150 Banksia Street, Ivanhoe - FC | 150BAN-0001 | Deposit | Draft | 0 | 0 | 0 | 2026-06-09 |  |  | 2025-11-19 11:18
Peter and Jenny Watt | 6 Myrtle Grove, Blackburn | 6MYR-0001 | Deposit | Draft | 0 | 0 | 0 |  |  |  | 2025-11-05 15:17
Rachel Shepheard | 17 Glyndon Ave - FC | 17GLYN-0001 | Deposit | Paid | 57767.26 | 57767.26 | 0 | 2025-11-06 | 2025-10-31 | 2025-10-30 | 2025-10-30 12:10
Michael Strachan | 3 Uvadale Grove, Kew | 3UVADALE-0001 | Deposit | Paid | 3355.26 | 3355.26 | 0 | 2025-10-09 | 2025-10-04 | 2025-10-03 | 2025-10-02 09:11
Mick Hall | 11-15 Station Street, Diamond Creek - FC | 11STA-0001 | Deposit | Paid | 32695.51 | 32695.51 | 0 | 2025-11-10 | 2025-11-07 | 2025-11-03 | 2025-09-09 13:50
Leah Reynolds Architect | 158 The Boulevard, Ivanhoe East | 158BLVD-0001 | Deposit | Draft | 18090.46 | 0 | 18090.46 | 2026-10-14 |  |  | 2025-08-25 13:27
David Chuter | 22 Longstaff St - Boundary Wall - FC | 22LONG-WALL-0001 | Deposit | Paid | 2565.63 | 2565.63 | 0 | 2025-07-25 | 2025-07-18 | 2025-07-18 | 2025-07-18 13:03
Suzi & Chris Harris | 37 Robinson St Moonee Ponds - FC | 37ROB-0001 | Deposit | Paid | 35257 | 35257 | 0 | 2025-07-09 | 2025-07-04 | 2025-07-02 | 2025-07-02 10:04
Martin & Lois Kesselring | 5 Woodhill Close, Research FC | 5WOODFC-0001 | Deposit | Paid | 16158.95 | 16158.95 | 0 | 2025-05-27 | 2025-05-29 | 2025-05-20 | 2025-05-20 15:42
Alanna Vivian and Michael Juttner | 73 Somers Ave, Macleod FC | 73SOM-0001 | Deposit | Paid | 28730.83 | 28730.83 | 0 | 2025-04-30 | 2025-04-26 | 2025-04-23 | 2025-04-23 15:40
Stefano Scalzo | 89 Glen Park Road, Eltham North FC | 89GP-0001 | Deposit as per contract | Paid | 22240.59 | 22240.59 | 0 | 2025-04-15 | 2025-04-12 | 2025-04-10 | 2025-04-09 09:15
Rudy Pilotto | 119 McIlwraith St - FC | 119MCIL-FC-0001 | Deposit | Paid | 84114.01 | 84114.01 | 0 | 2024-08-19 | 2024-08-15 | 2024-08-12 | 2024-08-12 17:23
Umut Akcelik | 105 Greythorn Rd - Downstairs Works | 105GREY-0001 | Deposit | Paid | 5443.34 | 5443.34 | 0 | 2023-09-20 | 2023-09-13 | 2023-09-13 | 2023-09-13 11:01
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0001D | Deposit for Construction works | Paid | 50597.89 | 50597.89 | 0 | 2023-08-31 | 2023-08-25 | 2023-08-23 | 2023-08-23 08:50
Jordan Crundwell | 1/55 Melbourne Ave, Glenroy Vic 3046 | MEL55-0002 | Demolition | Draft | 6420 | 0 | 6420 | 2026-06-02 |  |  | 2026-03-24 15:28
Tom Moore | 49 Kamarooka Drive Wattle Glen 3096 | 49KAM-0002 | Demolition | Paid | 7077.98 | 7077.98 | 0 | 2026-03-24 | 2026-03-17 | 2026-03-17 | 2026-03-02 18:08
Sophie Beaumont | 73 Fenwick St, Carlton North | 73FEN-0002 | Phase 1 Preliminaries | Paid | 6851.35 | 6851.35 | 0 | 2026-02-16 | 2026-02-20 | 2026-02-09 | 2026-02-04 17:34
Rachel Shepheard | 17 Glyndon Ave - FC | 17GLYN-0002 | Progress Claim #1 | Paid | 132221.7 | 132221.7 | 0 | 2025-12-30 | 2025-12-29 | 2025-12-23 | 2025-12-23 18:49
Sandra Wing | 29 River Gum Close, Diamond Creek FC | 29RIV-0002 | Window Ordering | Paid | 12642.39 | 12642.39 | 0 | 2026-02-20 | 2026-02-14 | 2026-02-13 | 2025-12-15 09:00
Hui Shi Peh | 150 Banksia Street, Ivanhoe - FC | 150BAN-0002 | Demolition Stage | Draft | 0 | 0 | 0 | 2026-06-15 |  |  | 2025-11-19 11:18
Peter and Jenny Watt | 6 Myrtle Grove, Blackburn | 6MYR-0002 | Demolition Stage | Draft | 0 | 0 | 0 |  |  |  | 2025-11-05 15:17
Michael Strachan | 3 Uvadale Grove, Kew | 3UVADALE-0002 | Plaster works | Paid | 13421.04 | 13421.04 | 0 | 2026-01-06 | 2025-12-30 | 2025-12-30 | 2025-10-02 09:14
Mick Hall | 11-15 Station Street, Diamond Creek - FC | 11STA-0002 | November Progress Claim | Paid | 94824.98 | 94824.98 | 0 | 2025-12-23 | 2025-12-21 | 2025-12-16 | 2025-09-09 13:50
Leah Reynolds Architect | 158 The Boulevard, Ivanhoe East | 158BLVD-0002 | Demolition Stage | Draft | 36180.93 | 0 | 36180.93 | 2026-11-29 |  |  | 2025-08-25 13:27
David Chuter | 22 Longstaff St - Boundary Wall - FC | 22LONG-WALL-0002 | Demolition | Paid | 23090.63 | 23090.63 | 0 | 2025-07-31 | 2025-07-30 | 2025-07-24 | 2025-07-18 13:03
Suzi & Chris Harris | 37 Robinson St Moonee Ponds - FC | 37ROB-0002 | Demolition | Paid | 70514 | 70514 | 0 | 2025-09-26 | 2025-09-25 | 2025-09-19 | 2025-07-02 10:04
Martin & Lois Kesselring | 5 Woodhill Close, Research FC | 5WOODFC-0002 | Demolition Progress Claim | Paid | 16158.95 | 16158.95 | 0 | 2025-06-04 | 2025-07-02 | 2025-06-17 | 2025-05-21 09:36
Alanna Vivian and Michael Juttner | 73 Somers Ave, Macleod FC | 73SOM-0002 | May Progress claim | Paid | 32124 | 32124 | 0 | 2025-05-30 | 2025-05-22 | 2025-05-20 | 2025-04-28 14:10
Stefano Scalzo | 89 Glen Park Road, Eltham North FC | 89GP-0002 | Demolition Stage as per contract | Paid | 22240.59 | 22240.59 | 0 | 2025-05-12 | 2025-05-12 | 2025-05-05 | 2025-04-09 09:17
Rudy Pilotto | 119 McIlwraith St - FC | 119MCIL-FC-0002 | Progress Claim #1 17.10.2024 | Paid | 39317.57 | 39317.57 | 0 | 2024-10-26 | 2024-10-21 | 2024-10-19 | 2024-10-17 16:08
Umut Akcelik | 105 Greythorn Rd - Downstairs Works | 105GREY-0002 | Demolition | Paid | 21773.37 | 21773.37 | 0 | 2023-10-18 | 2023-10-23 | 2023-10-11 | 2023-09-13 11:02
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0002 | Retentions - Deposit Stage | Pending/Sent | 2663.05 | 0 | 2663.05 | 2025-06-06 |  | 2023-08-25 | 2023-08-25 08:09
Jordan Crundwell | 1/55 Melbourne Ave, Glenroy Vic 3046 | MEL55-0003 | Membrane Installed | Draft | 6420 | 0 | 6420 | 2026-06-17 |  |  | 2026-03-24 15:29
Tom Moore | 49 Kamarooka Drive Wattle Glen 3096 | 49KAM-0003 | Tiling | Paid | 14155.97 | 14155.97 | 0 | 2026-04-06 | 2026-04-02 | 2026-03-30 | 2026-03-02 18:08
Sophie Beaumont | 73 Fenwick St, Carlton North | 73FEN-0003 | Phase 1 Construction | Paid | 10962.16 | 10962.16 | 0 | 2026-04-24 | 2026-05-06 | 2026-04-17 | 2026-02-04 17:35
Rachel Shepheard | 17 Glyndon Ave - FC | 17GLYN-0003 | Progress Claim #2 | Paid | 58540.35 | 58540.35 | 0 | 2026-02-06 | 2026-02-02 | 2026-01-30 | 2026-01-30 15:27
Sandra Wing | 29 River Gum Close, Diamond Creek FC | 29RIV-0003 | Garage Fire Separation work | Paid | 25284.76 | 25284.76 | 0 | 2026-04-08 | 2026-04-01 | 2026-03-25 | 2025-12-15 09:00
Serene Ho | 30 Connolly Ave, Coburg - FC | 30CON-0003 | Demolition Stage as per contract | Paid | 21954.99 | 21954.99 | 0 | 2026-03-07 | 2026-03-03 | 2026-02-28 | 2025-12-08 14:35
Hui Shi Peh | 150 Banksia Street, Ivanhoe - FC | 150BAN-0003 | Base stage | Draft | 0 | 0 | 0 | 2026-06-17 |  |  | 2025-11-19 11:18
Peter and Jenny Watt | 6 Myrtle Grove, Blackburn | 6MYR-0003 | Base stage | Draft | 0 | 0 | 0 | 2026-02-13 |  |  | 2025-11-05 15:17
Michael Strachan | 3 Uvadale Grove, Kew | 3UVADALE-0003 | Painting works | Paid | 16776.3 | 16776.3 | 0 | 2026-02-23 | 2026-02-18 | 2026-02-16 | 2025-10-02 09:15
Leah Reynolds Architect | 158 The Boulevard, Ivanhoe East | 158BLVD-0003 | Base stage | Draft | 54271.39 | 0 | 54271.39 | 2026-11-30 |  |  | 2025-08-25 13:27
David Chuter | 22 Longstaff St - Boundary Wall - FC | 22LONG-WALL-0003 | Frame | Draft | 23090.63 | 0 | 23090.63 |  |  |  | 2025-07-18 13:04
Suzi & Chris Harris | 37 Robinson St Moonee Ponds - FC | 37ROB-0003 | Frame | Paid | 211514.99 | 211514.99 | 0 | 2025-12-02 | 2025-12-11 | 2025-12-08 | 2025-07-02 10:05
Martin & Lois Kesselring | 5 Woodhill Close, Research FC | 5WOODFC-0003 | Base Progress Claim | Paid | 48476.84 | 48476.84 | 0 | 2025-06-30 | 2025-07-22 | 2025-07-16 | 2025-05-21 09:38
Alanna Vivian and Michael Juttner | 73 Somers Ave, Macleod FC | 73SOM-0003 | June Claim | Paid | 30560.85 | 30560.85 | 0 | 2025-06-23 | 2025-06-19 | 2025-06-18 | 2025-04-28 14:10
Stefano Scalzo | 89 Glen Park Road, Eltham North FC | 89GP-0003 | Base Stage as per contract | Paid | 44481.19 | 44481.19 | 0 | 2025-05-16 | 2025-07-23 | 2025-06-12 | 2025-04-09 09:18
Rudy Pilotto | 119 McIlwraith St - FC | 119MCIL-FC-0003 | Progress Claim #2 20.11.2024 | Paid | 80364.46 | 80364.46 | 0 | 2024-11-27 | 2024-11-26 | 2024-11-20 | 2024-11-20 09:16
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0003 | Progress Claim #3 | Paid | 5726.3 | 5726.3 | 0 | 2023-11-30 | 2023-12-01 | 2023-11-23 | 2023-11-23 15:28
Umut Akcelik | 105 Greythorn Rd - Downstairs Works | 105GREY-0003 | Waterproofing | Paid | 21773.37 | 21773.37 | 0 | 2023-11-23 | 2023-11-20 | 2023-11-16 | 2023-09-13 11:03
Jordan Crundwell | 1/55 Melbourne Ave, Glenroy Vic 3046 | MEL55-0004 | Tiling | Draft | 6420 | 0 | 6420 | 2026-06-29 |  |  | 2026-03-24 15:29
Tom Moore | 49 Kamarooka Drive Wattle Glen 3096 | 49KAM-0004 | Completion | Paid | 2122.53 | 2122.53 | 0 | 2026-04-27 | 2026-04-23 | 2026-04-20 | 2026-03-02 18:09 | 0001 - Flooring
Rachel Shepheard | 17 Glyndon Ave - FC | 17GLYN-0004 | Progress Claim #3 | Paid | 100065.15 | 100065.15 | 0 | 2026-03-07 | 2026-03-02 | 2026-02-28 | 2026-02-28 21:03
Michael Strachan | 3 Uvadale Grove, Kew | 3UVADALE-0004 | Fencing works | Paid | 26842.07 | 26842.07 | 0 | 2026-03-02 | 2026-02-18 | 2026-02-16 | 2025-12-30 13:55
Sandra Wing | 29 River Gum Close, Diamond Creek FC | 29RIV-0004 | 1st Wall complete | Paid | 50569.5 | 50569.5 | 0 | 2026-04-08 | 2026-04-03 | 2026-03-25 | 2025-12-15 09:00
Serene Ho | 30 Connolly Ave, Coburg - FC | 30CON-0004 | Frame | Paid | 65864.98 | 65864.98 | 0 | 2026-04-23 | 2026-04-20 | 2026-04-16 | 2025-12-08 14:35
Hui Shi Peh | 150 Banksia Street, Ivanhoe - FC | 150BAN-0004 | Frame stage | Draft | 0 | 0 | 0 | 2026-06-24 |  |  | 2025-11-19 11:18
Peter and Jenny Watt | 6 Myrtle Grove, Blackburn | 6MYR-0004 | Frame stage | Draft | 0 | 0 | 0 | 2026-02-17 |  |  | 2025-11-05 15:17
Mick Hall | 11-15 Station Street, Diamond Creek - FC | 11STA-0004 | January Progress Claim | Paid | 95415.71 | 95415.71 | 0 | 2026-02-07 | 2026-02-09 | 2026-01-31 | 2025-09-09 13:50
Leah Reynolds Architect | 158 The Boulevard, Ivanhoe East | 158BLVD-0004 | Frame stage | Draft | 90452.32 | 0 | 90452.32 | 2027-01-12 |  |  | 2025-08-25 13:27
David Chuter | 22 Longstaff St - Boundary Wall - FC | 22LONG-WALL-0004 | Completion | Draft | 2565.61 | 0 | 2565.61 |  |  |  | 2025-07-18 13:05
Suzi & Chris Harris | 37 Robinson St Moonee Ponds - FC | 37ROB-0004 | Lockup | Paid | 176284.99 | 176284.99 | 0 | 2025-12-30 | 2025-12-29 | 2025-12-23 | 2025-07-02 10:06
Martin & Lois Kesselring | 5 Woodhill Close, Research FC | 5WOODFC-0004 | Frame Progress Claim | Paid | 80794.74 | 80794.74 | 0 | 2025-07-31 | 2025-08-03 | 2025-07-24 | 2025-05-21 09:39
Alanna Vivian and Michael Juttner | 73 Somers Ave, Macleod FC | 73SOM-0004 | July Claim | Paid | 33036.97 | 33036.97 | 0 | 2025-07-25 | 2025-07-20 | 2025-07-18 | 2025-04-28 14:11
Stefano Scalzo | 89 Glen Park Road, Eltham North FC | 89GP-0004 | Frame stage as per contract | Paid | 88962.38 | 88962.38 | 0 | 2025-07-31 | 2025-08-08 | 2025-07-24 | 2025-04-09 09:19
Rudy Pilotto | 119 McIlwraith St - FC | 119MCIL-FC-0004 | Progress Claim #3 16.12.2024 | Paid | 97391.62 | 97391.62 | 0 | 2024-12-25 | 2024-12-19 | 2024-12-18 | 2024-12-16 15:35
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0004 | Retentions - Progress Claim #3 | Pending/Sent | 301.38 | 0 | 301.38 | 2025-06-06 |  | 2024-03-05 | 2023-11-23 15:30
Umut Akcelik | 105 Greythorn Rd - Downstairs Works | 105GREY-0004 | Tiling | Paid | 27216.72 | 27216.72 | 0 | 2023-11-30 | 2023-11-26 | 2023-11-23 | 2023-09-13 11:04
Rachel Shepheard | 17 Glyndon Ave - FC | 17GLYN-0005 | Progress Claim #4 | Paid | 127812.75 | 127812.75 | 0 | 2026-04-07 | 2026-04-07 | 2026-03-25 | 2026-03-25 14:03
Jordan Crundwell | 1/55 Melbourne Ave, Glenroy Vic 3046 | MEL55-0005 | Final Payment | Draft | 1070 | 0 | 1070 | 2026-07-07 |  |  | 2026-03-24 15:29
Michael Strachan | 3 Uvadale Grove, Kew | 3UVADALE-0005 | Final | Draft | 6710.52 | 0 | 6710.52 |  |  |  | 2025-12-30 13:56
Sandra Wing | 29 River Gum Close, Diamond Creek FC | 29RIV-0005 | 2nd Wall complete | Paid | 50569.5 | 50569.5 | 0 | 2026-04-21 | 2026-04-19 | 2026-04-14 | 2025-12-15 09:00
Serene Ho | 30 Connolly Ave, Coburg - FC | 30CON-0005 | Windows | Draft | 43909.99 | 0 | 43909.99 | 2026-05-05 |  |  | 2025-12-08 14:35
Hui Shi Peh | 150 Banksia Street, Ivanhoe - FC | 150BAN-0005 | Lockup stage | Draft | 0 | 0 | 0 | 2026-07-01 |  |  | 2025-11-19 11:18
Peter and Jenny Watt | 6 Myrtle Grove, Blackburn | 6MYR-0005 | Lockup stage | Draft | 0 | 0 | 0 | 2026-02-23 |  |  | 2025-11-05 15:17
Mick Hall | 11-15 Station Street, Diamond Creek - FC | 11STA-0005 | February Progress Claim | Paid | 118652.08 | 118652.08 | 0 | 2026-03-07 | 2026-03-09 | 2026-02-28 | 2025-09-09 13:50
Leah Reynolds Architect | 158 The Boulevard, Ivanhoe East | 158BLVD-0005 | Lockup stage | Draft | 90452.32 | 0 | 90452.32 | 2027-02-02 |  |  | 2025-08-25 13:27
Suzi & Chris Harris | 37 Robinson St Moonee Ponds - FC | 37ROB-0005 | Plaster | Paid | 105770.99 | 105770.99 | 0 | 2026-03-05 | 2026-03-03 | 2026-02-26 | 2025-07-02 10:07
Martin & Lois Kesselring | 5 Woodhill Close, Research FC | 5WOODFC-0005 | Lockup Progress Claim | Paid | 80794.74 | 80794.74 | 0 | 2025-09-11 | 2025-09-12 | 2025-09-04 | 2025-05-21 09:39
Alanna Vivian and Michael Juttner | 73 Somers Ave, Macleod FC | 73SOM-0005 | August Progress Claim | Paid | 64642.06 | 64642.06 | 0 | 2025-08-25 | 2025-08-25 | 2025-08-20 | 2025-04-28 14:11
Stefano Scalzo | 89 Glen Park Road, Eltham North FC | 89GP-0005 | Lockup Stage as per contract | Paid | 88962.38 | 88962.38 | 0 | 2025-09-18 | 2025-09-26 | 2025-09-11 | 2025-04-09 09:19
Rudy Pilotto | 119 McIlwraith St - FC | 119MCIL-FC-0005 | Progress Claim #4 16.01.2025 | Paid | 51612.77 | 51612.77 | 0 | 2025-01-23 | 2025-01-22 | 2025-01-16 | 2025-01-16 19:28
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0005 | Progress Claim #4 | Paid | 36167.81 | 36167.81 | 0 | 2023-12-27 | 2023-12-20 | 2023-12-20 | 2023-12-20 11:31
Umut Akcelik | 105 Greythorn Rd - Downstairs Works | 105GREY-0005 | Cabinetry | Paid | 27216.72 | 27216.72 | 0 | 2023-11-28 | 2023-11-24 | 2023-11-21 | 2023-09-13 11:05
Rachel Shepheard | 17 Glyndon Ave - FC | 17GLYN-0006 | Progress Claim #5 | Paid | 107043.05 | 107043.05 | 0 | 2026-05-07 | 2026-05-04 | 2026-04-30 | 2026-04-30 11:14
Sandra Wing | 29 River Gum Close, Diamond Creek FC | 29RIV-0006 | 3rd Wall complete stage | Paid | 50569.5 | 50569.5 | 0 | 2026-04-25 | 2026-04-24 | 2026-04-18 | 2025-12-15 09:00
Serene Ho | 30 Connolly Ave, Coburg - FC | 30CON-0006 | Lockup | Draft | 109774.95 | 0 | 109774.95 | 2026-05-20 |  |  | 2025-12-08 14:35
Hui Shi Peh | 150 Banksia Street, Ivanhoe - FC | 150BAN-0006 | Fix Stage | Draft | 0 | 0 | 0 | 2026-07-06 |  |  | 2025-11-19 11:18
Peter and Jenny Watt | 6 Myrtle Grove, Blackburn | 6MYR-0006 | Fix Stage | Draft | 0 | 0 | 0 | 2026-03-06 |  |  | 2025-11-05 15:17
Stefano Scalzo | 89 Glen Park Road, Eltham North FC | 89GP-0006 | Fix stage as per contract | Paid | 88962.38 | 88962.38 | 0 | 2025-10-30 | 2025-10-30 | 2025-10-23 | 2025-10-23 10:23
Mick Hall | 11-15 Station Street, Diamond Creek - FC | 11STA-0006 | March Progress Claim | Paid | 64831.58 | 64831.58 | 0 | 2026-04-08 | 2026-04-06 | 2026-03-25 | 2025-09-09 13:50
Leah Reynolds Architect | 158 The Boulevard, Ivanhoe East | 158BLVD-0006 | Fix Stage | Draft | 36180.93 | 0 | 36180.93 | 2027-02-23 |  |  | 2025-08-25 13:27
Suzi & Chris Harris | 37 Robinson St Moonee Ponds - FC | 37ROB-0006 | Fix | Paid | 70514 | 70514 | 0 | 2026-04-08 | 2026-04-15 | 2026-03-25 | 2025-07-02 10:07
Martin & Lois Kesselring | 5 Woodhill Close, Research FC | 5WOODFC-0006 | Fix Progress Claim | Paid | 48476.84 | 48476.84 | 0 | 2025-11-18 | 2025-11-14 | 2025-11-11 | 2025-05-21 09:41
Alanna Vivian and Michael Juttner | 73 Somers Ave, Macleod FC | 73SOM-0006 | September Progress Claim | Paid | 77594.15 | 77594.15 | 0 | 2025-09-29 | 2025-09-25 | 2025-09-22 | 2025-04-28 14:11
Rudy Pilotto | 119 McIlwraith St - FC | 119MCIL-FC-0006 | Progress Claim #4 16.01.2025 | Paid | 178173.25 | 178173.25 | 0 | 2025-02-24 | 2025-02-24 | 2025-02-17 | 2025-02-14 16:54
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0006 | Retentions - Progress Claim #4 | Pending/Sent | 1903.56 | 0 | 1903.56 | 2025-06-06 |  | 2024-03-05 | 2023-12-20 11:33
Umut Akcelik | 105 Greythorn Rd - Downstairs Works | 105GREY-0006 | Completion | Paid | 5443.35 | 5443.35 | 0 | 2023-12-22 | 2024-01-27 | 2023-12-15 | 2023-09-13 11:06
Sandra Wing | 29 River Gum Close, Diamond Creek FC | 29RIV-0007 | 4th Wall Complete Stage | Paid | 37927.13 | 37927.13 | 0 | 2026-04-25 | 2026-04-19 | 2026-04-18 | 2025-12-15 09:00
Serene Ho | 30 Connolly Ave, Coburg - FC | 30CON-0007 | Plaster | Draft | 65864.98 | 0 | 65864.98 | 2026-06-16 |  |  | 2025-12-08 14:35
Hui Shi Peh | 150 Banksia Street, Ivanhoe - FC | 150BAN-0007 | Completion stage | Draft | 0 | 0 | 0 | 2026-07-27 |  |  | 2025-11-19 11:18
Peter and Jenny Watt | 6 Myrtle Grove, Blackburn | 6MYR-0007 | Completion stage | Draft | 0 | 0 | 0 | 2026-03-17 |  |  | 2025-11-05 15:17
Mick Hall | 11-15 Station Street, Diamond Creek - FC | 11STA-0007 | April Progress Claim | Paid | 55346.01 | 55346.01 | 0 | 2026-05-07 | 2026-05-07 | 2026-04-30 | 2025-09-09 13:50
Leah Reynolds Architect | 158 The Boulevard, Ivanhoe East | 158BLVD-0007 | Completion stage | Draft | 36180.93 | 0 | 36180.93 | 2027-04-10 |  |  | 2025-08-25 13:27
Suzi & Chris Harris | 37 Robinson St Moonee Ponds - FC | 37ROB-0007 | Completion | Paid | 35257 | 35257 | 0 | 2026-04-19 | 2026-05-06 | 2026-04-14 | 2025-07-02 10:08
Martin & Lois Kesselring | 5 Woodhill Close, Research FC | 5WOODFC-0007 | Completion Progress Claim | Paid | 31858.06 | 31858.06 | 0 | 2025-12-22 | 2025-12-22 | 2025-12-15 | 2025-05-21 09:42 | 0024 - Painting - Existing House 0023 - CREDIT - Supply and Installation of stone benchtop
Alanna Vivian and Michael Juttner | 73 Somers Ave, Macleod FC | 73SOM-0007 | October Claim | Paid | 95290.47 | 95290.47 | 0 | 2025-10-28 | 2025-10-26 | 2025-10-21 | 2025-04-28 14:12
Stefano Scalzo | 89 Glen Park Road, Eltham North FC | 89GP-0007 | Completion stage as per contract | Paid | 88962.38 | 88962.38 | 0 | 2025-12-17 | 2025-12-22 | 2025-12-12 | 2025-04-09 09:21
Rudy Pilotto | 119 McIlwraith St - FC | 119MCIL-FC-0007 | Progress Claim #6 17.03.2025 | Paid | 124265.48 | 124265.48 | 0 | 2025-03-24 | 2025-03-24 | 2025-03-17 | 2025-03-17 11:32
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0007 | Progress Claim #5 | Paid | 26763.4 | 26763.4 | 0 | 2024-01-30 | 2024-01-25 | 2024-01-23 | 2024-01-23 17:11
Umut Akcelik | 105 Greythorn Rd - Downstairs Works | 105GREY-0007 | Cabinetry - Variations | Paid | 2769.63 | 2769.63 | 0 | 2023-11-30 | 2023-11-24 | 2023-11-23 | 2023-11-23 07:12 | 0002 - Emergency plumbing works 0001 - Construction Items
Sandra Wing | 29 River Gum Close, Diamond Creek FC | 29RIV-0008 | Final Payment upon Completion | Draft | 12642.36 | 0 | 12642.36 |  |  |  | 2025-12-15 09:00
Serene Ho | 30 Connolly Ave, Coburg - FC | 30CON-0008 | Fix | Draft | 87819.95 | 0 | 87819.95 | 2026-06-19 |  |  | 2025-12-08 14:35
Suzi & Chris Harris | 37 Robinson St Moonee Ponds - FC | 37ROB-0008 | Variations #1 | Paid | 33537.07 | 33537.07 | 0 | 2025-12-15 | 2025-12-11 | 2025-12-08 | 2025-12-08 14:22 | 0008 - Cellar Works 0003 - Engineering Revisions - Kitchen Roof 0001 - Studio Hot Water Service 0006 - Kitchen Flooring Works 0005 - Bathroom Floor Replacement 0004 - Front Lounge subfloor 0002 - Adjustment to Studio hot water
Mick Hall | 11-15 Station Street, Diamond Creek - FC | 11STA-0008 | May Progress Claim | Draft | 0 | 0 | 0 | 2026-05-22 |  |  | 2025-12-08 14:22
Martin & Lois Kesselring | 5 Woodhill Close, Research FC | 5WOODFC-0008 | Variations Complete to Base stage | Paid | 2200 | 2200 | 0 | 2025-07-23 | 2025-07-17 | 2025-07-16 | 2025-07-16 16:17 | 0001 - Additional Demolition - Fireplace
Stefano Scalzo | 89 Glen Park Road, Eltham North FC | 89GP-0008 | Variations complete to demoliton stage | Paid | 925 | 925 | 0 | 2025-05-12 | 2025-05-12 | 2025-05-05 | 2025-05-05 12:00 | 0001 - Removal of 8 M3 spoil
Alanna Vivian and Michael Juttner | 73 Somers Ave, Macleod FC | 73SOM-0008 | November Progress Claim | Paid | 102743.15 | 102743.15 | 0 | 2025-11-28 | 2025-11-26 | 2025-11-21 | 2025-04-28 14:12
Rudy Pilotto | 119 McIlwraith St - FC | 119MCIL-FC-0008 | Progress Claim #7 15.04.2025 | Paid | 265298.04 | 265298.04 | 0 | 2025-04-22 | 2025-04-22 | 2025-04-15 | 2025-04-08 12:11
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0008 | Retentions - Progress Claim #5 | Pending/Sent | 1408.6 | 0 | 1408.6 | 2025-06-06 |  | 2024-03-05 | 2024-01-23 17:12
Umut Akcelik | 105 Greythorn Rd - Downstairs Works | 105GREY-0008 | Final Items | Paid | 1789.74 | 1789.74 | 0 | 2023-12-22 | 2024-01-27 | 2023-12-15 | 2023-12-15 13:28 | 0004 - Replacement Vanity Unit 0005 - Extra tiling 0003 - Kitchen waste pipe alteration
Suzi & Chris Harris | 37 Robinson St Moonee Ponds - FC | 37ROB-0009 | Variations #2 | Paid | 6519.25 | 6519.25 | 0 | 2025-12-30 | 2025-12-30 | 2025-12-23 | 2025-12-23 12:30 | 0012 - Study Velux change 0011 - Tiling Supply 0009 - Floor Grinding
Serene Ho | 30 Connolly Ave, Coburg - FC | 30CON-0009 | Final Payment upon Completion | Draft | 21954.95 | 0 | 21954.95 | 2026-08-13 |  |  | 2025-12-08 14:35
Mick Hall | 11-15 Station Street, Diamond Creek - FC | 11STA-0009 | June Progress Claim | Draft | 0 | 0 | 0 | 2026-09-25 |  |  | 2025-12-08 14:22
Martin & Lois Kesselring | 5 Woodhill Close, Research FC | 5WOODFC-0009 | Variations complete to Fix Stage | Paid | 13404.73 | 13404.73 | 0 | 2025-11-24 | 2025-11-21 | 2025-11-17 | 2025-11-17 09:19 | 0019 - Cabinetry - Change to Red Heart Eucalypt Veneer 0006 - Additional Heating Duct Point 0010 - Electrical - General 0018 - CREDIT - Heater Repair 0011 - Electrical - Flood Light 0021 - Electrical - Power for Blinds - Remote
Stefano Scalzo | 89 Glen Park Road, Eltham North FC | 89GP-0009 | Variaitons complete to Base stage | Paid | 820 | 820 | 0 | 2025-06-19 | 2025-06-21 | 2025-06-12 | 2025-06-12 13:07 | 0005 - Remove and Dispose of existing underfloor ducting
Rudy Pilotto | 119 McIlwraith St - FC | 119MCIL-FC-0009 | Progress Claim #8 16.04.2025 | Paid | 150955.54 | 150955.54 | 0 | 2025-05-23 | 2025-05-23 | 2025-05-16 | 2025-05-16 16:00
Alanna Vivian and Michael Juttner | 73 Somers Ave, Macleod FC | 73SOM-0009 | December Claim | Paid | 77108.12 | 77108.12 | 0 | 2025-12-23 | 2025-12-18 | 2025-12-16 | 2025-04-28 14:13
Umut Akcelik | 105 Greythorn Rd - Downstairs Works | 105GREY-0009 | Progressive Invoice | Paid | 22428.75 | 22428.75 | 0 | 2024-06-21 | 2024-06-14 | 2024-06-14 | 2024-06-14 14:52 | 0006 - Additional Works
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0009 | Progress Claim #6 | Paid | 81909.95 | 81909.95 | 0 | 2024-03-10 | 2024-03-05 | 2024-03-03 | 2024-03-03 19:33
Sandra Wing | 29 River Gum Close, Diamond Creek FC | 29RIV-0010 | Variations complete to 1st Wall stage | Paid | 36264.41 | 36264.41 | 0 | 2026-04-08 | 2026-04-01 | 2026-03-31 | 2026-03-31 15:50 | 0004 - Electrical - Smoke Alarms 0003 - Electrical - First Floor Lighting 0008 - Electrical - Illume Skylight 0001 - Roofing - Upper Roof
Martin & Lois Kesselring | 5 Woodhill Close, Research FC | 5WOODFC-0010 | Electrical Switchboard Upgrade | Pending/Sent | 3671.64 | 0 | 3671.64 | 2026-04-06 |  | 2026-03-30 | 2026-03-30 03:05 | 0008 - Electrical - Switchboard Option 1
Serene Ho | 30 Connolly Ave, Coburg - FC | 30CON-0010 | Variations complete to demolition stage | Paid | 2904 | 2904 | 0 | 2026-03-07 | 2026-03-03 | 2026-02-28 | 2026-02-28 06:37 | 0002 - Asbestos Removal
Suzi & Chris Harris | 37 Robinson St Moonee Ponds - FC | 37ROB-0010 | Variations #3 | Paid | 1628 | 1628 | 0 | 2026-03-05 | 2026-02-26 | 2026-02-26 | 2026-02-26 14:01 | 0013 - Re Pointing Mud room wall 0007 - Solar provision
Mick Hall | 11-15 Station Street, Diamond Creek - FC | 11STA-0010 | November Progress Claim PT1 | Paid | 30000 | 30000 | 0 |  | 2025-12-17 | 2025-12-17 | 2025-12-17 10:12
Stefano Scalzo | 89 Glen Park Road, Eltham North FC | 89GP-0010 | Variations Complete to Lockup Stage | Paid | 9082.1 | 9082.1 | 0 | 2025-09-18 | 2025-10-06 | 2025-09-11 | 2025-09-11 14:34 | 0013 - Electrical - Additional GPO 0014 - Electrical - Unearthed Cabling 0024 - Electrical - External Light Fitting Supply Only 0016 - Electrical - Master Bed GPO 0012 - Revisions to Cabinetry V2 0008 - Sound proof insulation between bed 2 and 3 0017 - Electrical - Additional Light To Hallway 0019 - Additional Timber - Kitchen Shelf 0022 - Change Front cladding to horizontal
Rudy Pilotto | 119 McIlwraith St - FC | 119MCIL-FC-0010 | Progress Claim #9 16.06.2025 | Paid | 196536.32 | 196536.32 | 0 | 2025-06-23 | 2025-06-23 | 2025-06-16 | 2025-06-16 11:54
Alanna Vivian and Michael Juttner | 73 Somers Ave, Macleod FC | 73SOM-0010 | Retentions - May 2025 | Paid | 3569.33 | 3569.33 | 0 | 2025-12-11 | 2025-12-21 | 2025-05-20 | 2025-05-20 15:04
Umut Akcelik | 105 Greythorn Rd - Downstairs Works | 105GREY-0010 | Further Variations | Paid | 41983.25 | 41983.25 | 0 | 2024-08-22 | 2024-08-19 | 2024-08-15 | 2024-08-15 15:40 | 0014 - Additional Electrical Works 0015 - Aircon System in downstairs billiard room 0007 - Tap replacement in garden 0011 - Extra Door Sill Works 0016 - Dining Air Con Boxing 0019 - Carport bluestone clean 0006 - Additional Works 0017 - Glass inserts to replace mesh 0013 - Additional Electrical Supply Works 0010 - New studio electric blind
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0010 | Retentions - Progress Claim #6 | Pending/Sent | 4311.06 | 0 | 4311.06 | 2025-06-06 |  | 2024-03-05 | 2024-03-03 19:36
Serene Ho | 30 Connolly Ave, Coburg - FC | 30CON-0011 | Variations complete to Frame stage | Paid | 1101.98 | 1101.98 | 0 | 2026-04-23 | 2026-04-20 | 2026-04-16 | 2026-04-16 17:29 | 0003 - Verandah Posts 0004 - Dimensions
Sandra Wing | 29 River Gum Close, Diamond Creek FC | 29RIV-0011 | Variations complete to wall 2 stage | Partially Paid | 10606.23 | 5606.23 | 5000 | 2026-04-21 |  | 2026-04-14 | 2026-04-14 06:40 | 0011 - Retaining Wall - Rear LH side of Garage 0009 - Watertank - Relocation 0010 - Retaining Wall - Front LH side of Garage
Suzi & Chris Harris | 37 Robinson St Moonee Ponds - FC | 37ROB-0011 | Variations #4 | Paid | 32272.7 | 32272.7 | 0 | 2026-04-08 | 2026-04-02 | 2026-03-25 | 2026-03-25 14:14 | 0026 - Solid Plaster - PS Reconciliation 0020 - Window Replacement 0017 - Laundry Step 0022 - Plumbing Items 0023 - Brass hinges supply 0019 - Plumbing works - Tap 0010 - Cabinetry - PS Reconciliation 0015 - Cellar trapdoor access door - Upgrade
Mick Hall | 11-15 Station Street, Diamond Creek - FC | 11STA-0011 | January Progress Claim | Paid | 30000 | 30000 | 0 | 2026-02-11 | 2026-02-04 | 2026-02-04 | 2026-02-04 15:31
Stefano Scalzo | 89 Glen Park Road, Eltham North FC | 89GP-0011 | Variations complete to Fix Stage | Paid | 15785.34 | 15785.34 | 0 | 2025-10-30 | 2025-11-07 | 2025-10-23 | 2025-10-23 09:28 | 0032 - Entrance Door - Supply Incl Delivery 0025 - Electrical - External Light Bed 1 0027 - Entrance Door - Swing Other Way 0030 - Excavations to Front Yard 0026 - Electrical - External Light Front Porch 0018 - Cabinetry - Robe door adjustment and fit out
Rudy Pilotto | 119 McIlwraith St - FC | 119MCIL-FC-0011 | Progress Claim #10 15.07.2025 | Paid | 97419.57 | 97419.57 | 0 | 2025-07-22 | 2025-07-22 | 2025-07-15 | 2025-07-15 14:06
Alanna Vivian and Michael Juttner | 73 Somers Ave, Macleod FC | 73SOM-0011 | Var Approved (to bal prj - must end up at $0) | Draft | 0 | 0 | 0 |  |  |  | 2025-06-17 15:23 | 0003 - Reconciliation of Windows & Doors PC and PS 0001 - Remove Floating Floor Throughout House
Umut Akcelik | 105 Greythorn Rd - Downstairs Works | 105GREY-0011 | Remaining variations | Paid | 505.7 | 505.7 | 0 | 2024-10-09 | 2025-04-26 | 2024-10-02 | 2024-10-02 17:55 | 0020 - Curtain remote 0018 - Fly screens
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0011 | Progress Claim #7 | Paid | 156579 | 156579 | 0 | 2024-03-27 | 2024-03-25 | 2024-03-20 | 2024-03-20 13:56
Sandra Wing | 29 River Gum Close, Diamond Creek FC | 29RIV-0012 | Variations complete to 4th wall stage | Paid | 5777.33 | 5777.33 | 0 | 2026-04-25 | 2026-04-21 | 2026-04-18 | 2026-04-18 15:11 | 0006 - Electrical - Credit 0005 - Electrical - General 0013 - 29RIV-0013
Suzi & Chris Harris | 37 Robinson St Moonee Ponds - FC | 37ROB-0012 | Variations #5 | Paid | 4661.3 | 4661.3 | 0 | 2026-04-19 | 2026-04-15 | 2026-04-14 | 2026-04-14 15:19 | 0025 - Benchtop Reconciliation #2 0024 - Bricklayer - Repointing works
Stefano Scalzo | 89 Glen Park Road, Eltham North FC | 89GP-0012 | Variations complete to completion stage | Paid | 29543.31 | 29543.31 | 0 | 2025-12-19 | 2026-02-09 | 2025-12-12 | 2025-12-12 12:36 | 0031 - Concrete 0029 - Additional Door Furniture 0033 - Electrical - Garden Light 0044 - Additional Concrete Steppers 0038 - Spoil Removal, additional green waste removal 0036 - Electrical - Mirror Wiring
Rudy Pilotto | 119 McIlwraith St - FC | 119MCIL-FC-0012 | Progress Claim #11 15.08.2025 | Paid | 220752.29 | 220752.29 | 0 | 2025-08-22 | 2025-08-21 | 2025-08-15 | 2025-08-15 12:45
Alanna Vivian and Michael Juttner | 73 Somers Ave, Macleod FC | 73SOM-0012 | Retentions - June 2025 | Paid | 3395.66 | 3395.66 | 0 | 2025-11-24 | 2025-12-21 | 2025-06-18 | 2025-06-18 10:32
Umut Akcelik | 105 Greythorn Rd - Downstairs Works | 105GREY-0012 | Burst Pipe Works | Paid | 998.33 | 998.33 | 0 | 2025-05-23 | 2025-05-18 | 2025-05-17 | 2025-05-12 10:34
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0012 | Retentions - Progress Claim #7 | Pending/Sent | 8241.08 | 0 | 8241.08 | 2025-06-06 |  | 2024-03-20 | 2024-03-20 13:58
Suzi & Chris Harris | 37 Robinson St Moonee Ponds - FC | 37ROB-0013 | Variations #5.1 | Draft | 5000 | 0 | 5000 |  |  |  | 2026-04-14 15:24
Stefano Scalzo | 89 Glen Park Road, Eltham North FC | 89GP-0013 | Deck sealing | Pending/Sent | 2972.8 | 0 | 2972.8 | 2026-04-06 |  | 2026-03-30 | 2026-03-30 02:41 | 0045 - Painting - Stain Deck 0046 - Painting - Stairs and Balustrade
Rudy Pilotto | 119 McIlwraith St - FC | 119MCIL-FC-0013 | Progress Claim #12 15.09.2025 | Paid | 105550.17 | 105550.17 | 0 | 2025-09-23 | 2025-09-23 | 2025-09-15 | 2025-09-15 15:02
Alanna Vivian and Michael Juttner | 73 Somers Ave, Macleod FC | 73SOM-0013 | Retentions - July 2025 | Paid | 3670.77 | 3670.77 | 0 | 2025-11-24 | 2025-12-21 | 2025-07-18 | 2025-07-18 15:08
Umut Akcelik | 105 Greythorn Rd - Downstairs Works | 105GREY-0013 | Painting Works | Paid | 3731 | 3731 | 0 | 2025-07-09 | 2025-07-14 | 2025-07-02 | 2025-07-02 08:53 | 0022 - Painting Works
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0013 | Progress Claim #8 | Paid | 121663.65 | 121663.65 | 0 | 2024-04-29 | 2024-05-03 | 2024-04-22 | 2024-04-22 12:25
Rudy Pilotto | 119 McIlwraith St - FC | 119MCIL-FC-0014 | Progress Claim #13 15.10.2025 | Paid | 89668.18 | 89668.18 | 0 | 2025-10-22 | 2025-10-22 | 2025-10-15 | 2025-10-15 17:18
Alanna Vivian and Michael Juttner | 73 Somers Ave, Macleod FC | 73SOM-0014 | Retentions August 2025 | Partially Paid | 7182.45 | 3729.67 | 3452.78 | 2025-11-24 |  | 2025-08-20 | 2025-08-15 16:27
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0014 | Retentions - Progress Claim #8 | Pending/Sent | 6403.35 | 0 | 6403.35 | 2025-06-06 |  | 2024-04-22 | 2024-04-22 12:26
Rudy Pilotto | 119 McIlwraith St - FC | 119MCIL-FC-0015 | Progress Claim #14 17.11.2025 | Paid | 133269.57 | 133269.57 | 0 | 2025-11-24 | 2025-11-24 | 2025-11-17 | 2025-11-17 19:30
Alanna Vivian and Michael Juttner | 73 Somers Ave, Macleod FC | 73SOM-0015 | Retentions September 2025 | Pending/Sent | 8621.57 | 0 | 8621.57 | 2025-12-11 |  | 2025-09-22 | 2025-09-22 14:41
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0015 | Progress Claim #9 | Paid | 101708.9 | 101708.9 | 0 | 2024-06-04 | 2024-06-03 | 2024-05-21 | 2024-05-21 11:12
Rudy Pilotto | 119 McIlwraith St - FC | 119MCIL-FC-0016 | Progress Claim #15 15.12.2025 | Paid | 95944.84 | 95944.84 | 0 | 2025-12-23 | 2025-12-23 | 2025-12-16 | 2025-12-15 17:48
Alanna Vivian and Michael Juttner | 73 Somers Ave, Macleod FC | 73SOM-0016 | Retentions October 2025 | Pending/Sent | 2291.08 | 0 | 2291.08 | 2025-12-11 |  | 2025-10-21 | 2025-10-21 12:38
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0016 | Retentions - Progress Claim #9 | Pending/Sent | 5353.11 | 0 | 5353.11 | 2025-06-06 |  | 2024-05-21 | 2024-05-21 11:14
Rudy Pilotto | 119 McIlwraith St - FC | 119MCIL-FC-0017 | Progress Claim #16 21.04.2026 | Paid | 30089.45 | 30089.45 | 0 | 2026-04-28 | 2026-04-27 | 2026-04-21 | 2026-03-31 12:44
Alanna Vivian and Michael Juttner | 73 Somers Ave, Macleod FC | 73SOM-0017 | January Progress Claim | Paid | 28214.2 | 28214.2 | 0 | 2026-05-05 | 2026-05-03 | 2026-04-28 | 2025-12-16 09:35
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0017 | Progress Claim #10 | Paid | 80492.55 | 80492.55 | 0 | 2024-07-08 | 2024-07-08 | 2024-06-24 | 2024-06-24 14:57
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0018 | Retentions - Progress Claim #10 | Pending/Sent | 4236.54 | 0 | 4236.54 | 2025-06-06 |  | 2024-06-24 | 2024-06-24 14:59
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0019 | Progress Claim #11 | Paid | 58772.7 | 58772.7 | 0 | 2024-08-02 | 2024-07-29 | 2024-07-19 | 2024-07-19 11:46
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0020 | Retentions - Progress Claim #11 | Pending/Sent | 3093.3 | 0 | 3093.3 | 2025-06-06 |  | 2024-07-19 | 2024-07-19 11:49
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0021 | Progress Claim #12 | Paid | 79570.1 | 79570.1 | 0 | 2024-09-04 | 2024-09-09 | 2024-08-21 | 2024-08-21 16:11
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0022 | Retentions - Progress Claim #12 | Pending/Sent | 3134.4 | 0 | 3134.4 | 2025-06-06 |  | 2024-08-21 | 2024-08-21 16:13
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0023 | Progress Claim #13 | Paid | 68089.35 | 68089.35 | 0 | 2024-10-07 | 2024-10-04 | 2024-09-23 | 2024-09-23 15:42
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0024 | Retentions - Progress Claim #13 | Pending/Sent | 3583.98 | 0 | 3583.98 | 2025-06-06 |  | 2024-09-23 | 2024-09-23 15:45
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0025 | Progress Claim #14 | Paid | 70501.4 | 70501.4 | 0 | 2024-11-05 | 2024-11-14 | 2024-10-22 | 2024-10-22 20:32
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0026 | Retentions - Progress Claim #13 | Pending/Sent | 3710.66 | 0 | 3710.66 | 2025-06-06 |  | 2024-10-22 | 2024-10-22 20:35
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0027 | Progress Claim #15 | Paid | 66373.65 | 66373.65 | 0 | 2024-12-09 | 2024-12-09 | 2024-11-25 | 2024-11-25 16:58
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0028 | Retentions - Progress Claim #15 | Pending/Sent | 3492.89 | 0 | 3492.89 | 2025-06-06 |  | 2024-11-25 | 2024-11-25 16:59
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0029 | Progress Claim #16 | Paid | 37004.4 | 37004.4 | 0 | 2025-01-03 | 2025-01-03 | 2024-12-20 | 2024-12-20 16:11
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0030 | Retentions - Progress Claim #16 | Pending/Sent | 1947.62 | 0 | 1947.62 | 2025-06-06 |  | 2024-12-20 | 2024-12-20 16:13
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0031 | Progress Claim #17 | Paid | 24815.25 | 24815.25 | 0 | 2025-02-18 | 2025-02-17 | 2025-02-04 | 2025-02-04 07:45
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0032 | Retentions - Progress Claim #17 | Pending/Sent | 1306.09 | 0 | 1306.09 | 2025-06-06 |  | 2025-02-24 | 2025-02-24 14:11
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0033 | Progress Claim #18 | Paid | 33498.6 | 33498.6 | 0 | 2025-03-10 | 2025-03-17 | 2025-02-24 | 2025-02-24 14:34
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0034 | Retentions - Progress Claim #18 | Pending/Sent | 1762.83 | 0 | 1762.83 | 2025-06-06 |  | 2025-02-24 | 2025-02-24 14:35
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0035 | Progress Claim #19 | Paid | 15965.7 | 15965.7 | 0 | 2025-04-03 | 2025-04-05 | 2025-03-20 | 2025-03-20 12:32
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0036 | Retentions - Progress Claim #19 | Pending/Sent | 840.27 | 0 | 840.27 | 2025-06-06 |  | 2025-03-20 | 2025-03-20 12:34
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0037 | Progress Claim #20 | Paid | 11252.75 | 11252.75 | 0 | 2025-05-07 | 2025-05-07 | 2025-04-23 | 2025-04-23 12:22
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0038 | Retentions - Progress Claim #20 | Pending/Sent | 592.66 | 0 | 592.66 | 2025-06-06 |  | 2025-04-23 | 2025-04-23 12:23
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0039 | Progress Claim #21 | Paid | 30986.15 | 30986.15 | 0 | 2025-05-26 | 2025-05-21 | 2025-05-19 | 2025-05-19 14:32
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0040 | Retentions - Progress Claim #21 | Pending/Sent | 1630.44 | 0 | 1630.44 | 2025-06-06 |  | 2025-05-19 | 2025-05-19 15:05
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0041 | Progress Claim #22 | Paid | 23632.2 | 23632.2 | 0 | 2025-06-16 | 2025-06-17 | 2025-06-02 | 2025-06-02 21:11
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0042 | Retentions - Progress Claim #22 | Pending/Sent | 1246.72 | 0 | 1246.72 | 2025-06-09 |  | 2025-06-02 | 2025-06-02 21:12
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0043 | Deck Works | Paid | 13187.9 | 13187.9 | 0 | 2025-10-20 | 2025-10-16 | 2025-10-13 | 2025-10-13 13:31
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0044 | Retentions - Deck Works | Draft | 336.91 | 0 | 336.91 |  |  |  | 2025-10-13 13:34
Steffen Welsch | 63 Albert Street, Brunswick | 63ALBERT-0045 | Additional Rear Fence Works | Paid | 2388.32 | 2388.32 | 0 | 2025-12-15 | 2025-12-15 | 2025-12-08 | 2025-12-08 15:05
Greg Test Lead | 1 Robbies Road, Yarrambat 3091 | RO-test again | test again | Pending/Sent | 100 | 0 | 100 | 2022-12-14 |  | 2022-12-08 | 2022-12-08 10:53
[5 empty] | 8115651.98 | 7266568.39 | 849083.59