## Purchase Orders
Purchase Orders (exported on Thu, May 14, 2026)
Job | PO # | Title | PO Status | Work Status | Performed By | Created Date | Cost | Paid | Cost Code | Variance Code | Est. Complete | Files | RFIs
17 Glyndon Ave - FC | 17GLYN-0029 | Brick cleaning | Sent | Not Complete | Resurfix Pty Ltd | 2026-05-13 10:28 | 330 | Not Paid | Brickwork - General |  | 2026-05-13 |  | -
29 River Gum Close, Diamond Creek FC | 29RIV-0020 | Electrical - Front External Lights | Sub/Vendor Approved - 07-05-26 | Not Complete | DECAV Pty Ltd | 2026-05-07 18:50 | 220.95 | Not Paid | Electrical | 72 - Customer change order |  |  | -
17 Glyndon Ave - FC | 17GLYN-0028 | Brick laying | Approved by Dale Psaila - 10-05-26 | Work Complete by Dale Psaila - 11-05-2026 | Brick on Brick Pty Ltd | 2026-05-07 13:42 | 6008.75 | Fully Paid | Brickwork - Brick Layer |  | 2026-05-08 | 1 | -
17 Glyndon Ave - FC | 17GLYN-0027 | Blocked stormwater | Sent | Not Complete | JCB Plumbing & Maintenance | 2026-05-07 10:40 | 350 | Not Paid | Plumbing & Drainage |  | 2026-05-12 |  | -
801 Main Hurstbridge Road FC | 801MN-0010 | Vinyl - 801 Main Hurstbridge Road | Sent | Not Complete | Flooring Xtra Thomastown | 2026-05-07 06:37 | 5550 | Partially Paid | Vinyl Flooring |  |  | 1 | -
801 Main Hurstbridge Road FC | 801MN-0009 | Flooring to Salon - Hybrid | Sent | Not Complete | Flooring Xtra Thomastown | 2026-05-07 06:35 | 9795 | Partially Paid | Carpentry Labour - Timber Flooring Vinyl Flooring (+1)... | 72 - Customer change order |  |  | -
11-15 Station Street, Diamond Creek - FC | 11STA-0028 | Sliding Gate Motor | Sent | Not Complete | Victorian Commercial Gates and Fencing | 2026-05-06 13:15 | 2832.5 | Partially Paid | Garage Doors Garage Doors (+1)... | 72 - Customer change order |  | 1 | -
11-15 Station Street, Diamond Creek - FC | 11STA-0027 | Electrical - Amp and Mic Set up. | Sub/Vendor Approved - 06-05-26 | Not Complete | DECAV Pty Ltd | 2026-05-06 13:08 | 1989.57 | Not Paid | Electrical | 72 - Customer change order |  | 2 | -
11-15 Station Street, Diamond Creek - FC | 11STA-0026 | Security - Extra Camera | Sent | Not Complete | Metro Lock | 2026-05-06 13:08 | 231.41 | Not Paid | Electrical - Security Alarm System Electrical - Security Alarm System (+1)... | 72 - Customer change order |  |  | -
17 Glyndon Ave - FC | 17GLYN-0026 | Sound insulation | Approved by Dale Psaila - 10-05-26 | Work Complete by Dale Psaila - 11-05-2026 | Pride Insulation | 2026-05-06 09:49 | 649.85 | Fully Paid | Insulation - Supply & Install |  | 2026-05-08 | 4 | -
801 Main Hurstbridge Road FC | 801MN-0008 | Electrical - Speaker System | Sub/Vendor Approved - 06-05-26 | Not Complete | DECAV Pty Ltd | 2026-05-06 05:37 | 2463.21 | Not Paid | Electrical | 72 - Customer change order |  | 2 | -
30 Connolly Ave, Coburg - FC | 30CON-0013 | Blocked storm water | Approved by Dale Psaila - 10-05-26 | Work Complete by Dale Psaila - 11-05-2026 | JCB Plumbing & Maintenance | 2026-05-04 11:25 | 385 | Fully Paid | Plumbing & Drainage Plumbing & Drainage (+1)... | 21 - Price change | 2026-05-07 | 1 | -
17 Glyndon Ave - FC | 17GLYN-0025 | Velux Skylights | Sent | Not Complete | Insulite Pty Ltd | 2026-04-30 20:31 | 910.15 | Not Paid | Awning/Hoods / Privacy Screens MATERIALS ONLY |  | 2026-05-08 | 1 | -
17 Glyndon Ave - FC | 17GLYN-0024 | Insulation | Approved by Dale Psaila - 05-05-26 | Work Complete by Dale Psaila - 5-05-2026 | Pride Insulation | 2026-04-30 20:14 | 3385.61 | Fully Paid | Insulation - Supply & Install |  | 2026-05-05 | 1 | -
801 Main Hurstbridge Road FC | 801MN-0007 | Plastering | Sent | Not Complete | Stanislovas Gecevicius Plasterer | 2026-04-30 12:08 | 10422.5 | Partially Paid | Plastering |  |  | 1 | -
801 Main Hurstbridge Road FC | 801MN-0006 | Painting | Sub/Vendor Approved - 30-04-26 | Not Complete | MS Paterson Painting and Decorating | 2026-04-30 12:07 | 5920 | Not Paid | Painting |  |  |  | -
801 Main Hurstbridge Road FC | 801MN-0005 | 801 Main Hurstbridge road - Heating and Cooling | Sub/Vendor Approved - 30-04-26 | Not Complete | Everlasting Air | 2026-04-30 11:56 | 7350 | Not Paid | Air Conditioning |  |  | 2 | -
801 Main Hurstbridge Road FC | 801MN-0004 | 801 Main Hurstbridge Road - Electrical | Sub/Vendor Approved - 30-04-26 | Not Complete | DECAV Pty Ltd | 2026-04-30 11:53 | 18983.85 | Partially Paid | Electrical |  |  | 4 | -
801 Main Hurstbridge Road FC | 801MN-0003 | Plumbing - 801 Main Hurstbridge Road | Sent | Not Complete | JCB Plumbing & Maintenance | 2026-04-30 11:52 | 17270 | Not Paid | Plumbing & Drainage |  |  | 2 | -
801 Main Hurstbridge Road FC | 801MN-0002 | Electrical Variation | Sub/Vendor Approved - 30-04-26 | Not Complete | DECAV Pty Ltd | 2026-04-30 11:45 | 821.76 | Not Paid | Electrical | 72 - Customer change order | 2026-06-13 |  | -
801 Main Hurstbridge Road FC | 801MN-0001 | Security - Cameras | Sub/Vendor Approved - 08-05-26 | Not Complete | Metro Lock | 2026-04-30 11:39 | 4503.89 | Not Paid | Electrical - Security Alarm System | 72 - Customer change order |  | 2 | -
17 Glyndon Ave - FC | 17GLYN-0023 | Plaster(VLS) | Sub/Vendor Approved - 29-04-26 | Work Complete by Dale Psaila - 11-05-2026 | VLS Plastering | 2026-04-29 11:49 | 43681 | Not Paid | Plastering Plastering (+1)... |  | 2026-05-01 | 2 | -
89 Glen Park Road, Eltham North FC | 89GP-0047 | Plumbing - Extra Works | Sent | Not Complete | JCB Plumbing & Maintenance | 2026-04-27 09:46 | 638 | Fully Paid | Plumbing & Drainage Plumbing - Gas Connection (+1)... | 72 - Customer change order |  | 1 | -
30 Connolly Ave, Coburg - FC | 30CON-0012 | Roof Plumbing | Approved by Dale Psaila - 23-04-26 | Work Complete by Dale Psaila - 24-04-2026 | Ahearn Roofing | 2026-04-24 09:56 | 8195 | Partially Paid | Roofing - Fascia & Gutter |  | 2026-04-23 | 2 | -
17 Glyndon Ave - FC | 17GLYN-0022 | Internal door #2 | Sub/Vendor Approved - 23-04-26 | Work Complete by Dale Psaila - 11-05-2026 | All Timber Windows | 2026-04-23 21:43 | 1485 | Fully Paid | Windows & Doors - Timber MATERIALS ONLY |  |  | 2 | -
37 Robinson St Moonee Ponds - FC | 37ROB-0044 | Caulking | Draft | Not Complete | The Caulking Group | 2026-04-23 12:36 | 1039.5 | Fully Paid | Water Proofing |  | 2026-04-20 | 1 | -
37 Robinson St Moonee Ponds - FC | 37ROB-0043 | Solar panel skylight | Approved by Clive Webster - 30-04-26 | Not Complete | Insulite Pty Ltd | 2026-04-21 15:28 | 970 | Not Paid | Roofing - Sky Lights / Whirly Birds |  | 2026-05-01 | 1 | -
49 Kamarooka Drive Wattle Glen 3096 | 49KAM-0002 | Flooring | Sub/Vendor Approved - 21-04-26 | Work Complete by Dale Psaila - 23-04-2026 | Ken Built Timber Floors (T&C 15 Trading Pty Ltd) | 2026-04-19 20:14 | 660 | Fully Paid | Floor Sanding & Polishing | 72 - Customer change order |  | 1 | -
29 River Gum Close, Diamond Creek FC | 29RIV-0019 | 29RIV-0013 | Sub/Vendor Approved - 14-04-26 | Work Complete by Dale Psaila - 23-04-2026 | DECAV Pty Ltd | 2026-04-15 06:31 | 185 | Fully Paid | Electrical | 72 - Customer change order |  | 1 | -
1/55 Melbourne Ave, Glenroy Vic 3046 | MEL55-0003 | Pedestals | Sub/Vendor Approved - 14-04-26 | Not Complete | Keksia Raised Floor Systems | 2026-04-10 15:43 | 181.17 | Fully Paid | Tiles - Supply MATERIALS ONLY |  |  | 1 | -
1/55 Melbourne Ave, Glenroy Vic 3046 | MEL55-0002 | Pavers | Sub/Vendor Approved - 11-04-26 | Not Complete | Beaumont Tiles PRESTON STORE | 2026-04-10 15:40 | 737.59 | Fully Paid | Tiles - Supply MATERIALS ONLY |  |  | 1 | -
37 Robinson St Moonee Ponds - FC | 37ROB-0042 | House Clean | Sub/Vendor Approved - 17-04-26 | Work Complete by Dale Psaila - 23-04-2026 | BLAS Maintenance Services | 2026-04-09 11:40 | 1800 | Fully Paid | House Cleaner |  | 2026-04-20 | 1 | -
1/55 Melbourne Ave, Glenroy Vic 3046 | MEL55-0001 | Waterproofing (Butynol Supply and install) | Sent | Not Complete | The Waterproofers | 2026-04-08 14:16 | 1426.15 | Not Paid | Water Proofing |  |  | 1 | -
11-15 Station Street, Diamond Creek - FC | 11STA-0025 | Glass Entrance Doors | Approved by Dale Psaila - 23-04-26 | Work Complete by Dale Psaila - 23-04-2026 | All Timber Windows | 2026-04-03 08:37 | 1738 | Fully Paid | Windows & Doors - Timber MATERIALS ONLY | 72 - Customer change order |  | 2 | -
37 Robinson St Moonee Ponds - FC | 37ROB-0040 | Bricklayer - Repointing works | Approved by Clive Webster - 02-04-26 | Work Complete by Dale Psaila - 23-04-2026 | Brick on Brick Pty Ltd | 2026-04-02 12:34 | 2420 | Fully Paid | Brickwork - Brick Layer | 72 - Customer change order |  | 11 | -
17 Glyndon Ave - FC | 17GLYN-0020 | Window Refurbishment | Approved by Dale Psaila - 10-05-26 | Work Complete by Dale Psaila - 11-05-2026 | Thermawood Yarra Merri-bek | 2026-04-01 12:31 | 15492.38 | Not Paid | Windows & Doors - Glazing |  | 2026-04-18 | 2 | -
11-15 Station Street, Diamond Creek - FC | 11STA-0024 | Hebel Carport | Approved by Dale Psaila - 07-05-26 | Work Complete by Dale Psaila - 7-05-2026 | Plaster Wholesalers | 2026-03-30 16:21 | 3949 | Fully Paid | Cladding - Hebel - MATERIALS ONLY |  |  | 1 | -
37 Robinson St Moonee Ponds - FC | 37ROB-0039 | Glass replacement | Approved by Dale Psaila - 23-04-26 | Work Complete by Dale Psaila - 23-04-2026 | All Points Glass | 2026-03-30 10:05 | 260 | Fully Paid | Windows & Doors - Glazing |  | 2026-04-01 | 3 | -
29 River Gum Close, Diamond Creek FC | 29RIV-0018 | Plastering | Approved by Dale Psaila - 01-04-26 | Work Complete by Dale Psaila - 1-04-2026 | Stanislovas Gecevicius Plasterer | 2026-03-30 09:43 | 5200 | Fully Paid | Plastering |  |  | 1 | -
49 Kamarooka Drive Wattle Glen 3096 | 49KAM-0001 | Shower Screen | Sub/Vendor Approved - 27-03-26 | Work Complete by Dale Psaila - 23-04-2026 | Executive Robes and Screens | 2026-03-27 07:39 | 874.5 | Fully Paid | Shower Screens & Mirrors |  |  | 1 | -
17 Glyndon Ave - FC | 17GLYN-0019 | Cabinetry | Sent | Not Complete | Borella Kitchens & Joinery | 2026-03-27 07:17 | 124870 | Partially Paid | Cabinet Maker Cabinet Maker Cabinet Maker Cabinet Maker Cabinet Maker Cabinet Maker Cabinet Maker Cabinet Maker Cabinet Maker Cabinet Maker Cabinet Maker Cabinet Maker Cabinet Maker Cabinet Maker Cabinet Maker Cabinet Maker Cabinet Maker Cabinet Maker Cabinet Maker Cabinet Maker Cabinet Maker Cabinet Maker Cabinet Maker Cabinet Maker (+23)... | 11 - Omitted from estimate 72 - Customer change order |  | 2 | -
17 Glyndon Ave - FC | 17GLYN-0018 | James Hardie- Cladding | Approved by Dale Psaila - 25-03-26 | Work Complete by Dale Psaila - 11-05-2026 | Mitre 10 Diamond Creek | 2026-03-26 10:33 | 11907.25 | Partially Paid | Timber Supply - Cladding MATERIALS ONLY Timber Supply - Cladding MATERIALS ONLY (+1)... |  | 2026-04-25 | 4 | -
29 River Gum Close, Diamond Creek FC | 29RIV-0017 | Watertank - Relocation | Sent | Not Complete | JCB Plumbing & Maintenance | 2026-03-24 06:22 | 3278 | Fully Paid | Plumbing & Drainage Plumbing & Drainage (+1)... | 11 - Omitted from estimate |  | 1 | -
29 River Gum Close, Diamond Creek FC | 29RIV-0016 | Watertank - Relocation | Sub/Vendor Approved - 23-03-26 | Work Complete by Dale Psaila - 23-04-2026 | DECAV Pty Ltd | 2026-03-24 06:22 | 159 | Fully Paid | Electrical | 72 - Customer change order |  | 1 | -
89 Glen Park Road, Eltham North FC | 89GP-0046 | Benchtop Replacement | Sent | Not Complete | Borella Kitchens & Joinery | 2026-03-23 16:35 | 550 | Fully Paid | Cabinet Maker - Bench Tops |  |  | 2 | -
89 Glen Park Road, Eltham North FC | 89GP-0045 | Plumbingjcb | Sent | Not Complete | JCB Plumbing & Maintenance | 2026-03-23 16:31 | 506 | Fully Paid | Plumbing & Drainage |  |  | 2 | -
37 Robinson St Moonee Ponds - FC | 37ROB-0038 | Hot Water Service | Sub/Vendor Approved - 18-03-26 | Work Complete by Dale Psaila - 23-04-2026 | Bentons Heidelberg | 2026-03-18 10:30 | 3274.4 | Fully Paid | Plumbing - Fixtures & Fittings MATERIALS ONLY Plumbing - Fixtures & Fittings MATERIALS ONLY (+1)... |  |  | 2 | -
37 Robinson St Moonee Ponds - FC | 37ROB-0037 | Final Clean | Draft | Not Complete | BLAS Maintenance Services | 2026-03-17 14:57 | 0 | Not Paid | House Cleaner |  | 2026-04-15 |  | -
37 Robinson St Moonee Ponds - FC | 37ROB-0036 | Plaster repairs | Draft | Not Complete | VLS Plastering | 2026-03-17 13:26 | 0 | Not Paid | Plastering |  | 2026-03-20 | 7 | -
17 Glyndon Ave - FC | 17GLYN-0017 | Paving Slab | Sub/Vendor Approved - 17-03-26 | Work Complete by Dale Psaila - 25-03-2026 | Metro Concrete Works | 2026-03-10 07:18 | 10010 | Fully Paid | Concrete - Driveways & Pathways |  | 2026-03-27 | 2 | -
11-15 Station Street, Diamond Creek - FC | 11STA-0023 | Door Furniture | Sub/Vendor Approved - 05-03-26 | Not Complete | All Secure Locksmiths | 2026-03-06 07:13 | 5413 | Partially Paid | Door Hardware MATERIALS ONLY |  |  | 2 | -
17 Glyndon Ave - FC | 17GLYN-0016 | Ladenko Sliding Door Unit | Approved by Dale Psaila - 01-04-26 | Work Complete by Dale Psaila - 1-04-2026 | B & C Doors | 2026-03-05 12:56 | 1815 | Fully Paid | Windows & Doors - Timber MATERIALS ONLY |  |  | 4 | -
29 River Gum Close, Diamond Creek FC | 29RIV-0015 | Insulation - Material | Approved by Dale Psaila - 16-03-26 | Work Complete by Dale Psaila - 16-03-2026 | Pride Insulation | 2026-03-04 18:37 | 1122 | Fully Paid | Insulation - Supply & Install |  |  |  | -
37 Robinson St Moonee Ponds - FC | 37ROB-0035 | Shower Screens | Approved by Dale Psaila - 16-03-26 | Work Complete by Dale Psaila - 16-03-2026 | Stevens Glass | 2026-03-03 11:16 | 2816 | Fully Paid | Shower Screens & Mirrors |  | 2026-03-06 | 2 | -
30 Connolly Ave, Coburg - FC | 30CON-0010 | Insulation | Sent | Not Complete | Pride Insulation | 2026-02-27 15:14 | 4437 | Not Paid | Insulation - Supply & Install |  | 2026-05-09 | 1 | -
30 Connolly Ave, Coburg - FC | 30CON-0009 | Windows and Doors | Sub/Vendor Approved - 03-03-26 | Not Complete | MCG Windows | 2026-02-27 07:10 | 18675 | Partially Paid | Windows & Doors - Aluminium MATERIALS ONLY |  | 2026-03-20 | 5 | -
29 River Gum Close, Diamond Creek FC | 29RIV-0014 | Split System Air Conditioners - reinstallation | Sub/Vendor Approved - 27-02-26 | Not Complete | Everlasting Air | 2026-02-27 06:33 | 3140 | Not Paid | Air Conditioning |  |  | 1 | -
29 River Gum Close, Diamond Creek FC | 29RIV-0013 | Airconditioner - Bed 3 | Sub/Vendor Approved - 27-02-26 | Not Complete | Everlasting Air | 2026-02-27 05:55 | 2510 | Not Paid | Air Conditioning |  |  | 1 | -
29 River Gum Close, Diamond Creek FC | 29RIV-0012 | Electrical - Illume Skylight | Sub/Vendor Approved - 27-02-26 | Work Complete by Dale Psaila - 1-04-2026 | DECAV Pty Ltd | 2026-02-27 05:50 | 698.85 | Fully Paid | Electrical | 72 - Customer change order |  | 1 | -
30 Connolly Ave, Coburg - FC | 30CON-0008 | Cavity Sliders | Approved by Dale Psaila - 23-04-26 | Work Complete by Dale Psaila - 23-04-2026 | B & C Doors | 2026-02-26 11:47 | 3459.5 | Fully Paid | Timber Supply - Fix MATERIALS ONLY |  | 2026-06-13 | 5 | -
29 River Gum Close, Diamond Creek FC | 29RIV-0011 | Roofing - Upper Roof | Sub/Vendor Approved - 27-02-26 | Not Complete | Everlasting Air | 2026-02-26 10:20 | 1570 | Not Paid | Air Conditioning | 72 - Customer change order |  |  | -
29 River Gum Close, Diamond Creek FC | 29RIV-0010 | Roofing - Upper Roof | Sub/Vendor Approved - 26-02-26 | Work Complete by Dale Psaila - 23-04-2026 | DECAV Pty Ltd | 2026-02-26 10:20 | 500 | Fully Paid | Electrical | 72 - Customer change order |  | 1 | -
29 River Gum Close, Diamond Creek FC | 29RIV-0009 | Roofing - Upper Roof | Sub/Vendor Approved - 28-02-26 | Work Complete by Dale Psaila - 1-04-2026 | Ahearn Roofing | 2026-02-26 10:20 | 15883 | Fully Paid | Roofing | 72 - Customer change order |  | 1 | -
29 River Gum Close, Diamond Creek FC | 29RIV-0008 | Electrical - First Floor Lighting | Sub/Vendor Approved - 26-02-26 | Work Complete by Dale Psaila - 16-03-2026 | DECAV Pty Ltd | 2026-02-26 10:19 | 1692.35 | Fully Paid | Electrical | 72 - Customer change order |  | 1 | -
11-15 Station Street, Diamond Creek - FC | 11STA-0022 | Plumbing - Kitchen | Sub/Vendor Approved - 28-02-26 | Work Complete by Dale Psaila - 7-05-2026 | JCB Plumbing & Maintenance | 2026-02-26 10:16 | 638 | Fully Paid | Plumbing & Drainage | 72 - Customer change order |  | 1 | -
30 Connolly Ave, Coburg - FC | 30CON-0007 | Steel Posts and Brackets | Approved by Dale Psaila - 01-04-26 | Work Complete by Dale Psaila - 16-03-2026 | Sutton Steel | 2026-02-24 18:51 | 3928.1 | Fully Paid | Steel - Posts & Beams |  | 2026-02-27 | 2 | -
37 Robinson St Moonee Ponds - FC | 37ROB-0033 | Borella kitchens | Approved by Dale Psaila - 01-04-26 | Work Complete by Dale Psaila - 1-04-2026 | Borella Kitchens & Joinery | 2026-02-24 18:36 | 350 | Fully Paid | Cabinet Maker |  | 2026-03-13 | 1 | -
37 Robinson St Moonee Ponds - FC | 37ROB-0032 | Painting | Sub/Vendor Approved - 31-03-26 | Work Complete by Dale Psaila - 23-04-2026 | APS Painting & Decorating Pty Ltd | 2026-02-23 16:00 | 21878 | Fully Paid | Painting Painting (+1)... |  | 2026-04-16 | 5 | -
29 River Gum Close, Diamond Creek FC | 29RIV-0007 | Electrical - Smoke Alarms | Sub/Vendor Approved - 23-02-26 | Work Complete by Dale Psaila - 16-03-2026 | DECAV Pty Ltd | 2026-02-23 09:18 | 1145.8 | Fully Paid | Electrical | 72 - Customer change order |  | 1 | -
29 River Gum Close, Diamond Creek FC | 29RIV-0006 | Electrical - General | Sub/Vendor Approved - 23-02-26 | Work Complete by Dale Psaila - 23-04-2026 | DECAV Pty Ltd | 2026-02-23 09:18 | 5947.11 | Fully Paid | Electrical | 72 - Customer change order |  | 1 | -
29 River Gum Close, Diamond Creek FC | 29RIV-0005 | Roof Plumbing - Lower Roofs | Sub/Vendor Approved - 02-03-26 | Work Complete by Dale Psaila - 23-04-2026 | Ahearn Roofing | 2026-02-19 09:23 | 7128 | Fully Paid | Roofing - Fascia & Gutter |  |  | 4 | -
11-15 Station Street, Diamond Creek - FC | 11STA-0021 | Tiles - Supply | Sub/Vendor Approved - 18-02-26 | Work Complete by Dale Psaila - 16-03-2026 | National Tiles (South Morang) | 2026-02-18 11:16 | 744.46 | Fully Paid | Tiles - Supply MATERIALS ONLY |  |  | 3 | -
11-15 Station Street, Diamond Creek - FC | 11STA-0020 | **Carpet Supply and Install | Sent | Not Complete | Flooring Xtra Thomastown | 2026-02-17 14:18 | 13000 | Partially Paid | Carpet |  |  | 3 | -
29 River Gum Close, Diamond Creek FC | 29RIV-0004 | Cladding | Approved by Dale Psaila - 23-04-26 | Work Complete by Dale Psaila - 23-04-2026 | Mitre 10 Diamond Creek | 2026-02-17 13:55 | 9591.27 | Fully Paid | Timber Supply - Cladding MATERIALS ONLY Timber Supply - Frame MATERIALS ONLY (+1)... |  | 2026-03-02 | 2 | -
37 Robinson St Moonee Ponds - FC | 37ROB-0031 | Plumbing works - Tap | Sub/Vendor Approved - 24-02-26 | Work Complete by Jacquie Bell - 2-03-2026 | JCB Plumbing & Maintenance | 2026-02-16 21:36 | 528 | Fully Paid | Plumbing & Drainage | 72 - Customer change order | 2026-02-27 | 1 | -
17 Glyndon Ave - FC | 17GLYN-0015 | Shower base ENS | Approved by Dale Psaila - 05-05-26 | Work Complete by Dale Psaila - 5-05-2026 | Mitre 10 Diamond Creek | 2026-02-16 19:39 | 2303.62 | Fully Paid | Tiling - MATERIALS ONLY Timber Supply - Frame MATERIALS ONLY Timber Supply - Frame MATERIALS ONLY Timber Supply - Frame MATERIALS ONLY (+3)... |  | 2026-03-06 | 1 | -
30 Connolly Ave, Coburg - FC | 30CON-0006 | Concrete Stage 1 Bored Piers | Approved by Dale Psaila - 23-02-26 | Work Complete by Dale Psaila - 23-02-2026 | Trade Alliance | 2026-02-16 18:25 | 1276 | Not Paid | Concrete - Supply MATERIALS ONLY |  | 2026-02-17 | 1 | -
29 River Gum Close, Diamond Creek FC | 29RIV-0003 | Insulation - Rockwool | Approved by Dale Psaila - 01-04-26 | Work Complete by Dale Psaila - 1-04-2026 | Pride Insulation | 2026-02-13 11:27 | 1316 | Fully Paid | Insulation MATERIALS ONLY |  | 2026-02-17 | 2 | -
479367