## schedule-percent-complete-by-jo
Job name | Job status | Project type | % complete of job | Projected completion date
1 18 Mihil St | Open | Other - Residential Remodeler | 0
1/55 Melbourne Ave, Glenroy Vic 3046 | Open | Other - Residential Remodeler | 0
10 Irvine Rd - balcony Repair | Open | Decks & Porches | 0
10 Vincent Street - Coburg | Open | Addition | 0
105 Greythorn Rd - Downstairs Works | Open | Bathroom | 0
11-15 Station Street, Diamond Creek - FC | Open | Addition | 69.68 | 2026-07-22T14:00:00
115 Normanby Rd, Kew East | Open | Other - Residential Remodeler | 0
119 McIlwraith St - FC | Open | Addition | 92.54 | 2025-11-16T13:00:00
150 Banksia Street, Ivanhoe - FC | Open | Bathroom | 0
158 The Boulevard, Ivanhoe East | Open | Addition | 0
17 Glyndon Ave - FC | Open | Other - Residential Remodeler | 62.32 | 2026-08-25T14:00:00
22 Longstaff St - Boundary Wall - FC | Open | Other - Residential Homebuilder | 72.73 | 2027-12-31T13:00:00
29 River Gum Close, Diamond Creek FC | Open | Whole Home Remodel | 97.37 | 2026-09-13T14:00:00
3 Uvadale Grove, Kew | Open | Other - Residential Remodeler | 100 | 2025-11-26T13:00:00
30 Connolly Ave, Coburg - FC | Open | Addition | 46.18 | 2026-09-08T14:00:00
37 Robinson St Moonee Ponds - FC | Open | Addition | 84.12 | 2026-04-08T14:00:00
49 Kamarooka Drive Wattle Glen 3096 | Open | Bathroom | 100 | 2026-04-26T14:00:00
5 Woodhill Close, Research FC | Open | Renovate/Resell | 100 | 2025-11-17T13:00:00
6 Myrtle Grove, Blackburn | Open | Bathroom | 0
6.1 Marshall Place, Clifton Hill | Open | Other - Residential Remodeler | 0
63 Albert Street, Brunswick | Open | Addition | 100
73 Fenwick St, Carlton North | Open | Other - Residential Remodeler | 100 | 2026-02-05T13:00:00
73 Somers Ave, Macleod FC | Open | Other - Residential Remodeler | 100 | 2026-02-09T13:00:00
801 Main Hurstbridge Road FC | Open | Addition | 30 | 2026-06-30T03:36:44
89 Glen Park Road, Eltham North FC | Open | Other - Residential Remodeler | 100 | 2025-11-06T13:00:00
Sample Job | Open | Sample Job | 11.55
Trailer | Open | Infrastructure/Utilities | 94.72
Transform Homes Boys | Open | Custom New Home | 5.24
Transform Homes Project Overview | Open | Other - Residential Homebuilder | 79.31