## Schedules
Schedule - List - 6 Myrtle Grove, Blackburn (exported on May 14, 2026)
ID # | Title | Complete | Percent Complete | Phase | Duration | Start | End | Assigned To | Accepted | Pending | Declined | Pred 1 Id | Pred 1 Type | Pred 1 Lag
1 | PRE-START MEETING | FALSE | 0 |  | 1 | 2026-05-14 | 2026-05-14 |  | 0 | 0 | 0
2 | Make Safe | FALSE | 0 |  | 1 | 2026-05-15 | 2026-05-15 |  | 0 | 0 | 0 | 3 | FS | -1
3 | Site Setup | FALSE | 0 |  | 1 | 2026-05-15 | 2026-05-15 |  | 0 | 0 | 0 | 1 | FS | 0
4 | Demolition works | FALSE | 0 |  | 3 | 2026-05-18 | 2026-05-20 |  | 0 | 0 | 0 | 2 | FS | 0
5 | Inspection of Timber Frame - Repairs as required | FALSE | 0 |  | 2 | 2026-05-21 | 2026-05-22 |  | 0 | 0 | 0 | 4 | FS | 0
6 | Plumbing Rough in | FALSE | 0 |  | 1 | 2026-05-25 | 2026-05-25 |  | 0 | 0 | 0 | 5 | FS | 0
7 | Electrical Rough In | FALSE | 0 |  | 1 | 2026-05-26 | 2026-05-26 |  | 0 | 0 | 0 | 6 | FS | 0
8 | Plaster Works (MR Board) | FALSE | 0 |  | 2 | 2026-05-27 | 2026-05-28 |  | 0 | 0 | 0 | 7 | FS | 0
9 | Waterproofing/Water Stops | FALSE | 0 |  | 1 | 2026-05-29 | 2026-05-29 |  | 0 | 0 | 0 | 8 | FS | 0
10 | Membrane Curing Time | FALSE | 0 |  | 3 | 2026-06-01 | 2026-06-03 |  | 0 | 0 | 0 | 9 | FS | 0
11 | Install underfloor heating | FALSE | 0 |  | 1 | 2026-06-04 | 2026-06-04 |  | 0 | 0 | 0 | 10 | FS | 0
12 | Tiling (Inc Niches) | FALSE | 0 |  | 4 | 2026-06-05 | 2026-06-11 |  | 0 | 0 | 0 | 11 | FS | 0
13 | Painting | FALSE | 0 |  | 2 | 2026-06-12 | 2026-06-15 |  | 0 | 0 | 0 | 12 | FS | 0
14 | Plumbing Fitoff | FALSE | 0 |  | 1 | 2026-06-16 07:00 | 2026-06-16 11:00 |  | 0 | 0 | 0 | 13 | FS | 0
15 | Electrical Fitoff | FALSE | 0 |  | 1 | 2026-06-16 11:30 | 2026-06-16 16:00 |  | 0 | 0 | 0 | 14 | FS | -1
16 | Reinstall S/Screen, Vanity, Holders | FALSE | 0 |  | 1 | 2026-06-17 | 2026-06-17 |  | 0 | 0 | 0 | 15 | FS | 0
17 | Caulking | FALSE | 0 |  | 1 | 2026-06-18 | 2026-06-18 |  | 0 | 0 | 0 | 16 | FS | 0
18 | Final Clean | FALSE | 0 |  | 1 | 2026-06-19 | 2026-06-19 |  | 0 | 0 | 0 | 17 | FS | 0
19 | Handover | FALSE | 0 |  | 1 | 2026-06-22 | 2026-06-22 |  | 0 | 0 | 0 | 18 | FS | 0