## work-in-progress-report-2026051
Job name | Revised client price | Projected costs | Actual costs | Amount invoiced | % complete of job | Projected profit | Projected profit % | Earned revenue | Over/under billing | Over/under billing % | Profit earned
1/55 Melbourne Ave, Glenroy Vic 3046 | 21400 | 12917.39 | 1798.08 | 1070 | 14 | 8482.61 | 39.64 | 2978.85 | -1908.85 | -8.92 | 1180.77
105 Greythorn Rd - Downstairs Works | 182074.94 | 182458.65 | 130957.99 | 183073.27 | 72 | -383.71 | -0.21 | 130682.59 | 52390.68 | 28.77 | -275.4
11-15 Station Street, Diamond Creek - FC | 711645.22 | 530438.86 | 418287.85 | 521765.87 | 79 | 181206.36 | 25.46 | 561181.64 | -39415.77 | -5.54 | 142893.79
115 Normanby Rd, Kew East | 16896.65 | 11991.01 | 9375.01 | 16896.65 | 78 | 4905.64 | 29.03 | 13210.42 | 3686.23 | 21.82 | 3835.41
119 McIlwraith St - FC | 1447941.6 | 1499050.36 | 1499050.36 | 2040723.13 | 100 | -51108.76 | -3.53 | 1447941.6 | 592781.53 | 40.94 | -51108.76
150 Banksia Street, Ivanhoe - FC | 87752.5 | 65675.36 | 855.36 |  | 1 | 22077.14 | 25.16 | 1142.89 | -1142.89 | -1.3 | 287.53
17 Glyndon Ave - FC | 1242323.03 | 933170.04 | 490575.69 | 583450.26 | 53 | 309152.99 | 24.89 | 653100.13 | -69649.87 | -5.61 | 162524.44
22 Longstaff St - Boundary Wall - FC | 55249.1 | 40477.46 | 21738.46 | 25656.26 | 54 | 14771.64 | 26.74 | 29671.58 | -4015.32 | -7.27 | 7933.12
29 River Gum Close, Diamond Creek FC | 305811.14 | 166696.93 | 136786.09 | 292853.14 | 82 | 139114.21 | 45.49 | 250938.7 | 41914.44 | 13.71 | 114152.61
3 Uvadale Grove, Kew | 73658.2 | 37957.04 | 36530.35 | 60394.67 | 96 | 35701.16 | 48.47 | 70889.61 | -10494.94 | -14.25 | 34359.26
30 Connolly Ave, Coburg - FC | 450782.46 | 279823.41 | 146217.66 | 113780.94 | 52 | 170959.05 | 37.92 | 235549.83 | -121768.89 | -27.01 | 89332.17
37 Keam Street, Ivanhoe East Prelim Design | 6305 | 6010.03 | 2060.03 | 2662.5 | 34 | 294.97 | 4.68 | 2161.14 | 501.36 | 7.95 | 101.11
37 Robinson St Moonee Ponds - FC | 792500.99 | 668208.31 | 645438.31 | 783731.29 | 97 | 124292.68 | 15.68 | 765495.57 | 18235.72 | 2.3 | 120057.26
49 Kamarooka Drive Wattle Glen 3096 | 24536.14 | 9948.97 | 9948.97 | 24536.14 | 100 | 14587.17 | 59.45 | 24536.14 | 0 | 0 | 14587.17
5 Woodhill Close, Research FC | 341995.49 | 221636.59 | 231316.59 | 341995.49 | 104 | 120358.9 | 35.19 | 356932.18 | -14936.69 | -4.37 | 125615.59
63 Albert Street, Brunswick | 1257811.01 | 1109881.81 | 1101285.15 | 1258811.51 | 99 | 147929.2 | 11.76 | 1248068.55 | 10742.96 | 0.85 | 146783.4
73 Somers Ave, Macleod FC | 599976.25 | 534837.05 | 534837.05 | 598775.66 | 100 | 65139.2 | 10.86 | 599976.25 | -1200.59 | -0.2 | 65139.2
801 Main Hurstbridge Road FC | 198190.71 | 140696.94 | 30515.98 |  | 22 | 57493.77 | 29.01 | 42985.89 | -42985.89 | -21.69 | 12469.91
89 Glen Park Road, Eltham North FC | 520166.74 | 414431.08 | 413831.08 | 503940.44 | 100 | 105735.66 | 20.33 | 519413.66 | -15473.22 | -2.97 | 105582.58